## Cover
EBRORA
ebrora.com
EA / Planning / Highways
Consent Tracker
Track consent conditions from regulatory authorities through to
compliance, evidence submission, and formal discharge.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Consent Tracker' sheet. Each row tracks one condition from a planning, EA, or highways consent.
2. | Enter the Condition Ref (e.g., PP-C12 for Planning Condition 12), Consent Type, and Issuing Authority.
3. | Describe the condition and identify the compliance trigger (e.g., 'before first occupation', 'prior to commencement').
4. | Record the evidence required, track its compilation status, and note when compliance is verified.
5. | The Status column tracks: Not Started, In Progress, Evidence Submitted, Discharged, Non-Compliant.
6. | Expand optional columns for linked permits, drawings, submission/response dates, and filing references.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
Green = Discharged or Evidence Complete
Amber = In Progress or Evidence Submitted (awaiting confirmation)
Red = Not Started or Non-Compliant
Tips
Tip 1: | Extract ALL conditions from the decision notice/consent letter at project start. Missing a condition can stop the works.
Tip 2: | Pre-commencement conditions must be discharged BEFORE you break ground. Filter by trigger = 'Prior to commencement' weekly.
Tip 3: | Keep formal discharge letters from the authority filed with this tracker. 'Discharged' means you have written confirmation, not just that you've submitted evidence.

## Consent Tracker
Condition Ref | Consent Type | Issuing Authority | Condition Description | Compliance Trigger | Evidence Required | Evidence Status | Compliance Date | Verified By | Status | Notes | Linked Permit Ref | Drawing Ref | Submission Date | Authority Response | Filing Ref
PP-C03 | Planning Permission | Local Planning Authority | Construction Environmental Management Plan (CEMP) to be submitted and approved | Prior to commencement | CEMP document, ecology survey, dust management plan | Verified | 2025-11-24 | LPA Case Officer | Discharged | Formal discharge letter received 15/11/2025 | PER-001 |  |  | 2025-11-19 | CONS/PP/C03
PP-C07 | Planning Permission | Local Planning Authority | Archaeological watching brief during all ground disturbance works | During construction | Archaeological report, photo record, finds log | In Progress |  |  | In Progress | Watching brief ongoing — archaeologist on site during excavations | PER-001 | DWG-ARCH-001
PP-C12 | Planning Permission | Local Planning Authority | Landscaping scheme including native species planting to be agreed before occupation | Before first use/occupation | Landscaping drawings (approved), planting schedule, maintenance plan | Not Started |  |  | Not Started | Deferred to Phase 2 — need to submit scheme 3 months before occupation | PER-001
EA-01 | EA Discharge Consent | Environment Agency | Final effluent quality: BOD ≤20mg/l, SS ≤30mg/l, NH3 ≤5mg/l. Continuous monitoring. | Ongoing/perpetuity | 12 months monitoring data, process proving report, instrument calibration certs | In Progress |  |  | In Progress | Process proving underway — 8 months of data collected. See KPI Tracker. | PER-002 |  |  |  | CONS/EA/01
EA-03 | EA Discharge Consent | Environment Agency | No discharge of trade effluent during construction without prior written consent | During construction | Written consent from EA, monitoring records, incident log | Complete | 2026-01-23 | A. Khan | Evidence Submitted | Evidence submitted — awaiting formal confirmation from EA | PER-002 |  |  | 2026-01-18 | CONS/EA/03
HW-01 | Highways S278 | County Highways Authority | Carriageway reinstatement to adoptable standard with 12-month defects period | Before completion | As-built drawings, CCTV survey, reinstatement photos, safety audit report | Not Started |  |  | Not Started | Works not yet complete — reinstatement scheduled month 10 | PER-003 | DWG-HW-005
SUMMARY | Total Conditions: | 6 | Discharged: | 1 | Not Started: | 2 | Non-Compliant: | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.