## Cover
EBRORA
ebrora.com
Environmental Permit Compliance Register
Track environmental permits and their conditions with compliance status monitoring.
Ensures ongoing compliance with EA, NRW, and SEPA permit requirements.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Permit Compliance' sheet. The top dashboard summarises compliance across all permits. It updates as you complete the register below.
2. | Each permit is shown as a category band (dark navy) with its conditions listed as rows beneath. Enter the permit details, reference number, and expiry date.
3. | For each condition, select the compliance status: Compliant, Non-Compliant, Partially Compliant, or Not Yet Assessed.
4. | Record the evidence of compliance (e.g. monitoring data, inspection records) and the person responsible for maintaining compliance.
5. | Expand the optional columns for review frequency, last review date, next review date, and action required for non-compliant items.
6. | The dashboard auto-counts conditions by status and calculates the overall compliance rate. Non-compliant items turn red.
7. | Review monthly with your environmental manager. Flag any upcoming permit expiry dates — these highlight amber within 30 days.
Colour Key
Light teal — user input / editable
Dark navy — permit headers, do not edit
Green — Compliant
Amber — Partially Compliant / approaching expiry
Red — Non-Compliant or expired
Tips
• | Set calendar reminders for permit renewal 3 months before expiry — late renewals can halt work.
• | Keep a digital copy of each permit linked from the Evidence column for easy audit access.
• | If a condition changes mid-project, update the register and re-assess compliance immediately.

## Permit Compliance
ENVIRONMENTAL PERMIT COMPLIANCE REGISTER
Compliance Status Summary |  |  |  |  | Overall Compliance
Compliant |  |  | 9 |  | Total Conditions: |  | 11
Partially Compliant |  |  | 1 |  | Compliance Rate: |  | 81.82%
Non-Compliant |  |  | 1 |  | Full+Partial Rate: |  | 90.91%
Not Yet Assessed |  |  | 0
PERMIT CONDITIONS REGISTER
Cond. # | Condition Description | Status | Evidence / Action Taken | Responsible | Review Freq. | Last Review | Next Review | Expiry Date | Notes / Actions Required
DISCHARGE CONSENT — Environment Agency Ref: EPR/AB1234CD | [7 empty] | 2027-06-30
DC-01 | Discharge to watercourse shall not exceed 50 mg/L TSS at outfall point | Compliant | Weekly TSS monitoring results all <30 mg/L — see monitoring log | A. Hussain | Weekly | 2026-03-16 | 2026-03-23
DC-02 | pH of discharge shall be between 6.0 and 9.0 | Compliant | pH probe readings logged daily at outfall — range 6.8–7.6 | A. Hussain | Weekly | 2026-03-16 | 2026-03-23
DC-03 | No visible oil or grease in discharge | Compliant | Visual inspection at each monitoring visit — no sheen observed | A. Hussain | Weekly | 2026-03-16 | 2026-03-23
DC-04 | Flow rate shall not exceed 5 L/s | Partially Compliant | Flow meter installed but needs recalibration — last reading 4.2 L/s | A. Hussain | Monthly | 2026-02-28 | 2026-03-31 |  | Calibration booked for 25/03/2026
WASTE MANAGEMENT LICENCE — EA Ref: WML/EF5678GH | [7 empty] | 2026-12-31
WM-01 | All waste stored in designated, bunded storage areas | Compliant | Storage areas inspected weekly — bunding intact, no overflows | M. Okafor | Weekly | 2026-03-14 | 2026-03-21
WM-02 | Waste transfer notes completed for all movements | Compliant | WTN file up to date — cross-referenced with waste log | M. Okafor | Per transfer | 2026-03-18
WM-03 | Hazardous waste consignment notes for all haz. waste | Compliant | 2 consignment notes issued — both filed and registered | M. Okafor | Per transfer | 2026-03-12
WM-04 | Site operatives trained in waste segregation | Non-Compliant | 3 new starters not yet inducted on waste procedures | M. Okafor | Monthly | 2026-02-15 | 2026-03-15 |  | Toolbox talk scheduled 22/03/2026
SECTION 61 NOISE CONSENT — Local Authority Ref: S61/2025/0042 | [7 empty] | 2026-09-30
N-01 | Construction noise shall not exceed 75 dB LAeq,T at NSR | Compliant | Monitoring log shows max 73 dB at nearest receptor | J. Barton | Weekly | 2026-03-16 | 2026-03-23
N-02 | Piling operations restricted to 08:00–18:00 Mon-Fri only | Compliant | Programme confirms piling within permitted hours | J. Barton | Daily | 2026-03-20 | 2026-03-21
N-03 | Best Practicable Means (BPM) applied to all noisy activities | Compliant | BPM register maintained — acoustic screens around piling rig | J. Barton | Monthly | 2026-02-28 | 2026-03-31

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.