## Cover
EBRORA
ebrora.com
Bund Inspection &
Integrity Test Register
Track secondary containment bund inspections, integrity tests,
pass/fail results, and remedial actions for environmental compliance.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Bund Register' sheet. Each row tracks one bund through its inspection and testing lifecycle.
2. | Record the Bund Ref, Location, Contents/Chemical stored, and Bund Capacity in litres.
3. | Log each visual inspection: date, inspector, and result (Pass/Fail/Remedial Required).
4. | Record integrity tests separately: date, test method (hydrostatic, vacuum, dye test), and result.
5. | The Next Due Date should be set based on your inspection regime (typically quarterly visual, annual integrity test).
6. | If remedial action is needed, describe it in the Remedial Action column and track completion.
7. | Overdue inspections (Next Due Date passed) highlight red automatically.
Colour Key
Light teal cells (#E8F6F7) = User input / editable fields
Dark navy headers (#1B2A4A) = Do not edit
Green = Pass
Amber = Remedial Required (minor)
Red = Fail or overdue inspection
Tips
Tip 1: | Bund inspections are an EA compliance requirement. A failed bund during an EA visit can result in enforcement action.
Tip 2: | Visual inspections should be at least quarterly. Integrity tests annually or after any suspected damage.
Tip 3: | Filter by Next Due Date to generate a monthly inspection schedule. Don't let inspections lapse during busy construction periods.

## Bund Register
Bund Ref | Location | Contents / Chemical | Capacity (litres) | Last Inspection Date | Inspector | Inspection Result | Integrity Test Date | Test Method | Test Result | Next Due Date | Remedial Action | Notes | Bund Material | Liner Type | Linked Permit Ref | Photo Ref | Remedial Cost (£)
BND-001 | Chemical Dosing Kiosk | Ferric Chloride (40%) | 2000 | 2026-02-22 | R. Evans | Pass | 2025-12-24 | Hydrostatic Test | Pass | 2026-05-23 |  | Annual integrity test passed. Quarterly visual OK. | Concrete with Epoxy Coating | N/A | PER-002 | PHOTO-BND-001 | 0
BND-002 | Diesel Generator Compound | Red Diesel (DERV) | 1200 | 2026-03-09 | R. Evans | Pass | 2025-09-25 | Visual Only | Pass | 2026-06-07 |  | No cracks or staining observed | Masonry | N/A |  | PHOTO-BND-002 | 0
BND-003 | Polymer Dosing Area | Polyelectrolyte | 500 | 2026-02-07 | A. Khan | Remedial Required | 2026-02-07 | Dye Penetrant Test | Fail | 2026-03-09 | Hairline crack at base/wall joint — needs epoxy resin repair | Crack found during integrity test. Repair ordered. | Concrete | N/A |  | PHOTO-BND-003 | 850
BND-004 | Oil Storage Area | Hydraulic Oil / Lubricants | 800 | 2026-01-23 | R. Evans | Pass | 2026-01-23 | Hydrostatic Test | Pass | 2026-07-22 |  | All satisfactory | Steel | Integral |  |  | 0
BND-005 | Sodium Hypochlorite Store | Sodium Hypochlorite (14%) | 3000 | 2026-03-14 | A. Khan | Pass |  | N/A | N/A | 2026-06-12 |  | New bund — first visual inspection complete. Integrity test due at 6 months. | GRP | N/A | PER-002 | PHOTO-BND-005 | 0
SUMMARY | Total Bunds: | 5 | Failed: | 1 | Overdue: | 1 | Remedial Needed: | 1

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.