## Cover
EBRORA
ebrora.com
Environmental Incident Log
Record, track and manage environmental incidents on construction sites.
Includes severity classification, corrective actions, and regulatory notification tracking.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Environmental Incident Log' sheet. The top section is a live summary dashboard — it updates automatically as you log incidents below.
2. | Start logging incidents from the first empty row in the log section (row 12 onwards). Enter the date, select the incident type and severity from the dropdowns.
3. | Fill in the location and a brief description of the incident. Record the immediate action taken on site.
4. | Set the Status to Open, Under Investigation, Corrective Action, or Closed using the dropdown.
5. | Expand the optional columns (click the [+] button above the column headers) to record the reporter, root cause, corrective actions, close-out date, and whether the regulator was notified.
6. | The dashboard at the top auto-calculates totals by incident type and severity. Use this for reporting to your environmental manager or client.
7. | Use Excel's built-in filters on the header row to sort or filter by type, severity, status, or date.
Colour Key
Light teal cells — user input / editable fields
Dark navy headers — do not edit
Green — Low severity or Closed status
Amber — Medium severity or Under Investigation
Red — High/Critical severity or Open incident
Tips
• | Log incidents as soon as possible after they occur — accuracy decreases over time.
• | Any spill, discharge to watercourse, or dust complaint should be recorded even if contained quickly.
• | Use the 'Regulator Notified' optional column to keep an audit trail for EA/NRW/SEPA reporting requirements.

## Environmental Incident Log
ENVIRONMENTAL INCIDENT LOG — SUMMARY DASHBOARD
Incidents by Type |  |  |  |  | Incidents by Severity |  |  |  |  | Status Overview
Spill / Leak |  |  | 1 |  | Critical |  |  | 1 |  | Open |  | 1
Dust / Air Quality |  |  | 1 |  | High |  |  | 1 |  | Under Investigation |  | 2
Noise Complaint |  |  | 1 |  | Medium |  |  | 2 |  | Corrective Action |  | 1
Water Pollution |  |  | 1 |  | Low |  |  | 1 |  | Closed |  | 1
Waste / Fly-Tipping |  |  | 1
TOTAL INCIDENTS |  |  | 5
INCIDENT LOG
Ref | Date | Incident Type | Severity | Location | Description | Immediate Action Taken | Status | Reported By | Root Cause | Corrective Action | Close-Out Date | Regulator Notified
ENV-001 | 2026-03-02 | Spill / Leak | High | Compound Area - South | Approx 50L diesel spill from generator refuelling. Spill reached unpaved ground. | Spill kit deployed, contaminated soil removed to sealed skip. | Under Investigation | J. Williams | Faulty nozzle on fuel bowser | Replace bowser nozzle, retrain operatives on refuelling procedure |  | Yes
ENV-002 | 2026-03-05 | Dust / Air Quality | Medium | Haul Road - Phase 2 | Dust complaints from neighbouring residential properties during dry spell. | Water bowser deployed to haul road, reduced vehicle speed limit. | Corrective Action | Site Office | Dry weather + uncompacted haul road surface | Install automatic sprinkler system on haul road |  | No
ENV-003 | 2026-03-08 | Water Pollution | Critical | Outfall Point 3 | Silty water discharge observed entering watercourse from site outfall. | Outfall blocked, silt fencing installed upstream, pumping redirected. | Open | M. Khan | Settlement pond overtopped during heavy rain | Increase pond capacity, install turbidity monitor |  | Yes
ENV-004 | 2026-03-12 | Noise Complaint | Low | Piling Rig - Grid K4 | Noise complaint logged by resident on Mill Lane regarding piling operations. | Operations paused during complaint call. Confirmed within permitted hours. | Closed | P. Davies | N/A — operations within consent limits | Letter sent to complainant confirming compliance | 2026-03-13 | No
ENV-005 | 2026-03-18 | Waste / Fly-Tipping | Medium | North Boundary Fence | Unauthorised dumping of construction waste found near boundary fence. | Waste removed and area cleared. CCTV check initiated. | Under Investigation | A. Osei | Unknown — possible third party or subcontractor | Review CCTV, brief all subcontractors on waste procedures |  | No

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.