## Cover
EBRORA
ebrora.com
Pollution Incident Response Checklist
Structured response checklist for managing pollution incidents on construction sites.
Covers initial response, containment, notification, investigation, and close-out phases.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'Response Checklist' sheet. Fill in the incident details in the header form at the top.
2. | Work through each response phase in order: Initial Response → Containment → Notification → Investigation → Close-Out.
3. | For each checklist item, select Yes, No, or N/A from the dropdown in column C. Add the time/date completed and any notes.
4. | Each section has an auto-calculating completion bar showing the percentage of items completed (Yes or N/A count as complete).
5. | The overall response completion score at the top updates in real time as you work through the phases.
6. | Items marked 'No' highlight red — these are outstanding actions that must be addressed before close-out.
7. | Print the completed checklist for your incident file and submit to your environmental manager for review.
Colour Key
Light teal — user input / editable
Dark navy — headers and section bands
Green — Yes / completed item
Red — No / outstanding action required
Amber — N/A or partial completion
Tips
• | Complete the Initial Response and Containment sections as the incident is unfolding — don't wait until it's over.
• | Photograph everything. Record the time of each action for your regulator file.
• | The Environment Agency incident hotline is 0800 80 70 60 — call immediately for any pollution reaching a watercourse.

## Response Checklist
POLLUTION INCIDENT RESPONSE CHECKLIST
Incident Ref: |  | PI-2026-003 | Date / Time Reported: | 02/03/2026 14:30
Incident Type: |  | Spill / Leak | Reported By: | J. Williams (Site Foreman)
Location: |  | Compound Area — South | Weather Conditions: | Dry, 12°C, light wind
Pollutant / Substance: |  | Diesel fuel (approx. 50 litres) | Receptor at Risk: | Drainage ditch → watercourse
Severity (High/Med/Low): |  | High | Site Manager Notified: | Yes — 14:35
OVERALL RESPONSE COMPLETION: |  |  |  | 33.33%
PHASE 1 — INITIAL RESPONSE
# | Checklist Item | Done? | Time / Date | Notes / Evidence
1 | Site personnel alerted and area secured | Yes | 14:32 | All personnel moved clear
2 | Source of pollution identified and stopped (if safe to do so) | Yes | 14:34 | Generator shut off, nozzle disconnected
3 | Immediate risks to people assessed (fumes, contact hazard) | Yes | 14:35 | No fumes — diesel only, no inhalation risk
4 | Affected area cordoned off with barriers / tape | Yes | 14:38 | Red/white tape around 10m radius
5 | Photographs taken of the incident scene | Yes | 14:40 | Photos on site phone — ref IMG_2026_0302
6 | Time and location of incident recorded | Yes | 14:32 | Logged in this checklist
Section Completion: |  | 100%
PHASE 2 — CONTAINMENT
# | Checklist Item | Done? | Time / Date | Notes / Evidence
1 | Spill kit deployed (absorbent pads, booms, granules) | Yes | 14:36 | 2x absorbent booms, granules on ground
2 | Drains blocked or dammed to prevent spread | Yes | 14:40 | Drain cover sealed with mat + sandbags
3 | Contaminated material contained in sealed skip / IBC | No |  | Skip being sourced — ETA 16:00
4 | Downstream / downwind receptors checked | Yes | 14:45 | Drainage ditch checked — no visible sheen beyond 20m
5 | Watercourse protected (silt fence, boom, sandbags) | Yes | 14:50 | Boom placed across ditch upstream of watercourse
6 | Secondary containment in place for remaining pollutant | No |  | Remaining fuel in generator — bunded but needs pumping out
Section Completion: |  | 66.67%
PHASE 3 — NOTIFICATION
# | Checklist Item | Done? | Time / Date | Notes / Evidence
1 | Site Manager notified
2 | Project Manager / Client notified
3 | Environment Agency incident hotline called (0800 80 70 60)
4 | Environmental Manager / ECoW notified
5 | Local authority notified (if required)
6 | Incident logged in site environmental register
Section Completion: |  | 0%
PHASE 4 — INVESTIGATION
# | Checklist Item | Done? | Time / Date | Notes / Evidence
1 | Root cause analysis completed
2 | Witness statements collected
3 | Photographic evidence filed
4 | Timeline of events documented
5 | Corrective / preventive actions identified
6 | Lessons learned briefing prepared
Section Completion: |  | 0%
PHASE 5 — CLOSE-OUT
# | Checklist Item | Done? | Time / Date | Notes / Evidence
1 | All corrective actions completed
2 | Environmental monitoring confirms no residual contamination
3 | Regulator satisfied (if involved)
4 | Incident report finalised and signed off
5 | Lessons learned communicated to site team (toolbox talk)
6 | Incident register updated with close-out date
Section Completion: |  | 0%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.