## Cover
EBRORA
ebrora.com
As-Built Drawing Register
Track as-built drawing production, revision status, and handover completeness.
Revision matrix with status workflow and auto-completion percentage for project handover.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. | Open the 'As-Built Register' sheet. The dashboard shows drawing status counts and handover readiness percentage.
2. | List every drawing required. Enter the drawing number, title, discipline, originator, and design revision.
3. | Update each drawing's as-built status: Not Started → In Progress → For Review → Approved → Issued as As-Built.
4. | Enter the as-built revision and issue date when complete. The dashboard auto-updates.
5. | Expand optional columns for file format, storage location, reviewer, and comments.
6. | Target 100% as-built completion before practical completion — a contractual handover requirement.
7. | Prioritise M&E as-builts early — these are the most complex and time-consuming to complete.
Colour Key
Light teal — user input
Dark navy — headers
Green — Issued as As-Built / Approved
Amber — In Progress / For Review
Red — Not Started
Tips
• | Start red-line markup during construction. Transfer to CAD weekly — don't leave it to the end.
• | Use consistent naming: [Project]-[Discipline]-[Number]-[Rev] e.g. EIP-S-RC101-AB01.
• | O&M manuals cannot be completed without as-builts. Chase M&E subcontractors early.

## As-Built Register
AS-BUILT DRAWING REGISTER
Status Summary |  |  |  |  | Handover Readiness
Not Started: | 1 | In Progress: | 4 |  | Total: | 7
For Review: | 2 | Complete: |  |  | As-Built %: | 42.86%
DRAWING REGISTER
Drawing No. | Drawing Title | Discipline | Originator | Design Rev | Date Issued | As-Built Status | As-Built Rev | AB Issue Date | Format | Storage Location | Reviewed By | Review Date | Notes
EIP-S-RC101 | Foundation layout — general arrangement | Structural | Smith & Partners | P03 | 2026-01-15 | Issued as As-Built | AB01 | 2026-03-10 | PDF+DWG | SharePoint/As-Builts/Structural | T. Henderson | 2026-03-08
EIP-S-RC102 | Foundation reinforcement details — Grids A-D | Structural | Smith & Partners | P03 | 2026-01-15 | Issued as As-Built | AB01 | 2026-03-10 | PDF+DWG | SharePoint/As-Builts/Structural | T. Henderson | 2026-03-08
EIP-C-DR201 | Below-ground drainage layout | Civil | Jones Civil Design | P02 | 2025-12-20 | For Review | AB01 |  | DWG |  | M. Khan |  | Red-line markup complete. CAD update in progress.
EIP-M-MH301 | Mechanical services — Level 0 plantroom | Mechanical | BES Consulting | P04 | 2026-02-01 | In Progress | [6 empty] | M&E as-builts typically lag — chase subcontractor.
EIP-E-EL401 | Electrical distribution — single line diagram | Electrical | BES Consulting | P03 | 2026-01-20 | Not Started | [6 empty] | Awaiting final installation completion.
EIP-A-AR501 | Architectural floor plans — Level 0 | Architectural | ABC Architects | P05 | 2026-02-15 | Approved | AB01 |  | PDF+DWG |  | T. Henderson | 2026-03-15 | Approved. Pending formal issue.
EIP-C-GA001 | Site general arrangement plan | Civil | Jones Civil Design | P02 | 2025-11-01 | Issued as As-Built | AB01 | 2026-03-05 | PDF | SharePoint/As-Builts/Civil | T. Henderson | 2026-03-03

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.