## Cover
EBRORA
ebrora.com
Red-Line / As-Built Change Log
Record every field change clouded on red-line drawings — track the change description, drawing revision, sign-off and transfer to formal as-built issue.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Red-Line / As-Built Change Log
Step-by-Step Instructions
1. | Go to the 'As-Built Change Log' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | Each change entry is automatically assigned a sequential reference (ABL-001, ABL-002, etc.) when a Drawing Number is entered in column C.
3. | Enter the Date the change was marked up in column B. This is the date the cloud was added to the red-line print — not the date it was transferred to the digital drawing.
4. | Record the Drawing Number in column C and the current Revision in column D. These should match the IFC drawing the red-line mark-up is made against.
5. | Select the Discipline in column E and the Change Category in column F: Dimension Change, Route / Level Change, Equipment Location, Additional Detail, Omission, or Specification Change.
6. | Enter a clear description of what changed on site vs the IFC drawing in column G. Be specific — reference grid lines, chainage, or asset tag where applicable.
7. | Record who raised the change (column H) — typically the Site Engineer or Foreman who identified the as-built condition.
8. | Use the Status dropdown (column I): Clouded on Red-Line, Transferred to Digital, Issued as As-Built, or Superseded. Progress each entry through to 'Issued as As-Built'.
9. | Enter the Target As-Built Issue Date (column J) — when you expect the designer to issue the formal as-built drawing incorporating this change.
10. | Column K flags overdue transfers. Expand Optional Columns L–O for the cloud reference, linked NCR, P&ID reference and file path.
Colour Key
Issued as As-Built — Change has been transferred and the formal as-built drawing has been issued.
Transferred to Digital — Change has been incorporated into the CAD model. Awaiting formal issue.
Clouded on Red-Line — Change marked up on paper print only. Not yet in the digital drawing.
Overdue — Target issue date has passed and the change has not reached 'Issued as As-Built'.
Superseded — Change has been superseded by a later revision. Retained for audit record.
Light teal cells — User input / editable fields.
Tips
* | Red-line mark-ups are a site record — they must be legible and signed. A photo of the clouded print filed against this log is best practice and protects you if the physical drawing is lost.
* | Set a regular transfer cycle — weekly is ideal. Leaving red-line changes to accumulate over months creates a backlog that delays the as-built submission and can cause the designer to miss changes in the digital transfer.
* | Under ISO 19650, as-built information must be handed over at practical completion. A complete, signed-off as-built change log showing every change moved from red-line to issued drawing is the evidence that the asset information model is complete.

## As-Built Change Log
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No] |  |  | ▸ Optional Fields — Click [+] to expand
ABL Ref | Date Marked Up | Drawing No. | Rev | Discipline | Change Category | Change Description | Raised By | Status | Target As-Built Date | Days to Target / Overdue | Cloud Ref | Linked NCR | P&ID / Tag Ref | File Path / Link
ABL-001 | 2025-01-16 | WRC-CV-0001 | C | Civil | Route / Level Change | Inlet main re-routed around existing unknown service at Ch0+062. Offset 1.2m east of IFC route. | T. Walsh | Issued as As-Built | 2025-02-28 |  | Cloud-CV-001
ABL-002 | 2025-01-25 | WRC-ST-0003 | C | Structural | Dimension Change | Tank base slab thickness increased from 400mm to 450mm at NW corner — soft spot found in formation. | S. Patel | Issued as As-Built | 2025-02-28 |  | Cloud-ST-001 | NCR-018
ABL-003 | 2025-02-10 | WRC-ME-0008 | B | Mechanical | Equipment Location | Pump PST-01 baseplate shifted 200mm north to avoid sleeve clash with existing drain. | T. Walsh | Transferred to Digital | 2025-03-31 | -358 | Cloud-ME-001 |  | PST-01
ABL-004 | 2025-02-22 | WRC-EL-0005 | B | Electrical | Route / Level Change | MCC cable duct re-routed above slab level from Ch0+031 to Ch0+048 — ground conditions unsuitable for burial. | C. Roberts | Clouded on Red-Line | 2025-03-31 | -358 | Cloud-EL-001 | NCR-031 | FCV-201
ABL-005 | 2025-03-05 | WRC-IN-0002 | P02 | Instrumentation | Additional Detail | Additional isolation valve added to P&ID — instrument air supply to FT-301 added during installation. | A. Nkosi | Clouded on Red-Line | 2025-04-30 | -328 | Cloud-IN-001 |  | FT-301
TOTAL CHANGES | 5 | ISSUED AS-BUILT | 2 | TRANSFERRED | 1 | RED-LINE ONLY | 2 | OVERDUE | 3 | % COMPLETE | 40%
Formulas:
Days to Target / Overdue = IF(AND([Target As-Built Date]<>"",[Status]<>"Issued as As-Built",[Status]<>"Superseded"),[Target As-Built Date]-TODAY(),"")

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.