## Cover
EBRORA
ebrora.com
Lessons Learned Register
Capture project lessons — both positive and negative — with category tagging, impact assessment, and recommendations for future projects.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Lessons Learned' sheet. Log lessons as they arise — don't wait until the end of the project.
2. Enter each lesson with the date, phase it relates to, and whether it was a positive or negative experience.
3. Describe what happened, what the impact was, and what the recommendation is for future projects.
4. Categorise each lesson (Design, Procurement, Construction, Commercial, H&S, etc.) for searchability.
5. The summary shows total lessons, split by positive/negative, and category breakdown.
6. Record who raised the lesson and whether it has been shared with the wider business.
7. Expand optional columns [+] for project phase, related risk ref, and sharing status.
8. Review all lessons at project closeout — the register becomes part of the handover documentation.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Positive / Complete
| Amber | In progress / Medium
| Red | Negative / Critical
Tips
• Capture lessons in real time — memories fade and details get lost if you wait until project end.
• Positive lessons are just as valuable as negative ones — record what went well so it can be repeated.
• Share lessons across the business — a lesson learned on one project but not shared is a lesson wasted.

## Lessons Learned
LESSONS LEARNED REGISTER
Total Lessons |  | Positive |  | Negative |  | Shared |  | Pending Share
3 |  | 1 |  | 2 |  | 2 |  | 1
▸ Optional Fields — Click [+] to expand
Ref | Date | Category | Type | What Happened | Impact / Consequence | Recommendation | Raised By | Project Phase | Notes | Related Risk Ref | Shared? | Shared With
LL-001 | 2026-02-15 | Procurement | Positive | Early engagement with steel fabricator (12 weeks pre-order) secured capacity and avoided programme delay. | Steelwork delivered 1 week early — 5 days float gained on programme. | For steel-framed projects, engage fabricator at RIBA Stage 3 minimum. Include fabrication lead time in procurement schedule. | M. Evans | Construction |  |  | Yes | All PMs via monthly bulletin
LL-002 | 2026-02-20 | Construction | Negative | Insufficient trench support equipment on site caused 3-day delay to drainage works while additional drag boxes were sourced. | 3-day delay to drainage programme. £2,400 additional hire cost. | Pre-order trench support based on maximum excavation depth from drawings. Include in mobilisation checklist. | D. Murphy | Construction |  | R-002 | No
LL-003 | 2026-03-01 | Design | Negative | Late design information for M&E service routes caused 2 weeks of abortive work on builders' work openings. | £8,500 abortive cost. 2-week delay to internal fit-out start. | Mandate design freeze dates in consultant appointments. Include BIM clash detection as a contract deliverable. | Design Manager | Construction |  | R-005 | Yes | Design team leads

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.