## Cover
EBRORA
ebrora.com
O&M Submission
Tracker
Track O&M manual submissions by system and supplier
through review, resubmission, and final acceptance for handover.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'O&M Tracker' sheet. Each row tracks one O&M document submission.
2. | Fill in the light teal cells. Enter O&M Ref, System, Supplier, Document Title, and Revision.
3. | Record Date Submitted and track through Review Status (Pending / Under Review / Accepted / Rejected / Resubmit Required).
4. | The Days Since Submission column auto-calculates to help chase overdue reviews.
5. | Expand optional columns (click [+]) for linked asset tags, format, copies, final acceptance date, and filing location.
Colour Key
Light teal cells = User input / editable
Dark navy headers = Do not edit
Green = Accepted
Amber = Pending or Under Review
Red = Rejected / Resubmit Required, or >14 days without review
Tips
Tip 1: | Issue this tracker to suppliers at contract award with clear O&M submission deadlines.
Tip 2: | Filter by 'Rejected' or 'Resubmit Required' to generate chase lists for subcontractor meetings.
Tip 3: | Cross-reference O&M Refs to your Asset Tag Register to ensure every asset has O&M coverage.

## O&M Tracker
O&M Ref | System / Process Area | Supplier | Document Title | Rev | Date Submitted | Date Reviewed | Review Status | Reviewer | Review Comments | Resubmission Req'd | Days Since Sub. | Notes | Linked Asset Tags | Format | Copies Req'd | Final Accepted Date | Filed Location
OM-INL-001 | Inlet Works | Xylem Water Solutions | Inlet Pump Station — Submersible Pumps O&M Manual | B | 2026-02-22 | 2026-03-06 | Accepted | S. Patel | Comprehensive and well-structured. Minor formatting corrections made. | No | 12 |  | PMP-INL-001, PMP-INL-002 | Both | 3 | 2026-03-06 | H&S File Box 3
OM-SPS-003 | Storm Water | AVK UK Ltd | Storm Tank Penstock Valves — Installation & Maintenance Guide | A | 2026-02-27 | 2026-03-12 | Resubmit Required | M. Thompson | Missing torque settings for actuator. Lubrication schedule incomplete. | Yes | 13 |  | VLV-SPS-014 | Soft Copy | 2
OM-FST-002 | Secondary Treatment | Cerlic AB | Sludge Blanket Analyser SBM-500 — Technical Manual | A | 2026-03-04 |  | Under Review |  |  | No | 20 | Reviewer assigned — awaiting feedback | INS-FST-007 | Soft Copy | 2
OM-EL-003 | Electrical Distribution | Schneider Electric | MCC Panel 3 — Prisma iPM Operation & Maintenance | C | 2026-03-14 | 2026-03-21 | Accepted | R. Evans | Well detailed. Includes updated SLDs and protection settings. | No | 7 |  | MCC-EL-003 | Both | 3 | 2026-03-21 | H&S File Box 5
OM-RAS-001 | Secondary Treatment | Grundfos | RAS Pumps SE Series — Service & Maintenance Manual | A | 2026-03-19 |  | Pending |  |  | No | 5 | Submitted via portal, hard copy to follow | PMP-RAS-002 | Soft Copy | 2
SUMMARY | Total: | 5 | Accepted: | 2 | Awaiting: | 2 | Resubmit/Rejected: | 1
Formulas:
Days Since Sub. = IF([Date Submitted]="","",IF([Date Reviewed]<>"",[Date Reviewed]-[Date Submitted],TODAY()-[Date Submitted]))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.