## Cover
EBRORA
ebrora.com
Warranty & Service
Plan Tracker
Track warranty expiry dates, planned service intervals,
and supplier contacts for all commissioned assets.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Warranty Tracker' sheet. Each row is one asset or system with warranty and service plan details.
2. | Record the Asset/System, Supplier, Warranty Start/End dates, Service Interval, and Supplier Contact details.
3. | The 'Warranty Remaining' column auto-calculates days remaining. The 'Warranty Status' shows Active, Expiring Soon, or Expired.
4. | Monthly columns (12 months) show the service schedule. Mark: Planned, Booked, Done, N/A.
5. | The Next Service Due column calculates based on last service date and interval.
6. | Use this tracker to plan warranty inspections before expiry — claims after expiry are rarely honoured.
Colour Key
Light teal = Input
Green = Active warranty / Done service
Amber = Expiring within 90 days / Planned or Booked
Red = Expired warranty / Overdue service
Tips
Tip 1: | Schedule warranty inspections 4-6 weeks before expiry. Identify defects while you can still make a warranty claim.
Tip 2: | Hand this tracker to the operator at takeover. It's the single most useful document for their maintenance planning.
Tip 3: | Include supplier contact details — the operator needs to know who to call for warranty repairs at 2am on a Sunday.

## Warranty Tracker
Asset / System | Supplier | Warranty Start | Warranty End | Warranty Remaining | Warranty Status | Service Interval | Last Service | Supplier Contact | Supplier Phone | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Next Service Due
Inlet Pumps (PMP-INL-001/002) | Xylem | 2024-06-15 | 2026-06-15 | 83 | Expiring Soon | 6-Monthly | 2026-01-10 | Service Desk | 01onal 555 0101 | Done | N/A | N/A | Booked | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-10
MCC Panel 3 | Schneider Electric | 2024-04-01 | 2026-04-01 | 8 | Expiring Soon | Annually | 2025-04-01 | Technical Support | 0800 444 5566 | N/A | N/A | N/A | Planned | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-01
Fine Screens (3mm) | Huber Technology | 2026-01-01 | 2028-01-01 | 648 | Active | Quarterly | 2026-03-15 | After-Sales | 01onal 555 0202 | N/A | N/A | Planned | N/A | N/A | Planned | N/A | N/A | Planned | N/A | N/A | Planned | 2026-06-15
UV Disinfection System | Trojan Technologies | 2026-03-01 | 2028-03-01 | 708 | Active | 6-Monthly | 2026-03-01 | Service Engineer | 01onal 555 0303 | N/A | N/A | N/A | N/A | N/A | Planned | N/A | N/A | N/A | N/A | N/A | N/A | 2026-09-01
Sludge Blanket Analyser | Cerlic | 2025-01-10 | 2027-01-10 | 292 | Active | Quarterly | 2026-01-10 | UK Distributor | 01onal 555 0404 | Done | N/A | N/A | Planned | N/A | N/A | Planned | N/A | N/A | Planned | N/A | N/A | 2026-04-10
SCADA Server (Primary) | Schneider Electric | 2024-06-01 | 2026-06-01 | 69 | Expiring Soon | Annually | 2025-06-01 | SCADA Support | 0800 444 5567 | N/A | N/A | Planned | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-01
SUMMARY | Total Assets: | 6 | Active Warranty: | 3 | Expiring Soon: | 3 | Expired: | 0
Formulas:
Warranty Remaining = IF([Warranty End]="","",[Warranty End]-TODAY())
Warranty Status = IF([Warranty End]="","",IF([Warranty End]<TODAY(),"Expired",IF([Warranty End]<=TODAY()+90,"Expiring Soon","Active")))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.