## Cover
EBRORA
ebrora.com
Handover Readiness
Dashboard
Monitor multi-system handover readiness with % complete by discipline,
outstanding items tracking, and system-level status overview.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | This template has two working sheets: 'Dashboard' (readiness overview) and 'Handover Items' (detailed checklist).
2. | Start with the 'Handover Items' sheet. Each row is one handover deliverable or action.
3. | Enter the System, Discipline, Item Description, Responsible Person, and Status (Not Started / In Progress / Complete / N/A).
4. | The Dashboard auto-calculates: overall readiness %, readiness by system, readiness by discipline, and outstanding items count.
5. | Systems are defined by the data in the Handover Items sheet — add new systems by adding rows with new system names.
6. | Review the Dashboard at handover readiness meetings to track progress and identify blockers.
Colour Key
Light teal = Input cells
Green = Complete / ≥95% ready
Amber = In Progress / 50-94% ready
Red = Not Started / <50% ready
Tips
Tip 1: | Start populating this 3 months before planned handover. The items that are 'Not Started' at T-minus-3-months are your risks.
Tip 2: | Assign every item to a named person. 'TBC' as the responsible person means nobody is doing it.
Tip 3: | Present this dashboard at weekly handover readiness meetings. The % complete by system tells you which systems are holding up the handover.

## Dashboard
Handover Readiness Dashboard
Overall Readiness |  | Total Items |  | Complete |  | Outstanding
38.89% |  | 18 |  | 7 |  | 11
Readiness by System | [6 empty] | Readiness by Discipline
System | Total Items | Complete | In Progress | Not Started | Readiness % |  | Discipline | Complete | Readiness %
Inlet Works | 5 | 4 | 1 | 0 | 80% |  | Civil | 0 | 0%
Storm Water | 2 | 0 | 1 | 1 | 0% |  | Structural | 0 | —
Secondary Treatment | 2 | 1 | 1 | 0 | 50% |  | Mechanical | 3 | 60%
Sludge Treatment | 2 | 0 | 0 | 2 | 0% |  | Electrical | 1 | 50%
Electrical Distribution | 2 | 1 | 1 | 0 | 50% |  | Instrumentation | 2 | 66.67%
SCADA & Instrumentation | 2 | 1 | 1 | 0 | 50% |  | Process | 0 | 0%
Site-Wide & Civil | 3 | 0 | 2 | 1 | 0% |  | General | 1 | 33.33%

## Handover Items
Item Ref | System | Discipline | Description | Responsible | Status | Due Date | Date Complete | Notes
HO-001 | Inlet Works | Mechanical | Pump O&M manuals submitted and accepted | A. Khan | Complete | 2026-02-22 | 2026-02-27
HO-002 | Inlet Works | Mechanical | Pump commissioning certificates | A. Khan | Complete | 2026-03-04 | 2026-03-06
HO-003 | Inlet Works | Civil | As-built drawings — inlet structures | J. Davies | In Progress | 2026-04-07 |  | Survey complete, drawings being updated
HO-004 | Inlet Works | Instrumentation | Instrument calibration certificates | S. Patel | Complete | 2026-03-14 | 2026-03-16
HO-005 | Storm Water | Mechanical | Penstock valve O&M and test certificates | A. Khan | In Progress | 2026-04-14 |  | O&M submitted — under review
HO-006 | Storm Water | Civil | Storm tank as-built survey and drawings | J. Davies | Not Started | 2026-04-23 |  | Tank not yet complete
HO-007 | Secondary Treatment | Process | Process proving report — 12 month data | A. Khan | In Progress | 2026-05-23 |  | 8 months of data collected
HO-008 | Secondary Treatment | Mechanical | RAS pump spares list and maintenance schedule | M. Thompson | Complete | 2026-03-19 | 2026-03-21
HO-009 | Electrical Distribution | Electrical | MCC panel test certificates and as-builts | S. Patel | Complete | 2026-03-09 | 2026-03-12
HO-010 | Electrical Distribution | Electrical | Cable schedule and containment as-builts | S. Patel | In Progress | 2026-04-13 |  | 50% complete
HO-011 | SCADA & Instrumentation | Instrumentation | SCADA point schedule — verified | S. Patel | In Progress | 2026-04-18 |  | Cross-checking against P&IDs
HO-012 | SCADA & Instrumentation | Instrumentation | PLC software backup and documentation | S. Patel | Complete | 2026-03-16 | 2026-03-18 | See SCADA Change Log
HO-013 | Site-Wide & Civil | Civil | Drainage CCTV survey and report | R. Evans | Not Started | 2026-05-08 |  | Scheduled for month 10
HO-014 | Site-Wide & Civil | General | H&S file — complete and indexed | R. Evans | In Progress | 2026-04-23 |  | 60% compiled
HO-015 | Site-Wide & Civil | General | Consent compliance evidence pack | A. Khan | In Progress | 2026-05-03 |  | See Consent Tracker
HO-016 | Sludge Treatment | Mechanical | Sludge pump O&M and commissioning records | M. Thompson | Not Started | 2026-04-28 |  | Equipment not yet installed
HO-017 | Sludge Treatment | Process | Sludge dewatering performance test results | A. Khan | Not Started | 2026-05-13
HO-018 | Inlet Works | General | Photographic record — before/during/after | R. Evans | Complete | 2026-03-19 | 2026-03-21

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.