## Cover
EBRORA
ebrora.com
Process Handover Certificate Tracker
Track the formal handover of systems and processes from construction through commissioning to operations — managing certificates, stage-gate approvals, and outstanding items at each handover milestone.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. Open the 'Handover Tracker' sheet. The top section shows a Pipeline Dashboard summarising how many systems are at each handover stage.
2. Each row in the main tracker represents one system, sub-system, or process area that requires formal handover from construction to operations.
3. Enter the System Tag, system description, and discipline. Then work through the stage-gate columns from left to right as the system progresses.
4. The five handover stages are: Construction Complete → Pre-Commissioning Complete → Commissioning Complete → Handover Certificate Issued → Handover Accepted by Client.
5. For each stage, enter the date achieved. The Current Stage and Pipeline Position auto-calculate based on which dates have been filled in.
6. Track outstanding items (punch list count and critical items) — these must typically reach zero before the client accepts handover.
7. Expand the optional columns for certificate reference numbers, witness sign-off, and conditional acceptance details.
8. The Pipeline Dashboard updates live — use it in progress meetings to show the overall handover status across all systems.
Colour Key
Light teal cells = user input / editable fields
Dark navy headers = do not edit
Green = Handover accepted / stage complete
Amber = In progress / partially complete
Red = Not started or blocked
Light blue = Pipeline stage indicator (auto-calculated)
Tips
• Align your system list with the project's system breakdown structure (SBS) — each row should correspond to a handover-able package, not individual equipment items.
• Don't issue handover certificates until punch items are genuinely closed or formally accepted as outstanding — conditional acceptances should be the exception, not the rule.
• Use the certificate reference column to cross-reference your formal handover documentation filing system.

## Handover Tracker
Process Handover Certificate Tracker — Pipeline Dashboard
Stage | Construction Complete |  |  | Pre-Comm Complete |  |  | Commissioning Complete |  |  | Handover Cert Issued |  |  | Handover Accepted
Count | 1 |  |  | 1 |  |  | 1 |  |  | 1 |  |  | 1
% of Total | 16.67% |  |  | 16.67% |  |  | 16.67% |  |  | 16.67% |  |  | 16.67%
Summary Statistics |  |  | Outstanding Items
Total Systems: | 6 |  | Total Punch Items: | 18
Not Started: | 45 |  | Critical Items: | 1
Fully Handed Over: | 1 |  | Systems Blocked: | 1
Handover Rate: | 16.67%
System Identification |  |  |  | Stage-Gate Dates (enter date when stage achieved) |  |  |  |  | Status & Outstanding Items |  |  |  |  | ▸ Optional Fields — Click [+] to expand
Item No. | System Tag | System Description | Discipline | Construction Complete | Pre-Comm Complete | Commissioning Complete | Handover Cert Issued | Handover Accepted | Current Stage | Punch Items (Open) | Critical Items | Handover Status | Notes / Actions | Certificate Ref | Witness / Signatory | Conditional Acceptance? | Conditions / Caveats
1 | SYS-RWP-01 | Raw Water Pumping System | MEICA | 2026-01-15 | 2026-02-10 | 2026-03-05 | 2026-03-12 | 2026-03-18 | Handover Accepted | 2 | 0 | Complete | Fully handed over to client operations team
2 | SYS-PCT-01 | Primary Clarifier Tank 1 | Civils | 2026-01-20 | 2026-02-18 | 2026-03-10 | 2026-03-16 |  | Handover Cert Issued | 5 | 1 | Blocked | 1 critical punch item on scraper mechanism — bearing replacement due 22/03
3 | SYS-FLT-01 | Rapid Gravity Filters 1–4 | Multi-Discipline | 2026-02-05 | 2026-03-01 | 2026-03-14 |  |  | Commissioning Complete | 8 | 0 | On Track | Handover cert in preparation — target issue 25/03
4 | SYS-CDS-01 | Chemical Dosing — Chlorine | Process | 2026-02-12 | 2026-03-08 |  |  |  | Pre-Comm Complete | 3 | 0 | On Track | Commissioning scheduled week commencing 24/03
5 | SYS-SLG-01 | Sludge Thickening & Dewatering | MEICA | 2026-02-20 |  |  |  |  | Construction Complete | 0 | 0 | Delayed | Pre-comm delayed — awaiting polymer dosing pump delivery
6 | SYS-SCADA | SCADA & Control System | Electrical | [5 empty] | Not Started | 0 | 0 | Not Started | Dependent on all process systems completing commissioning first
7 | [8 empty] | Not Started
8 | [8 empty] | Not Started
9 | [8 empty] | Not Started
10 | [8 empty] | Not Started
11 | [8 empty] | Not Started
12 | [8 empty] | Not Started
13 | [8 empty] | Not Started
14 | [8 empty] | Not Started
15 | [8 empty] | Not Started
16 | [8 empty] | Not Started
17 | [8 empty] | Not Started
18 | [8 empty] | Not Started
19 | [8 empty] | Not Started
20 | [8 empty] | Not Started
21 | [8 empty] | Not Started
22 | [8 empty] | Not Started
23 | [8 empty] | Not Started
24 | [8 empty] | Not Started
25 | [8 empty] | Not Started
26 | [8 empty] | Not Started
27 | [8 empty] | Not Started
28 | [8 empty] | Not Started
29 | [8 empty] | Not Started
30 | [8 empty] | Not Started
31 | [8 empty] | Not Started
32 | [8 empty] | Not Started
33 | [8 empty] | Not Started
34 | [8 empty] | Not Started
35 | [8 empty] | Not Started
36 | [8 empty] | Not Started
37 | [8 empty] | Not Started
38 | [8 empty] | Not Started
39 | [8 empty] | Not Started
40 | [8 empty] | Not Started
41 | [8 empty] | Not Started
42 | [8 empty] | Not Started
43 | [8 empty] | Not Started
44 | [8 empty] | Not Started
45 | [8 empty] | Not Started
46 | [8 empty] | Not Started
47 | [8 empty] | Not Started
48 | [8 empty] | Not Started
49 | [8 empty] | Not Started
50 | [8 empty] | Not Started

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.