## Cover
EBRORA
ebrora.com
Project Closeout Checklist
Comprehensive project closeout checklist with scored categories covering documentation, defects, financial close, H&S file, and handover requirements.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Closeout Checklist' sheet. This is a scored checklist — work through each category systematically.
2. Categories cover: Documentation, Defects & Snagging, Financial Close, H&S File, Training & O&M, and Handover.
3. Mark each item Pass, Fail, or N/A. Every Fail must have a note explaining what's outstanding.
4. Each category auto-calculates a completion score. The Overall Readiness assessment determines if handover can proceed.
5. READY FOR HANDOVER = all items pass/N-A. NOT READY = any item fails. Complete all items before client handover.
6. Use this as a living document — start populating it 4 weeks before anticipated completion date.
7. The sign-off section at the bottom requires both contractor and client signatures.
8. Print as A4 portrait — take it to the pre-handover meeting as your completion evidence.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Positive / Complete
| Amber | In progress / Medium
| Red | Negative / Critical
Tips
• Start closeout planning at 80% completion — don't leave it until the last week.
• The H&S file is a legal requirement under CDM 2015 — handover cannot proceed without it.
• Agree the defects list with the client BEFORE the handover meeting — no surprises on the day.

## Closeout Checklist
PROJECT CLOSEOUT CHECKLIST
Project:
Completion Date:
Prepared By:
Date:
No. | Checklist Item | Result | Comments / Evidence | Section Score
DOCUMENTATION & RECORDS
1 | As-built drawings issued to client
2 | O&M manuals compiled and issued
3 | Test certificates and commissioning records complete
4 | All RFIs closed and filed
5 | Meeting minutes archive compiled
6 | Photographic record complete
DEFECTS & SNAGGING
7 | Snagging list agreed with client
8 | All Category A defects (safety/function) rectified
9 | Category B defects (cosmetic) programme agreed
10 | Defects liability period start date confirmed
FINANCIAL CLOSE
11 | Final account prepared and submitted
12 | All subcontract final accounts agreed
13 | Retention release schedule confirmed
14 | Outstanding invoices settled or accrued
15 | Daywork sheets agreed and valued
16 | Variation account finalised
H&S FILE & CDM
17 | H&S file compiled per CDM 2015 Reg 12
18 | Residual risk register included in H&S file
19 | Asbestos register (if applicable) included
20 | Fire safety information included
21 | Structural design information included
TRAINING & COMMISSIONING
22 | Client staff training completed (M&E systems)
23 | Building management system handover and training
24 | Emergency procedures briefing delivered
25 | Maintenance schedules issued
HANDOVER & COMPLETION
26 | Practical completion certificate prepared
27 | Keys and access devices handed over
28 | Utility meter readings recorded
29 | Insurance responsibility transferred
30 | Site security responsibility transferred
31 | All temporary works removed
OVERALL READINESS |  |  |  | READY FOR HANDOVER
Contractor PM: |  |  | Date:
Client PM: |  |  | Date:

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.