## Cover
EBRORA
ebrora.com
Site Handover Checklist
A comprehensive checklist for site or section handover — covering documentation, statutory compliance, building services, finishes, externals, safety, and commercial close-out.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Handover Checklist' sheet. Fill in the project details at the top: Project Name, Section/Phase being handed over, Client, Handover Date, and who is conducting the handover.
2. | The checklist is pre-populated with standard handover items grouped under 7 categories. Work through each item and set the Status using the dropdown.
3. | Status options: Pass (item satisfactory), Fail (defect or issue found), Outstanding (not yet complete), or N/A (not applicable to this handover).
4. | Enter who checked each item and the date. Use the Comments column for any notes, defect descriptions, or snag references.
5. | The completion tracker at the top auto-calculates the percentage of items marked Pass or N/A in each category. Aim for 100% before signing off.
6. | Add extra rows within any category if your project requires additional checklist items. The formulas will need adjusting if you add rows.
7. | Complete the sign-off section at the bottom. Both parties should sign to confirm the handover.
Colour Key
Light teal cells — Editable input cells.
Teal category headers — Section dividers grouping related items.
Green — Status is 'Pass' (item satisfactory).
Amber — Status is 'Outstanding' (not yet complete).
Red — Status is 'Fail' (defect found).
Grey — Status is 'N/A' (not applicable).
Tips
Tip 1: | Walk the site with this checklist on a tablet. Go category by category — documentation first (office-based), then a physical walkthrough for M&E, finishes, and externals.
Tip 2: | Any item marked 'Fail' should have a corresponding entry on your Snagging List with a reference number in the Comments column. Don't just fail it — log the defect properly.
Tip 3: | For phased handovers, save a copy per section (e.g. 'Handover Checklist — Block A.xlsx'). The completion tracker lets you see at a glance which sections are ready.

## Handover Checklist
SITE HANDOVER CHECKLIST
Project: | Riverside Gateway Phase 2 |  | Section: | Block A — Levels G to 3
Client: | Salford City Council |  | Handover Date: | 2026-04-15
Conducted By: | S. Patel / J. Hartley |  | Overall Complete: | Practical Completion
Overall Completion: | 87.5% | Pass: | 12 | Fail: | 1
COMPLETION TRACKER
A. DOCUMENTATION
1 | O&M manuals received and complete | Pass | J. Hartley | 2026-04-10
2 | As-built drawings issued (full set) | Pass | J. Hartley | 2026-04-10
3 | Test certificates and commissioning records | Pass | J. Hartley | 2026-04-10
4 | Building control sign-off / completion certificate | Pass | J. Hartley | 2026-04-10
5 | Planning condition discharge letters | Pass | J. Hartley | 2026-04-10
6 | CDM Health & Safety File complete | Pass | J. Hartley | 2026-04-10
7 | Warranties and guarantees collated | Outstanding | D. Khan |  | Warranties for roofing subcontractor still outstanding — chased 08/04
8 | Meter readings recorded (gas, electric, water) | Pass | S. Patel | 2026-04-12
B. STATUTORY & COMPLIANCE
9 | Fire alarm system commissioned and certified | Pass | T. Brennan | 2026-04-11
10 | Emergency lighting tested and certified | Pass | T. Brennan | 2026-04-11
11 | Fire risk assessment completed | Pass | T. Brennan | 2026-04-11
12 | Electrical installation certificate (EICR) issued | Pass | T. Brennan | 2026-04-11
13 | Gas safety certificate issued | Pass | T. Brennan | 2026-04-11
14 | Lift / escalator commissioning certificates | N/A |  |  | No lifts in Block A
15 | Water hygiene risk assessment and L8 compliance | Fail | Northern M&E |  | L8 chlorination results pending — retest booked 16/04. Snag ref SNG-089.
16 | Asbestos management survey (if applicable) | N/A |  |  | Pre-2000 building — R&D survey complete, no asbestos found
C. M&E SERVICES
17 | HVAC system tested, balanced, and commissioned
18 | BMS / controls operational and demonstrated
19 | Hot and cold water systems flushed and tested
20 | Drainage CCTV survey complete and satisfactory
21 | Electrical distribution boards labelled and tested
22 | Data / comms infrastructure tested
23 | Lightning protection tested and certified
D. FINISHES & INTERNALS
24 | All rooms clean, dust-free, and accessible
25 | Floor finishes complete and undamaged
26 | Wall and ceiling finishes complete
27 | Doors operate correctly (closers, locks, ironmongery)
28 | Sanitary ware installed and functional
29 | Snagging list items resolved (see defects list)
30 | Touch-up painting complete
E. EXTERNAL WORKS
31 | External landscaping complete and established
32 | Car park surfacing, markings, and signage complete
33 | External lighting operational
34 | Drainage and gullies clear and functional
35 | Boundary fencing and gates complete
36 | Footpaths and kerbing complete
F. SAFETY & ACCESS
37 | All temporary works removed (scaffold, hoarding, etc.)
38 | Site compound and welfare removed
39 | Perimeter security operational (CCTV, access control)
40 | Key schedule issued and all locks operational
41 | Fire escape routes clear and signed
42 | First aid provisions in place
G. COMMERCIAL
43 | Final account agreed or position statement issued
44 | All variations valued and agreed
45 | Retention release schedule confirmed
46 | Defects liability period start date agreed
47 | Outstanding claims resolved or documented
48 | Subcontractor final accounts progressed
SIGN-OFF
Contractor: |  |  | Date: |  | Signature:
Client: |  |  | Date: |  | Signature:
ebrora.com — Free professional construction management templates

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.