## Cover
EBRORA
ebrora.com
Near Miss / Incident Report Log
Log and track near misses, incidents, and dangerous occurrences — from initial report through investigation to corrective action close-out.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Incident Report Log” tab. Each row records one event — a near miss, incident, or dangerous occurrence.
2. | Enter the date and time of the event and select the Report Type from the dropdown: Near Miss, Incident, or Dangerous Occurrence.
3. | Write a clear, factual description of what happened. Include enough detail that someone who wasn’t there can understand the event.
4. | Record the location on site and who reported it.
5. | Select the Severity from the dropdown: Low, Medium, High, or Critical. Use your site’s risk matrix if you have one.
6. | Describe the immediate action taken at the time of the event (e.g. area cordoned off, first aid administered, works stopped).
7. | Set the Status: Open (just reported), Under Investigation (being looked into), or Closed (all actions complete).
8. | For additional detail, click the [+] button above the optional columns to expand: Injured Party, Injury Type, RIDDOR Reportable, Root Cause, Corrective Action, Action Owner, Action Due Date, Date Closed, Witnesses, and Notes.
9. | For incidents involving injury, always fill in the Injured Party, Injury Type, and RIDDOR Reportable fields in the optional section.
10. | Assign corrective actions with an owner and due date. The register will flag overdue actions automatically in red.
11. | The summary dashboard at the top auto-calculates event counts, severity breakdown, near miss ratio, overdue actions, and RIDDOR count.
Colour Key
• | Light teal cells (#E8F6F7) = User input / editable fields. Type directly into these.
• | Dark navy headers (#1B2A4A) = Column headers. Do not edit.
• | Severity colours across the row: Green = Low, Amber = Medium, Red = High, Dark Red text = Critical.
• | Status colours: Red = Open, Amber = Under Investigation, Green = Closed.
• | Red highlight on Action Due Date = Corrective action is overdue (past today, status not Closed).
• | Amber highlight on RIDDOR column = Event is RIDDOR reportable.
Tips
• | Report near misses just as diligently as actual incidents. A high near miss ratio is a positive sign of a strong reporting culture — aim for at least 10 near misses for every 1 incident.
• | Review the log weekly at your site safety meeting. Use the filters to show only Open and Under Investigation items.
• | RIDDOR-reportable events must be reported to the HSE within the statutory timeframe. Use this register to track them but don’t rely on it as your sole RIDDOR notification — always submit through the HSE website.

## Incident Report Log
NEAR MISS / INCIDENT REPORT LOG |  |  | Total Events: | 5 |  | Near Misses: | 3
|  |  | Incidents: | 1 |  | Dangerous Occurrences: | 1
|  |  | Low: | 2 | Medium: | 1 | High: | 1 | Critical: | 1
|  |  | Open: | 1 |  | Under Investigation: | 1 |  | Overdue Actions: | 1
|  |  | RIDDOR Reportable: | 1 |  | NM:Incident Ratio: | 3:1
▸ Optional Fields — Click [+] to expand
Ref No. | Date of Event | Time | Report Type | Description of Event | Location on Site | Reported By | Severity | Immediate Action Taken | Status | Injured Party Name | Injury Type | RIDDOR Reportable | Root Cause | Corrective Action | Action Owner | Action Due Date | Date Closed | Witnesses | Notes
1 | 2026-03-16 | 8:45 | Near Miss | Loose scaffold board on level 2 identified during morning walkround. Board not secured with clips, could have fallen onto walkway below. | Block A, Level 2 scaffold, north elevation | K. Price | Medium | Area cordoned off. Scaffold crew called to re-secure board immediately. Scaffold inspection brought forward. | Closed |  |  | No | Scaffold board clips missing after overnight wind. Clips not checked during pre-start. | All scaffold to be checked for loose clips at pre-start daily. Additional clips ordered. | M. Davies | 2026-03-17 | 2026-03-17 | J. Adams, S. Hall | Closed same day. Toolbox talk on scaffold safety held 17/03.
2 | 2026-03-17 | 11:20 | Incident | Operative sustained minor cut to left hand while cutting copper pipe. Pipe slipped from vice. First aid administered on site. | Plant Room 2, Basement Level | R. Thomas | Low | First aider attended. Wound cleaned and dressed. Operative returned to work after 15 minutes. | Closed | P. Morgan | Minor Cut / Abrasion | No | Pipe not properly secured in vice. Operative rushing to meet programme. | Revised SOP for pipe cutting issued. Operative re-briefed on vice use. | R. Thomas | 2026-03-19 | 2026-03-19 | D. Evans | Minor injury. No lost time.
3 | 2026-03-18 | 14:05 | Near Miss | Telehandler reversed within 2m of pedestrian walkway without a banksman. No contact made but pedestrians were present in the area. | Block C, external hardstanding, south side | M. Davies | High | Telehandler operations stopped immediately. Banksman assigned. Exclusion zone re-established with barriers. | Under Investigation |  |  | No | Banksman had left the area without informing driver. Traffic management plan not followed. | Disciplinary review for banksman. All plant operators re-briefed on traffic management plan. | M. Davies | 2026-03-22 |  | T. Williams, 2x site operatives (statements taken) | Investigation ongoing. CCTV footage reviewed.
4 | 2026-03-19 | 9:30 | Dangerous Occurrence | Tower crane anti-collision system activated unexpectedly during routine lift. Load held safely but all crane operations ceased for inspection. | Tower Crane TC-01, central compound | Site Engineer | Critical | All crane operations ceased. Crane engineer called. Exclusion zone extended to 25m radius around crane base. | Open |  |  | Yes |  |  | M. Davies | 2026-03-21 |  | Crane operator, slinger/signaller, lifting supervisor | HSE notified under RIDDOR. Crane manufacturer contacted. Awaiting engineer report.
5 | 2026-03-20 | 7:15 | Near Miss | Trip hazard identified at site entrance — temporary cable run across pedestrian route not covered or ramped. Identified during pre-start walkround before operatives arrived. | Main site entrance gate, pedestrian route | S. Hall | Low | Cable covered with rubber ramp immediately. Temporary works team notified to install permanent cable route. | Closed |  |  | No | Electrical subcontractor ran cable late previous evening and did not install protection. | Subcontractor issued improvement notice. All temporary cable routes to be inspected at close of shift. | R. Thomas | 2026-03-20 | 2026-03-20 |  | Quick fix. No risk to operatives as identified before site opened.

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.