## Cover
EBRORA
ebrora.com
Excavation Inspection Checklist
Inspect and manage all excavations on site — track edge protection, ground support, service protection, water ingress, and remedial actions in one register.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Excavation Inspection Checklist” tab. Each row records one inspection of one excavation.
2. | Enter the Date and the Excavation Ref / Location (e.g. “Trench TR-05, Drainage Run DR-03, Grid C1–C8”).
3. | Select the Excavation Type from the dropdown: Trench, Pit, Basement, Shaft, Open Cut, or Other.
4. | Enter the Depth in metres. Excavations deeper than 1.2m generally require formal support (shoring, battering, or benching).
5. | Work through the three safety check columns: Edge Protection in Place, Support/Battering Adequate, and Services Identified & Protected. Select Yes or No for each.
6. | Set the Overall Verdict: Pass (safe to work in/around), Fail (excavation must be barriered off — no access), or Remedial Work Required (issues to fix before next shift).
7. | Enter the inspector’s name. The inspector must be a competent person — typically a site engineer, site manager, or appointed person with relevant experience.
8. | For additional detail, expand the optional columns: Permit to Dig Ref, Ground Conditions, Water Ingress, Adjacent Structures at Risk, Defects Found, Remedial Action, Date Remedial Completed, and Notes.
9. | The dashboard auto-calculates total inspections, pass rate, failed checks, outstanding remedials, type breakdown, average and maximum depth.
Colour Key
• | Light teal cells = User input / editable fields.
• | Dark navy headers = Column headers. Do not edit.
• | Verdict: Green = Pass, Amber = Remedial Work Required, Red = Fail.
• | Red cell in any Y/N check column = “No” — that safety measure has failed.
• | Full-row red highlight = Overall Verdict is “Fail”.
• | Red in Water Ingress = “Significant” water ingress detected.
Tips
• | Under CDM 2015 and the Construction (Design and Management) Regulations, excavations must be inspected by a competent person before work begins each shift, after any event likely to affect stability (heavy rain, vehicle loading), and after any accidental fall of material.
• | Always check for underground services before digging. Use CAT and Genny scanners and refer to utility plans. Services Identified & Protected must be “Yes” before any excavation work proceeds.
• | Failed excavations must be barriered immediately with “DANGER — NO ENTRY” signage. No person may enter or work adjacent to a failed excavation until remedial work is completed and a re-inspection records a Pass.

## Excavation Inspection Checklist
EXCAVATION INSPECTION CHECKLIST |  |  |  | Total Inspections: | 5 |  | Pass Rate: | 60%
|  |  |  | Pass: | 3 | Remedial: | 1 | Fail: | 1
|  |  |  | Failed Checks (any No): | 2 |  | Outstanding Remedials: | 1
|  |  |  | Trench: | 3 | Pit: | 1 | Open Cut: | 1
|  |  |  | Avg Depth (m): | 3.02 |  | Max Depth (m): | 4.2
▸ Optional Fields — Click [+] to expand
Inspection No. | Date | Excavation Ref / Location | Excavation Type | Depth (m) | Edge Protection OK | Support / Battering OK | Services Identified | Overall Verdict | Inspected By | Permit to Dig Ref | Ground Conditions | Water Ingress | Adj. Structures at Risk | Defects Found | Remedial Action | Date Remedial Completed | Notes
1 | 2026-03-16 | Trench TR-05, Drainage Run DR-03, Grid C1–C8 | Trench | 2.8 | Yes | Yes | Yes | Pass | R. Thomas | PTD-019 | Firm/Stable | None | No |  |  |  | Trench box shoring in place. CAT & Genny scan completed pre-dig. All clear.
2 | 2026-03-17 | Pit EX-02, Lift Pit Block A, Grid B3 | Pit | 3.5 | Yes | Yes | Yes | Pass | R. Thomas | PTD-020 | Soft/Clay | Minor | Yes |  |  |  | Adjacent to existing retaining wall. Monitoring points installed. Minor seepage from clay — sump pump running.
3 | 2026-03-18 | Trench TR-07, Foul Drainage, Grid E2–E5 | Trench | 1.8 | Yes | No | Yes | Remedial Work Required | R. Thomas | PTD-021 | Sandy/Granular | Minor | No | Trench box displaced 300mm at south end due to sandy ground movement overnight. Gap between box and trench wall. | Re-seat trench box. Backfill void behind box with pea gravel. Re-inspect before operatives enter. |  | Trench barriered. No entry until remedial complete.
4 | 2026-03-19 | Open Cut OC-01, Attenuation Tank Formation, South Compound | Open Cut | 4.2 | No | Yes | Yes | Fail | R. Thomas | PTD-022 | Made Ground | Significant | No | Edge protection barriers removed by subcontractor for plant access and not replaced. Significant water accumulation from overnight rain — approx 600mm standing water. | Excavation barriered and signed DANGER NO ENTRY. Pump out standing water. Reinstate edge protection. Investigate subcontractor for removing barriers. |  | Failed — critical. Two issues: no edge protection + significant water. HSE advisor notified.
5 | 2026-03-20 | Trench TR-05, Drainage Run DR-03, Grid C1–C8 | Trench | 2.8 | Yes | Yes | Yes | Pass | R. Thomas | PTD-019 | Firm/Stable | None | No |  |  |  | Routine daily inspection. Shoring and edge protection in good order. Pipe laying 70% complete.

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.