## Cover
EBRORA
ebrora.com
Weekly Safety Inspection Checklist
A structured weekly walkround checklist covering housekeeping, access, scaffolding, excavations, welfare, fire safety, PPE, plant, and environmental compliance.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Weekly Safety Checklist” tab. The checklist is pre-populated with 20 standard inspection items grouped by category.
2. | Carry out your weekly walkround and work through each check item. Select “Yes” (compliant), “No” (non-compliant), or “N/A” (not applicable this week) in the Compliant column.
3. | For any non-compliant item, set the Priority (Low, Medium, High, or Critical) and describe the Action Required.
4. | Assign the action to a named person in “Assigned To” and set a Due Date for resolution.
5. | Set the Status to “Open” for new actions. Update to “Closed” once the action is complete.
6. | Enter the inspector’s name in “Inspected By” (usually the site manager or HSE advisor carrying out the walkround).
7. | For additional detail, expand the optional columns: Location/Area, Photo Ref, Date Closed, Root Cause, Follow-Up Required, and Notes.
8. | You can add extra check items below the pre-populated ones, or delete items not relevant to your site.
9. | The summary dashboard at the top auto-calculates compliance rate, non-compliant items, open and overdue actions, and a priority breakdown.
10. | Duplicate this sheet each week (right-click tab → Move or Copy → tick “Create a copy”) to build a running record of weekly inspections.
Colour Key
• | Light teal cells (#E8F6F7) = User input / editable fields.
• | Dark navy headers (#1B2A4A) = Column headers. Do not edit.
• | Teal-filled rows = Category header rows (Housekeeping, Access/Egress, etc.).
• | Compliant column: Green = Yes, Red = No.
• | Priority row colours: Green = Low, Amber = Medium, Red = High/Critical.
• | Status: Red = Open, Green = Closed.
• | Red cell in Due Date = Action is overdue (past today, status still Open).
Tips
• | Conduct your weekly safety inspection on the same day each week (e.g. every Monday morning) so it becomes routine. Consistency drives compliance.
• | Walk the entire site during the inspection — don’t just check the areas where work is active. Idle areas accumulate hazards.
• | Close out actions promptly. Review all Open items at your weekly safety meeting and escalate anything overdue.

## Weekly Safety Checklist
WEEKLY SAFETY INSPECTION CHECKLIST
Inspection Date: | 2026-03-20 | Inspector Name: | M. Davies (Site Manager) |  | Weather: | Overcast, dry, light wind
Total Items: | 23 |  | Compliance Rate: | 82.61% |  | Non-Compliant: | 4
Open Actions: | 4 |  | Overdue Actions: | 0 |  | Closed Actions: | 0
Low: | 1 | Medium: | 2 | High: | 1 | Critical: | 0
▸ Optional Fields — Click [+] to expand
Item No. | Inspection Category | Check Item | Compliant | Priority | Action Required | Assigned To | Due Date | Status | Inspected By | Location / Area | Photo Ref | Date Closed | Root Cause | Follow-Up Req (Y/N) | Notes
HOUSEKEEPING
1 | Housekeeping | Site areas clean and tidy, free from unnecessary materials and waste | Yes | [5 empty] | M. Davies
2 | Housekeeping | Walkways and access routes clear of obstructions and trip hazards | No | Medium | Remove stacked formwork from main walkway. Install barrier. | D. Evans | 2026-03-24 | Open | M. Davies
3 | Housekeeping | Waste segregated correctly (general, timber, metal, hazardous) | Yes | [5 empty] | M. Davies
ACCESS / EGRESS
4 | Access / Egress | Site entrance and exit points clearly signed and unobstructed | Yes | [5 empty] | M. Davies
5 | Access / Egress | Pedestrian and vehicle routes clearly segregated with barriers/signage | Yes | [5 empty] | M. Davies
6 | Access / Egress | Emergency escape routes clear and signed | Yes | [5 empty] | M. Davies
SCAFFOLDING
7 | Scaffolding | All scaffolds have current inspection tags (within 7 days) | Yes | [5 empty] | M. Davies
8 | Scaffolding | Toe boards, guard rails, and brick guards in place on all working platforms | No | High | Missing toe boards on SC-07 level 2 landing. Scaffold tagged DO NOT USE. | K. Price | 2026-03-22 | Open | M. Davies
9 | Scaffolding | Scaffold access ladders secured and in good condition | Yes | [5 empty] | M. Davies
EXCAVATIONS
10 | Excavations | All excavations fenced/barriered with edge protection | Yes | [5 empty] | M. Davies
11 | Excavations | Excavation support (shoring/battering) in place and adequate | N/A | [5 empty] | M. Davies
WELFARE
12 | Welfare | Toilet and washing facilities clean, stocked, and operational | Yes | [5 empty] | M. Davies
13 | Welfare | Drying room / changing facilities available and adequate | Yes | [5 empty] | M. Davies
14 | Welfare | Drinking water available and clearly labelled | Yes | [5 empty] | M. Davies
FIRE SAFETY
15 | Fire Safety | Fire extinguishers in place, accessible, and within inspection date | Yes | [5 empty] | M. Davies
16 | Fire Safety | Fire assembly point clearly signed and accessible | Yes | [5 empty] | M. Davies
PPE COMPLIANCE
17 | PPE Compliance | All operatives wearing correct PPE for their activity | No | Low | 2 operatives in compound area without hi-vis. Verbal warning given. | R. Thomas | 2026-03-23 | Open | M. Davies
18 | PPE Compliance | RPE / hearing protection being used where required | Yes | [5 empty] | M. Davies
PLANT & EQUIPMENT
19 | Plant & Equipment | All plant has current inspection/test certificates displayed | Yes | [5 empty] | M. Davies
20 | Plant & Equipment | Pre-use checks being completed and recorded by operators | Yes | [5 empty] | M. Davies
21 | Plant & Equipment | Exclusion zones around plant operations maintained | Yes | [5 empty] | M. Davies
ENVIRONMENTAL
22 | Environmental | Dust suppression measures in place and operational | Yes | [5 empty] | M. Davies
23 | Environmental | Spill kits available and stocked near fuel/chemical storage | Yes | [5 empty] | M. Davies
24 | Environmental | Site boundary hoarding intact and secure | No | Medium | Section of hoarding panel loose at south boundary. Needs re-fixing. | S. Hall | 2026-03-24 | Open | M. Davies

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.