## Cover
EBRORA
ebrora.com
Crane Lift Plan Summary Sheet
A per-lift record sheet covering crane specification, load details, rigging arrangement, and pre-lift safety checks — supporting compliance with BS 7121 and LOLER 1998.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | This form is completed once per planned lift. Save a copy for each lift (e.g. 'Lift Plan LP-001 Steel Column A1.xlsx').
2. | Fill in Section 1 (Lift Identity) with the lift reference, date, and project details.
3. | Complete Section 2 (Crane Details) with the crane type, capacity, and configuration for this specific lift.
4. | In Section 3 (Load Details), enter the item being lifted, its total weight, dimensions, and centre of gravity position.
5. | Section 4 (Rigging Arrangement) records the slings, shackles, and lifting accessories. Enter SWL and condition for each.
6. | Work through Section 5 (Pre-Lift Checklist) and mark each item Pass or Fail. All items must be Pass before the lift proceeds.
7. | Section 6 is the Authorisation sign-off. The Appointed Person, Crane Supervisor, and Slinger/Signaller must all sign.
Colour Key
Light teal cells — Editable input fields.
Teal section headers — Section dividers.
Green — Pre-lift check is 'Pass'.
Red — Pre-lift check is 'Fail'. Lift must NOT proceed.
Tips
Tip 1: | Under LOLER 1998, every lift must be planned by a competent person. This form provides the documented evidence that planning took place — keep it in the lifting file.
Tip 2: | The Duty Chart / Load Chart radius and SWL must be checked against the actual lift configuration. If in doubt, get the crane supplier to confirm in writing.
Tip 3: | For tandem lifts (two cranes), complete a separate form for each crane and cross-reference them. Tandem lifts require a specific method statement beyond this summary.

## Lift Plan
CRANE LIFT PLAN — SUMMARY SHEET
In accordance with LOLER 1998, BS 7121, and CDM 2015
1. LIFT IDENTITY
Lift Plan Ref: | LP-2026-014 | Date of Lift: | 2026-03-23 | Time: | 8:30
Project: | Riverside Gateway Phase 2 |  |  | Location: | Grid B3 — Level 2
Appointed Person: | K. Davies | Crane Supervisor: | K. Davies | Lift Category: | Standard
2. CRANE DETAILS
Crane Type: | Tower Crane | Make / Model: | Liebherr 172 EC-B 8 | Fleet / ID No.: | TC-001
Max SWL (tonnes): | 8.0 | SWL at Radius: | 3.2t @ 45m | Max Radius (m): | 55
Hook Height (m): | 42 | Jib Length (m): | 55 | Counterweight: | Standard config
Last Inspection: | 2026-03-01 | Next Thorough Exam: | 2026-09-01 | Cert. No.: | LOLER-TC001-2026
3. LOAD DETAILS
Description: | Universal steel column UC 305x305x118 — 12m length |  |  | Drawing Ref: | S-201 Rev C
Total Weight (kg): | 1,416 | Rigging Weight (kg): | 85 | Total Lift (kg): | 1501
Dimensions (LxWxH): | 12.0m x 0.31m x 0.31m | C of G Position: | Centre — uniform section | Wind Limit: | 38 mph max
Lift Radius (m): | 32 | % of SWL: | 46.91% | Within Capacity: | Yes
4. RIGGING ARRANGEMENT
Item | Description | SWL (tonnes) | Cert No. | Condition | Inspected By
Sling 1 | 2-leg chain sling, 3m legs, 60° incl. | 3.2 | CS-2024-0891 | Good | K. Davies
Sling 2 | 2-leg chain sling, 3m legs, 60° incl. | 3.2 | CS-2024-0892 | Good | K. Davies
Shackle 1 | Bow shackle 4.75t WLL | 4.75 | SH-2025-1104 | Good | K. Davies
Shackle 2 | Bow shackle 4.75t WLL | 4.75 | SH-2025-1105 | Good | K. Davies
Tag line | 10m polypropylene tag line | N/A | N/A | Good | Slinger
5. PRE-LIFT SAFETY CHECKLIST
Check Item |  |  |  | Result | Notes
Lift plan reviewed and understood by all personnel |  |  |  | Pass
Exclusion zone established and barriered |  |  |  | Pass
Banksman / signaller in position with clear sight lines |  |  |  | Pass
Wind speed checked and within limits |  |  |  | Pass | Measured 22mph at 08:15 — within 38mph limit
Crane on firm, level ground / outriggers fully extended |  |  |  | Pass
Lifting accessories inspected and within certification |  |  |  | Pass
Load weight confirmed (weighed or from manufacturer data) |  |  |  | Pass
Sling angles checked — no leg exceeds 60° from vertical |  |  |  | Pass
Tag lines attached and manned |  |  |  | Pass
No persons under suspended load confirmed |  |  |  | Pass
Communications checked (radio / hand signals agreed) |  |  |  | Pass
Overhead obstructions / power lines checked |  |  |  | Pass
ALL CHECKS PASS: |  |  | YES — PROCEED
6. AUTHORISATION — LIFT APPROVED TO PROCEED
Appointed Person: | K. Davies | Signature: |  | Date/Time:
Slinger/Signaller: | M. Briggs | Signature: |  | CPCS Card No.: | CPCS-SL-44821
Crane Operator: | K. Davies | Signature: |  | CPCS Card No.: | CPCS-TC-31205
IF ANY PRE-LIFT CHECK FAILS, THE LIFT MUST NOT PROCEED UNTIL THE ISSUE IS RESOLVED AND RE-CHECKED.
ebrora.com — Free professional construction management templates

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.