## Cover
EBRORA
ebrora.com
Lifting Operations Register
Record and manage all lifting operations on site — track crane capacity, load weights, appointed persons, and lift status in one LOLER-compliant register.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Lifting Operations Register” tab. Each row records one lifting operation.
2. | Enter the date of the lift and a clear description of what is being lifted (e.g. “Steel beam S1–S4, 6m long”, “Precast staircase flight, Block A”).
3. | Record the specific location on site where the lift is taking place.
4. | Enter the Crane / Plant Used (e.g. “TC-01 Tower Crane”, “50T Mobile Crane”, “Telehandler TH-02”) and its rated Capacity in tonnes.
5. | Enter the Load Weight in tonnes. The register will auto-calculate the percentage of crane capacity used in the optional columns.
6. | Record the Appointed Person (the competent person responsible for planning the lift) and the Slinger/Signaller on the ground.
7. | Set the Status: Planned (scheduled but not yet carried out), Completed (lift done safely), or Aborted (lift stopped or cancelled — record the reason in Notes).
8. | For additional detail, click the [+] button above the optional columns to expand: Lift Plan Ref, RAMS Ref, Weather Check (Pass/Fail), Radius (m), % Capacity Used (auto-calculated), and Notes.
9. | The summary dashboard at the top auto-calculates total lifts, status breakdown, average capacity usage, critical lifts (over 80% capacity), and aborted lift count.
Colour Key
• | Light teal cells (#E8F6F7) = User input / editable fields. Type directly into these.
• | Dark navy headers (#1B2A4A) = Column headers. Do not edit.
• | Status: Green = Completed, Amber = Planned, Red = Aborted.
• | % Capacity Used: Green = under 60%, Amber = 60–80%, Red = over 80% (critical lift territory).
• | Weather Check: Red = Fail (lift should not proceed in adverse conditions).
Tips
• | Under LOLER 1998 (Lifting Operations and Lifting Equipment Regulations), every lifting operation must be properly planned, supervised by a competent person, and carried out safely. This register supports your compliance records.
• | Any lift exceeding 80% of the crane’s rated capacity is flagged as critical. These lifts require enhanced planning, additional risk assessment, and approval from the Appointed Person before proceeding.
• | Always check wind speed before lifting. Most tower cranes have a maximum operational wind speed of 20 m/s (45 mph). If in doubt, abort the lift and record the reason.

## Lifting Operations Register
LIFTING OPERATIONS REGISTER |  |  |  | Total Lifts: | 5 |  | Completed: | 4
|  |  |  | Planned: | 0 |  | Aborted: | 1
|  |  |  | Avg % Capacity: | 46.51% |  | Critical Lifts (>80%): | 2
|  |  |  | Weather Fails: | 1 |  | Max Load (T): | 7.5
▸ Optional Fields — Click [+] to expand
Lift No. | Date | Lift Description | Location | Crane / Plant Used | Capacity (T) | Load Weight (T) | Appointed Person | Slinger / Signaller | Status | Lift Plan Ref | RAMS Ref | Weather Check | Radius (m) | % Capacity Used | Notes
1 | 2026-03-16 | Steel beam package S1–S4 (4 beams bundled, 6m long) | Block C, Grid C1–C4, Ground to Level 1 | TC-01 Tower Crane | 8 | 3.2 | J. Griffiths (AP) | K. Price / D. Evans | Completed | LP-026 | RAMS-041 | Pass | 25 | 40% | Routine lift. No issues.
2 | 2026-03-17 | Precast concrete staircase flight (Block A, Stair 1) | Block A, Stairwell North, Ground to Level 1 | 50T Mobile Crane (Liebherr LTM 1050) | 50 | 4.8 | J. Griffiths (AP) | S. Hall / T. Williams | Completed | LP-027 | RAMS-042 | Pass | 18 | 9.6% | Tandem lift considered but single crane sufficient at this radius.
3 | 2026-03-18 | M&E rooftop plant unit (AHU-01, packaged) | Block B, Roof Level, Plant Plinth PP-01 | TC-01 Tower Crane | 8 | 6.8 | J. Griffiths (AP) | K. Price / R. Jones | Aborted | LP-028 | RAMS-043 | Fail | 30 | 85% | Wind speed exceeded 18 m/s at jib height. Lift aborted at 09:15. Rescheduled to 20/03.
4 | 2026-03-19 | Reinforcement cage for pile cap PC-07 (12m long) | Block C, Piling Mat, Grid E3 | 50T Mobile Crane (Liebherr LTM 1050) | 50 | 2.1 | J. Griffiths (AP) | S. Hall / D. Evans | Completed | LP-029 | RAMS-044 | Pass | 12 | 4.2% | Long load — tag lines used at both ends. Exclusion zone set at 10m.
5 | 2026-03-20 | Generator set (350 kVA) relocation to new compound | From: Temp Compound A. To: Compound B (south) | TC-01 Tower Crane | 8 | 7.5 | J. Griffiths (AP) | K. Price / T. Williams | Completed | LP-030 | RAMS-045 | Pass | 22 | 93.75% | Critical lift — 93.8% capacity. Enhanced planning and dual signaller arrangement used. AP present throughout.

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.