## Cover
EBRORA
ebrora.com
Hot Works Permit Log
Track and manage hot works permits across your site — issue, monitor, close out, and flag overdue permits in one register.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Hot Works Permit Log” tab. Each row is one permit entry.
2. | Enter the date the permit is issued. Hot works permits on this register are valid for one calendar day only.
3. | Describe the hot works being carried out (e.g. “Grinding steel beams at level 2”, “Welding pipework in plant room”).
4. | Record the specific location on site where the hot works will take place.
5. | Enter the name and company of the person the permit is issued to, and the name of the issuing authority (usually the site manager or fire safety coordinator).
6. | Confirm who has been assigned fire watch duty in the “Fire Watch Assigned” column. This is a mandatory field for hot works.
7. | Set the Status to “Open” when the permit is issued. Change to “Closed” at the end of the day once fire watch is complete and the area has been checked. Use “Cancelled” if works did not proceed.
8. | When closing the permit, enter the name of the person who closed it out in “Closed By”.
9. | Use the Notes column for anything extra — fire watch duration, specific precautions, or follow-up actions.
Colour Key
• | Light teal cells (#E8F6F7) = User input / editable fields. Type directly into these.
• | Dark navy headers (#1B2A4A) = Column headers. Do not edit.
• | Green row = Status is “Closed” — permit completed and closed out.
• | Amber row = Status is “Open” — permit is active today.
• | Red row = Permit is overdue — date is before today and status is still “Open”. Close it out immediately.
• | Grey row = Status is “Cancelled”.
Tips
• | Hot works permits should be issued fresh each day. Never carry a permit over to the next day — issue a new one.
• | Fire watch must continue for a minimum of 60 minutes after hot works cease. Record the end time in Notes if needed.
• | Use the filter arrows on the header row to view only open or overdue permits for your daily check.

## Hot Works Permit Log
HOT WORKS PERMIT LOG |  |  | Total Permits: | 5 |  | Open: | 1
|  |  | Closed: | 3 |  | Overdue: | 1
Permit No. | Date | Description of Works | Location | Issued To (Name / Company) | Issuing Authority | Fire Watch Assigned | Status | Closed By | Notes
1 | 2026-03-16 | Grinding structural steel connections — Block A roof level | Block A, Roof Level, Grid C3-C7 | D. Evans / ProSteel Ltd | M. Davies (Site Manager) | K. Price | Closed | M. Davies | Fire watch completed 17:30. Area inspected — no issues.
2 | 2026-03-17 | Welding pipework brackets in boiler room | Plant Room 2, Basement Level | R. Jones / MechServ Ltd | M. Davies (Site Manager) | S. Hall | Closed | M. Davies | Sprinkler system isolated during works. Reinstated and tested at 16:00.
3 | 2026-03-18 | Cutting steel decking for service penetrations | Block B, Level 1, Zones 4-6 | T. Williams / ProSteel Ltd | M. Davies (Site Manager) | K. Price | Closed | R. Thomas | Fire blankets deployed. All hot cut edges treated with intumescent paint.
4 | 2026-03-19 | Brazing copper pipework at riser connection | Block A, Riser R2, Level 3 | P. Morgan / MechServ Ltd | R. Thomas (Asst. Site Manager) | J. Adams | Open |  | Fire watch ongoing. Permit to be closed out by end of day.
5 | 2026-03-20 | Welding handrail fixings to external staircase | External Staircase S1, North Elevation | D. Evans / ProSteel Ltd | M. Davies (Site Manager) | K. Price | Cancelled |  | Works postponed due to high winds. Rescheduled to 23/03.

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.