System Turnover Certificate

Formal certificate confirming that a defined system has achieved mechanical completion and is ready for safe transfer from the construction team to the commissioning team. This certificate confirms that all construction, installation, inspection, and pre-commissioning activities within the system boundary are complete (or that residual items have been assessed and do not prevent safe commissioning).

Certificate Details

| Certificate No.: | Enter unique system turnover certificate number |
| --- | --- |
| Date: | DD / MM / YYYY |
| Project Name: | Enter project name |
| Contract Number: | Enter contract number |
| Prepared By: | Name / role |

System Identification

| System Name: | Enter system name |
| --- | --- |
| System Number: | Enter system identification number |
| System Description: | Enter brief description of system function and scope |
| P&ID Reference(s): | Enter P&ID drawing number(s) defining the system boundary |
| System Boundary Drawing Ref: | Enter turnover boundary drawing reference |
| Associated Subsystems: | Enter related subsystem references if applicable |
| Location / Area: | Enter plant area or building reference |
| Design Contractor: | Enter design organisation name |
| Installation Contractor: | Enter principal installation contractor |
| Commissioning Contractor: | Enter commissioning contractor name |

Turnover Prerequisites

All items must be confirmed as complete (Y), not applicable (NA), or identified as outstanding with a reference to the punch list.

| No. | Prerequisite Item | Y / N / NA | Reference / Comments |
| --- | --- | --- | --- |
| 1 | System boundary defined and agreed — all equipment and piping within scope identified |  |  |
| 2 | All construction and installation work within the system boundary complete |  |  |
| 3 | Pre-commissioning punch list issued and all Category A items closed out |  |  |
| 4 | All pressure tests complete with signed certificates |  |  |
| 5 | All flushing and cleaning complete with signed records |  |  |
| 6 | All NDT and weld inspection complete with signed reports |  |  |
| 7 | All alignment checks complete (pumps, motors, couplings, etc.) |  |  |
| 8 | All electrical installation and termination complete with test certificates |  |  |
| 9 | All instrumentation installed, calibrated, and loop-checked with signed records |  |  |
| 10 | All cable insulation resistance (Megger) tests complete |  |  |
| 11 | All RCD trip tests and continuity tests complete |  |  |
| 12 | All earthing and bonding tests complete |  |  |
| 13 | All painting, coating, and corrosion protection complete |  |  |
| 14 | All insulation and lagging complete (thermal, acoustic) |  |  |
| 15 | Safety systems operational (fire detection, gas detection, emergency shutdown) |  |  |
| 16 | All safety devices tested and commissioned (relief valves, rupture discs, interlocks) |  |  |
| 17 | As-built drawings available for the system |  |  |
| 18 | O&M documentation available for all equipment within the system |  |  |
| 19 | Spare parts delivered and catalogued |  |  |
| 20 | Operator training completed for the system |  |  |
| 21 | Isolation philosophy and lock-off procedures in place |  |  |
| 22 | HAZOP / risk assessment close-out actions completed for this system |  |  |
| 23 | DSEAR / ATEX compliance confirmed where applicable |  |  |
| 24 | All permits and regulatory approvals in place for commissioning activities |  |  |

Punch List Status at Turnover

| Punch List Reference: | Enter punch list document reference |
| --- | --- |
| Category A Items — Total: | Enter number |
| Category A Items — Open: | Enter number (must be zero for turnover) |
| Category B Items — Total: | Enter number |
| Category B Items — Open: | Enter number |
| Category C Items — Total: | Enter number |

Declaration

We hereby certify that the above system has been inspected and all construction, installation, and pre-commissioning activities within the defined system boundary are sufficiently complete for the system to be safely transferred from the construction team to the commissioning team. All Category A punch list items have been closed. Residual Category B and C items have been documented and do not prevent safe commissioning.

Turnover Details

| Turnover From (Construction): | Enter construction manager name and company |
| --- | --- |
| Turnover To (Commissioning): | Enter commissioning manager name and company |
| Effective Date of Turnover: | DD / MM / YYYY |
| Care, Custody, and Control: | Transfers to commissioning team from the effective date above |

Sign-Off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Construction Manager |  |  | DD / MM / YYYY |
| QA / QC Manager |  |  | DD / MM / YYYY |
| Commissioning Manager |  |  | DD / MM / YYYY |
| Project Manager |  |  | DD / MM / YYYY |
| Client / Employer Representative |  |  | DD / MM / YYYY |
| Health and Safety Manager |  |  | DD / MM / YYYY |

Distribution List

| No. | Recipient Name / Role | Organisation |
| --- | --- | --- |
| 1 |  |  |
| 2 |  |  |
| 3 |  |  |
| 4 |  |  |
| 5 |  |  |
| 6 |  |  |

Document Control

| Revision | Date | Description of Change | Author | Approved By |
| --- | --- | --- | --- | --- |
| A |  | Initial issue |  |  |