## Cover
EBRORA
ebrora.com
Permit Close-Out
Register
Track permits, conditions, and close-out evidence
to demonstrate regulatory compliance at handover.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Permit Register' sheet. Each row tracks one permit or consent and its associated conditions.
2. | Enter the Permit Ref, Type, Issuing Authority, and Date Issued. Select the Permit Type from the dropdown.
3. | Summarise the conditions in the Conditions Summary column. Enter the total Condition Count and how many are Conditions Closed.
4. | Close-Out % auto-calculates. The Status column tracks the overall permit status (Active / Conditions Met / Expired / Surrendered).
5. | Use optional columns (click [+]) for evidence references, linked drawings, review dates, and days to expiry.
6. | Days to Expiry auto-calculates from the Expiry Date and highlights red when <30 days or expired.
Colour Key
Light teal cells = User input / editable
Dark navy headers = Do not edit
Green = Conditions Met or 100% close-out
Amber = Active with partial close-out
Red = Expired, or close-out <50%, or <30 days to expiry
Tips
Tip 1: | Review this register monthly with the project team. Permit conditions are contractual obligations — missing one can halt the works.
Tip 2: | Link evidence (photos, test certs, inspection records) to each condition so close-out is auditable.
Tip 3: | Set calendar reminders for permits approaching expiry — renewal applications typically need 3+ months lead time.

## Permit Register
Permit Ref | Permit Type | Issuing Authority | Date Issued | Expiry Date | Conditions Summary | Condition Count | Conditions Closed | Close-Out % | Responsible Person | Status | Notes | Evidence Ref | Linked Drawing | Review Date | Days to Expiry | Renewal Required
PCR-001 | Planning Permission | Local Planning Authority | 2023-06-01 | 2028-05-31 | Pre-commencement conditions including CEMP, archaeology, ecology, access, drainage | 12 | 10 | 83.33% | J. Davies | Active | 2 conditions outstanding: ecology survey and drainage cert | CEMP-001, ECO-003 | DWG-PLN-001 | 2026-06-01 | 799 | No
PCR-002 | EA Discharge Consent | Environment Agency | 2024-01-15 | 2029-01-14 | Consent conditions: final effluent BOD<20, SS<30, NH3<5, P<1. Monitoring & reporting. | 8 | 8 | 100% | S. Patel | Conditions Met | All parameters demonstrated within limits during process proving | PP-001 to PP-015 | P&ID-1001-Rev.C | 2026-07-01 | 1027 | No
PCR-003 | Highways S278 | Highways Authority | 2024-03-01 | 2026-09-30 | Road reinstatement, signage, drainage, as-built survey, 12-month maintenance period | 6 | 3 | 50% | M. Thompson | Active | Maintenance period ongoing — 3 conditions outstanding | ROAD-001, SIGN-003 | DWG-HWY-001 | 2026-06-01 | 190 | Yes
PCR-004 | S61 Noise | Environmental Health | 2024-06-01 | 2026-06-30 | Working hours restriction, noise monitoring, complaints procedure, dust suppression | 5 | 5 | 100% | A. Khan | Conditions Met | All conditions met. Zero noise complaints recorded. | NOISE-LOG-001 |  |  | 98 | No
PCR-005 | EA Abstraction Licence | Environment Agency | 2024-09-01 | 2026-04-30 | Abstraction volume limits, meter readings, reporting schedule | 4 | 2 | 50% | R. Evans | Active | Approaching expiry — renewal application submitted | ABS-LOG-001 |  |  | 37 | Yes
SUMMARY | Total Permits: | 5 | Conditions Met: | 2 | Active: | 3 | Expired: | 0
Formulas:
Days to Expiry = IF([Expiry Date]="","",[Expiry Date]-TODAY())

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.