## Cover
EBRORA
ebrora.com
Permit to Work Register
Track, manage, and close out all permits to work on site — hot works, confined spaces, excavations, working at height, and more.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Navigate to the 'Permit to Work Register' sheet to begin logging permits.
2. | Each row represents one permit to work. Add a new row for every permit issued on site.
3. | Select the permit type from the dropdown — Hot Works, Confined Space, Excavation, Working at Height, Electrical, Demolition, LOLER/Lifting, or Other.
4. | Enter a clear description of works, the exact location on site, and the name of the person requesting the permit.
5. | Record the issuing authority (competent person), the date issued, and the validity period (Valid From / Valid To).
6. | The 'Duration (Days)' and 'Days Until Expiry' columns calculate automatically — do not edit these.
7. | Reference the associated risk assessment and method statement numbers so auditors can cross-check.
8. | When a permit is completed, update the status to 'Closed', enter the closure date and the name of the person closing it, and confirm the physical permit was returned.
9. | Use the summary dashboard at the top of the data sheet to monitor active, closed, expired, and total permits at a glance.
Colour Key
Light teal cells (#E8F6F7) — Editable input cells. Enter your data here.
Dark navy header row — Column headings. Do not edit.
Green fill — Permit status is 'Closed' (safely completed).
Amber fill — Permit status is 'Active' or 'Suspended', or expiry is approaching (3 days or fewer).
Red fill — Permit status is 'Expired' or 'Cancelled', or expiry has passed.
Tips
Never allow works to proceed without a valid, in-date permit. Use the 'Days Until Expiry' column to catch permits about to lapse.
Ensure the physical permit document is returned and signed off before marking as 'Closed' — the 'Permit Returned' column tracks this.
Review this register at every morning briefing to confirm which permits are active and which need renewing or closing out.

## Permit to Work Register
PERMIT TO WORK REGISTER |  |  | Total Permits: | 5 |  | Active: | 2 |  | Closed: | 2 |  | Expired/Cancelled: | 1 |  | % Closed: | 40%
Permit No. | Permit Type | Description of Works | Location on Site | Requested By | Issuing Authority | Date Issued | Valid From | Valid To | Duration (Days) | Permit Status | Risk Assessment Ref | Method Statement Ref | Specific Controls / Conditions | Date Closed | Closed By | Permit Returned | Days Until Expiry | Notes / Comments
PTW-001 | Hot Works | Cutting and welding of steel beams at roof level — Block A steelwork connections | Block A — Roof Level, Gridline 4-6 | Mike Brennan | David Clarke (Site Manager) | 2026-03-10 | 2026-03-10 | 2026-03-11 | 1 | Active | RA-2026-041 | MS-2026-019 | Fire watch maintained for 60 min after works cease. Extinguisher within 2m at all times. Hot work screen erected. |  |  | No | -10
PTW-002 | Confined Space | Entry into attenuation tank for internal inspection and silt removal | External Works — Attenuation Tank AT-01 | Chris Woodward | David Clarke (Site Manager) | 2026-03-07 | 2026-03-07 | 2026-03-08 | 1 | Closed | RA-2026-038 | MS-2026-017 | Continuous gas monitoring. Tripod and winch at entry. Two-person standby team. Radio comms. | 2026-03-08 | David Clarke | Yes |  | Tank cleared. No defects found.
PTW-003 | Excavation | Trench excavation for foul drainage run from MH4 to MH7 — 2.1m depth | Phase 2 Drainage — South Elevation | Sarah Ahmed | James Thornton (Senior Engineer) | 2026-03-05 | 2026-03-05 | 2026-03-12 | 7 | Active | RA-2026-035 | MS-2026-015 | Trench support installed before entry. Banksman for plant operations. Exclusion zone 2m from edge. CAT & Genny sweep completed. |  |  | No | -9 | Utility survey confirmed no live services in trench alignment.
PTW-004 | Working at Height | Scaffold erection and cladding installation — Block C east elevation | Block C — East Elevation, All Levels | Tom Fletcher | David Clarke (Site Manager) | 2026-03-03 | 2026-03-03 | 2026-03-09 | 6 | Expired | RA-2026-030 | MS-2026-012 | Full scaffold inspection by CISRS cardholder before each shift. Harness required above 4m. Debris netting on all elevations. |  |  | No |  | Permit expired — renewal required before works resume.
PTW-005 | Electrical | Isolation and testing of LV distribution board DB-03 for circuit modifications | Block B — Electrical Riser, Level 1 | Ryan Gallagher | Neil Parsons (Authorised Person) | 2026-03-08 | 2026-03-08 | 2026-03-08 | 0 | Closed | RA-2026-039 | MS-2026-018 | Lock-off and prove dead procedure. Personal padlock on isolator. Permit holder and AP only. Test equipment calibrated. | 2026-03-08 | Neil Parsons | Yes |  | Isolation confirmed dead. Circuit modifications completed and tested.
Formulas:
Days Until Expiry = IF(AND([Valid To]<>"",[Permit Status]="Active"),[Valid To]-TODAY(),"")

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.