## Cover
EBRORA
ebrora.com
RAMS Register
Track every Risk Assessment & Method Statement from submission through review, acceptance and expiry — keep your site compliant and your audit trail clean.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — RAMS Register
Step-by-Step Instructions
1. | Go to the 'RAMS Register' sheet. Enter the Project Name and Contract Number in the info strip at the top.
2. | Each RAMS is automatically given a sequential reference (RAMS-001, RAMS-002, etc.) once a Title is entered in column C.
3. | Enter the Subcontractor or Author name in column B and the RAMS title/description in column C.
4. | Use the Activity Type dropdown (column D) to categorise the work — e.g. Excavation, Lifting, Confined Space, Hot Works.
5. | Enter the date the RAMS was Submitted in column E. This starts the review clock.
6. | Use the Status dropdown (column F) to track progress: Submitted, Under Review, Accepted, Rejected, Expired, or Superseded.
7. | Enter the Review Date (column G) when you complete the formal review, and the Accepted Date (column H) once formally approved.
8. | Column I calculates the number of days since the RAMS was submitted. Monitor this — target review within 5 working days.
9. | Set the Expiry Date in column J. Most RAMS expire after 12 months, or sooner if the scope or risk profile changes.
10. | Column K flags whether the RAMS is Overdue for review or nearing expiry. Use Optional Columns L–O for revision tracking and file references.
Colour Key
Accepted — RAMS formally reviewed and approved. Safe to proceed with this activity.
Under Review — RAMS submitted and being assessed. Do not start work until accepted.
Rejected or Expired — RAMS not approved or validity has lapsed. Activity must not proceed.
Superseded — Replaced by a later revision. Retained for audit trail only.
Expiring Soon — Expiry date is within the next 30 days. Renewal action required.
Light teal cells — User input / editable fields.
Dark navy header rows — Do not edit.
Tips
* | Never accept a RAMS verbally. The register entry and signature on the document itself are the only valid records. Under CDM 2015, the Principal Contractor must ensure RAMS are suitable and sufficient before work starts.
* | If a RAMS is rejected, record the reason in the Notes column and agree a resubmission date. Set a calendar reminder — it is easy for rejected RAMS to get lost and work to start without a valid document.
* | Review the Expiry column every Monday morning. A RAMS that expires mid-activity needs renewing before the expiry date, not after. Factor in review time — you need at least 5 working days for a proper technical review.

## RAMS Register
Project Name: |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No] |  |  | ▸ Optional Fields — Click [+] to expand
Ref | Subcontractor / Author | RAMS Title / Activity Description | Activity Type | Date Submitted | Status | Review Date | Accepted Date | Days Since Submission | Expiry Date | Notes | Revision | Supersedes | Previous Ref | File Path / Link
RAMS-001 | Groundworks Ltd | Excavation & Earthworks — Zone 3 Inlet Main Trench | Excavation | 2025-01-10 | Accepted | 2025-01-14 | 2025-01-16 |  | 2026-01-16 | Rev 2 — updated for trench depths >3m. CDM F10 ref. | Rev 2 | RAMS-001 Rev 1
RAMS-002 | Walsh MEP Ltd | Confined Space Entry — Inlet Chamber Inspection & Cleaning | Confined Space | 2025-02-03 | Accepted | 2025-02-07 | 2025-02-10 |  | 2025-08-10 | Rescue team briefed. Rescue pack at site entrance. | Rev 1
RAMS-003 | Roberts Electrical | HV Cable Jointing — 11kV Feeder to MCC-01 | Electrical | 2025-02-20 | Under Review |  |  | 397 |  | AP review required before acceptance. Awaiting HV specialist sign-off. | Rev 1
RAMS-004 | Hargreaves Plant Ltd | Crane Lifts — Pump Station Roof Slab Installation | Lifting | 2025-03-01 | Submitted |  |  | 388 |  | Lift plan and 3rd party crane certificate to accompany RAMS. | Rev 1
RAMS-005 | Groundworks Ltd | Demolition of Existing Inlet Screen Chamber | Demolition | 2024-10-05 | Expired | 2024-10-09 | 2024-10-12 |  | 2025-04-12 | Works complete — RAMS retained for record. Expiry passed. | Rev 1
TOTAL | 5 | ACCEPTED | 2 | UNDER REVIEW | 1 | SUBMITTED | 1 | REJECTED | 0 | EXPIRED | 1 | EXPIRING ≤30 DAYS | 0
Formulas:
Days Since Submission = IF(AND([Date Submitted]<>"",[Status]<>"Accepted",[Status]<>"Expired",[Status]<>"Superseded"),TODAY()-[Date Submitted],"")
Previous Ref = COUNTIFS(F3:[Status, row above],"Accepted",J3:[Expiry Date, row above],">="&TODAY(),J3:[Expiry Date, row above],"<="&(TODAY()+30))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.