## Cover
EBRORA
ebrora.com
Risk Register
Identify and manage project risks with likelihood × impact scoring, automatic risk ratings, mitigation actions, and residual risk tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Risk Register' sheet. The summary shows total risks and RAG breakdown (High/Medium/Low).
2. Enter each risk with its reference, date identified, category, and a clear description of the risk event.
3. Score the Likelihood (1–5) and Impact (1–5). The Risk Score auto-calculates (L × I) and RAG assigns automatically.
4. Record the mitigation action, owner, and due date. Then score the residual risk after mitigation.
5. Risk Rating: 1–6 = LOW (green), 8–12 = MEDIUM (amber), 15–25 = HIGH (red).
6. The Residual Score shows whether mitigations are bringing risk down to acceptable levels.
7. Review the register monthly — update scores, close risks that have passed, and add new ones.
8. Filter by RAG or category to focus your risk review on the most critical areas.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Low risk / Complete
| Amber | Medium risk / In progress
| Red | High risk / Critical
Tips
• Describe risks as events: 'There is a risk THAT [event] CAUSED BY [cause] RESULTING IN [consequence]'.
• Every High-rated risk must have an active mitigation with an owner and due date — unmitigated red risks are unacceptable.
• Review residual scores after mitigations are complete — if the risk hasn't reduced, the mitigation hasn't worked.

## Risk Register
RISK REGISTER
Total Risks |  | High (Red) |  | Medium (Amber) |  | Low (Green) |  | Open |  | Closed
5 |  | 2 |  | 3 |  | 31 |  | 3 |  | 1
IDENTIFICATION |  |  |  | PRE-MITIGATION SCORE |  |  |  | MITIGATION |  |  | RESIDUAL SCORE |  |  |  | STATUS
Risk Ref | Date Identified | Category | Risk Description | Likelihood (1–5) | Impact (1–5) | Risk Score | RAG | Mitigation Action | Owner | Due Date | Residual Likelihood | Residual Impact | Residual Score | Residual RAG | Status | Notes / Review Comments
R-001 | 2026-01-15 | Programme | Delay to steelwork delivery due to supplier capacity constraints | 4 | 4 | 16 | HIGH | Early order placement and regular progress chasing with fabricator | M. Evans | 2026-02-01 | 2 | 4 | 8 | MEDIUM | Open | Order placed 20/01. Weekly calls scheduled.
R-002 | 2026-01-15 | H&S | Collapse of excavation faces in deep trenches due to poor ground conditions | 3 | 5 | 15 | HIGH | Install trench support (drag boxes) for all excavations >1.2m | Site Foreman | 2026-01-20 | 1 | 5 | 5 | LOW | Open | Drag boxes on site and in use.
R-003 | 2026-01-20 | Commercial | Client variations exceeding contingency budget leading to cost overrun | 3 | 4 | 12 | MEDIUM | Monthly cost reviews. Early warning notices under NEC contract. | QS | 2026-02-28 | 2 | 3 | 6 | LOW | Open | First review completed Feb.
R-004 | 2026-01-25 | Environmental | Contaminated land discovered during excavation requiring specialist disposal | 2 | 5 | 10 | MEDIUM | GI report reviewed. Contingency budget for contamination held. Watching brief on excavations. | Environmental Advisor | 2026-02-15 | 2 | 4 | 8 | MEDIUM | Watching | No contamination found to date.
R-005 | 2026-02-01 | Design | Late design information for M&E services causing clash with structural frame | 4 | 3 | 12 | MEDIUM | BIM clash detection weekly. Design freeze deadline agreed with consultant. | Design Manager | 2026-02-20 | 2 | 2 | 4 | LOW | Closed | Design freeze achieved 18/02. No clashes.
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW
[6 empty] | 0 | LOW | [5 empty] | 0 | LOW

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.