## Cover
EBRORA
ebrora.com
RACI Matrix
Define project responsibilities with a Responsible, Accountable, Consulted, Informed matrix across tasks and team members.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'RACI Matrix' sheet. Tasks/activities are listed as rows; team roles are column headers.
2. Enter task names in column A. Enter team member names/roles across row 4 (columns B onwards).
3. For each task × person intersection, enter R (Responsible), A (Accountable), C (Consulted), or I (Informed).
4. R = does the work. A = ultimately answerable (only ONE per task). C = provides input. I = kept updated.
5. The template auto-checks that every task has exactly one A. Tasks with 0 or 2+ A's highlight red.
6. Summary counts at the bottom show how many R, A, C, I assignments each person has.
7. Use this at project kickoff to align the team on who does what — prevents confusion and duplication.
8. Print as A4 landscape — it's a reference document that should be pinned up in the site office.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Positive / Complete
| Amber | In progress / Medium
| Red | Negative / Critical
Tips
• Every task MUST have exactly one A (Accountable) — multiple A's means nobody is truly accountable.
• R without A is fine (doer with no explicit sign-off), but A without R means someone is accountable for work nobody is doing.
• Review the RACI when team members change — update it, don't just leave gaps.

## RACI Matrix
RACI MATRIX
R = Responsible (does the work) ¦ A = Accountable (one per task, ultimate owner) ¦ C = Consulted (input needed) ¦ I = Informed (kept updated)
Task / Activity | Project Manager | Site Manager | Design Manager | QS / Commercial | H&S Advisor | Setting Out Eng. | M&E Coordinator | Client PM | A Count Check
Programme management & reporting | A | R | C | C | I | I | I | C | 1
Site management & coordination | C | A | I | I | C | R | C | I | 1
Design management & review | C | I | A | I | I | I | C | C | 1
Cost management & valuations | C | I | I | A | I | I | I | C | 1
Health & safety management | C | C | I | I | A | I | I | I | 1
Setting out & survey control | I | C | C | I | I | A | I | I | 1
M&E coordination & commissioning | I | C | C | I | I | I | A | C | 1
Client liaison & approvals | R | C | C | C | I | I | I | A | 1
Quality management & ITP | C | R | C | I | C | I | C | I | 0
Procurement & subcontract management | C | I | C | A | I | I | I | C | 1
Environmental management | C | C | I | I | A | I | I | I | 1
Risk management | A | C | C | C | C | I | I | C | 1
Document control | C | R | C | I | I | I | I | I | 0
Temporary works design | C | R | A | I | C | I | I | I | 1
Logistics & deliveries | I | A | I | I | I | I | I | I | 1
TOTALS: | R:1 A:2 C:9 I:3 | R:4 A:2 C:6 I:3 | R:0 A:2 C:8 I:5 | R:0 A:2 C:3 I:10 | R:0 A:2 C:4 I:9 | R:1 A:1 C:0 I:13 | R:0 A:1 C:3 I:11 | R:0 A:1 C:6 I:8

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.