## Cover
EBRORA
ebrora.com
Stakeholder Contact List
Centralised stakeholder directory with contact details, organisation, role, influence/interest mapping, and communication preferences.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Contacts' sheet. List all project stakeholders with their contact details.
2. Enter the name, organisation, role, and contact details (phone, email) for each stakeholder.
3. Categorise each stakeholder (Client, Consultant, Subcontractor, Statutory, Community, etc.).
4. Rate their Influence (1–5) and Interest (1–5) to understand engagement priority.
5. Engagement Level auto-calculates: Manage Closely (high both), Keep Satisfied, Keep Informed, or Monitor.
6. Record the preferred communication method and frequency for each stakeholder.
7. Expand optional columns [+] for address, emergency contact, and notes.
8. Keep this list updated — it's the single source of truth for who to contact about what.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Monitor — low engagement needed
| Amber | Keep Informed / Keep Satisfied
| Red | Manage Closely — high influence & interest
Tips
• Influence = their power to affect the project. Interest = how much they care about the outcome.
• 'Manage Closely' stakeholders should hear from you weekly. 'Monitor' stakeholders need updates monthly at most.
• Include statutory bodies (EA, HSE, local authority) — you'll need their details when something goes wrong.

## Contacts
STAKEHOLDER CONTACT LIST
Total Contacts |  | Manage Closely |  | Keep Satisfied |  | Keep Informed |  | Monitor
6 |  | 2 |  | 2 |  | 2 |  | 0
▸ Optional Fields — Click [+] to expand
Name | Organisation | Role / Title | Category | Email | Phone | Influence (1–5) | Interest (1–5) | Engagement Level | Comms Method | Notes | Address | Emergency Contact | Additional Notes
J. Stevens | Client Co | Project Manager | Client | j.stevens@clientco.com | 07700 900001 | 5 | 5 | Manage Closely | Meeting | Key decision maker — weekly meetings | 123 High Street, London EC1 |  | Chair of progress meetings
S. Okonkwo | Design Consultants | Lead Structural Engineer | Consultant | s.okonkwo@designco.com | 07700 900002 | 4 | 4 | Manage Closely | Email | Design authority for structural elements
D. Murphy | Murphy Groundworks | Contracts Manager | Subcontractor | d.murphy@murphygw.com | 07700 900003 | 3 | 4 | Keep Informed | Phone | Groundworks subcontractor — main package |  | 07700 900099
P. Wilson | Environment Agency | Area Officer | Statutory Body | p.wilson@environment-agency.gov.uk | 03708 506506 | 5 | 2 | Keep Satisfied | Letter | Discharge consent holder — formal comms only
Mrs A. Brown | Local Resident | Neighbour | Community |  | 07700 900005 | 2 | 5 | Keep Informed | Letter | Adjacent property — noise concerns raised | 14 Oak Lane, Anytown |  | Very engaged — responds to all consultations
T. Kowalski | HSE | Inspector | Statutory Body |  | 0300 003 1647 | 5 | 3 | Keep Satisfied | Phone | Construction division

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.