## Cover
EBRORA
ebrora.com
Action Tracker
Track project actions with priority, ownership, due dates, and automatic overdue monitoring to ensure nothing falls through the cracks.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Action Tracker' sheet. The dashboard panel shows open, overdue, and closed action counts.
2. Log each action with its reference, date raised, source (meeting, site walk, audit, etc.), and description.
3. Assign a priority (Critical, High, Medium, Low), an owner, and a due date for every action.
4. Days Open and Status auto-calculate. OVERDUE flags when the due date has passed and the action is still open.
5. When an action is completed, enter the date closed. Status changes to CLOSED automatically.
6. The priority breakdown in the summary shows how many Critical/High items remain open.
7. Expand optional columns [+] for category, related document ref, and verification details.
8. Review this tracker weekly in your project team meeting — it's the backbone of project governance.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | CLOSED — action complete
| Amber | OPEN — in progress, not yet due
| Red | OVERDUE — past due date
Tips
• Every action needs one owner — shared ownership means nobody owns it.
• Set realistic due dates. An action due 'ASAP' is an action that never gets done — give it a date.
• Close actions formally with evidence — don't just change the status, record what was done and when.

## Action Tracker
ACTION TRACKER
Total Actions |  | Open |  | Overdue |  | Closed |  | Closure Rate
5 |  | 0 |  | 3 |  | 2 |  | 40%
Priority: Critical 0 ¦ High 2 ¦ Medium 1 ¦ Low 0
▸ Optional Fields — Click [+] to expand
Action Ref | Date Raised | Source | Action Description | Priority | Owner | Due Date | Date Closed | Days Open | Status | Notes / Evidence of Closure | Category | Related Doc Ref | Verified By
ACT-001 | 2026-02-10 | Progress Meeting | Chase RFI-031 response from structural engineer regarding pile cap reinforcement detail | High | R. Khan | 2026-02-25 |  | 41 | OVERDUE | Chased 15/02 and 20/02 — response promised by 25/02 | Design | RFI-031
ACT-002 | 2026-02-10 | Site Walk | Repair damaged edge protection on excavation zone B — south side | Critical | M. Evans | 2026-02-11 | 2026-02-11 | 1 | CLOSED | Repaired same day. Photo evidence filed. | H&S |  | J. Stevens
ACT-003 | 2026-02-12 | Client Instruction | Submit revised programme showing recovery from drainage delay | High | M. Evans | 2026-02-19 | 2026-02-18 | 6 | CLOSED | Rev P05 issued to client 18/02 | Programme
ACT-004 | 2026-02-14 | Audit | Update COSHH register with new intumescent paint product data sheet | Medium | H&S Advisor | 2026-02-28 |  | 37 | OVERDUE | Data sheet received — register update in progress | H&S | COSHH-REG
ACT-005 | 2026-02-18 | Progress Meeting | Coordinate crane access and concrete delivery schedules to avoid clashes | High | M. Evans | 2026-02-25 |  | 33 | OVERDUE | Logistics meeting scheduled 24/02 | Logistics
Formulas:
Closure Rate = IF([Date Raised]="","",IF([Date Closed]<>"",[Date Closed]-[Date Raised],TODAY()-[Date Raised]))
Status = IF([Total Actions]="","",IF([Date Closed]<>"","CLOSED",IF(AND([Closed]<>"",[Closed]<TODAY()),"OVERDUE","OPEN")))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.