## Cover
EBRORA
ebrora.com
Decision Log
Record and track project decisions with context, alternatives considered, rationale, and approval status for full audit traceability.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Decision Log' sheet. Log every significant project decision as it's made.
2. Enter the decision reference, date, a clear description of the decision made, and why it was made.
3. Record what alternatives were considered — this is critical for audit trail and dispute avoidance.
4. Assign a decision maker and record who was consulted before the decision was taken.
5. Track the impact: what does this decision affect (cost, programme, design, scope)?
6. Status options: Pending, Approved, Reversed, Superseded. Most decisions should move to Approved quickly.
7. Expand optional columns [+] for related RFI/TQ, financial impact, and review date.
8. Reference this log in meeting minutes — 'As per Decision D-023, the approach agreed is...'.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Green | Positive / Complete
| Amber | In progress / Medium
| Red | Negative / Critical
Tips
• Record decisions at the time they're made — reconstructing the rationale months later is unreliable.
• Include the 'alternatives considered' even if obvious — it proves due diligence if challenged.
• Every decision with a cost or programme impact should be formally recorded here, not just in an email.

## Decision Log
DECISION LOG
Total Decisions |  | Approved |  | Pending |  | Reversed
3 |  | 3 |  | 0 |  | 0
▸ Optional Fields — Click [+] to expand
Decision Ref | Date | Decision Made | Alternatives Considered | Rationale | Decision Maker | Consulted | Impact Area | Status | Notes | Related RFI/TQ | Financial Impact (£) | Review Date
D-001 | 2026-01-20 | Proceed with CFA piling instead of driven precast piles for main building foundations. | 1) Driven precast (original design). 2) Steel H-piles. 3) CFA bored piles. | CFA selected due to noise restrictions from adjacent school. Vibration from driven piles would exceed planning condition limits. | S. Okonkwo | J. Stevens, M. Evans | Cost | Approved | £45k additional cost accepted by client. Programme neutral. | RFI-012 | 45000
D-002 | 2026-02-05 | Accept 3-day programme delay to drainage rather than implement weekend working. | 1) Weekend working (additional £12k). 2) Accept delay and recover elsewhere. 3) Additional gang (not available). | Recovery possible through parallel working on steelwork. Weekend working cost not justified for 3 days. | M. Evans | J. Stevens | Programme | Approved |  |  | 0
D-003 | 2026-02-18 | Change cladding supplier from Alpha Panels to Beta Systems due to Alpha's financial difficulties. | 1) Continue with Alpha (risk of insolvency). 2) Switch to Beta (4-week re-procurement). 3) Defer cladding decision. | Alpha Panels issued profit warning. Risk of mid-project failure too high. Beta Systems pre-qualified and competitively priced. | J. Stevens | QS, Design Manager | Procurement | Approved | 4-week delay to cladding start. Mitigated by bringing forward internal works. |  | 8500

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.