## Cover
EBRORA
ebrora.com
Dry & Wet Commissioning Schedule
Plan and track dry and wet commissioning activities by system — baseline dates, actual dates, responsible engineer and completion status week by week.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — Dry & Wet Commissioning Schedule
Step-by-Step Instructions
1. | Go to the 'Commissioning Schedule' sheet. Enter the Project Name, Contract Number and commissioning start date in the info strip.
2. | Each row represents a commissioning activity. Enter a unique Activity ID in column A and a clear description in column B.
3. | Select the System in column C — this groups activities by process system for filtering.
4. | Select the Phase in column D: Dry Commissioning (mechanical/electrical checks with no process fluid) or Wet Commissioning (process fluid introduced).
5. | Enter the Responsible Engineer in column E — the person accountable for completing and signing off this activity.
6. | Enter the Planned Start Date in column F and the Planned Finish Date in column G. These define the baseline schedule.
7. | Update columns H and I with Actual Start and Actual Finish dates as work progresses.
8. | Use the Status dropdown in column J. The row colour updates automatically: green for Complete, amber for In Progress, red for Delayed.
9. | In the weekly columns (K onwards), mark 'P' for weeks the activity is planned to be active, and 'A' once complete in that week. These provide a visual Gantt-style timeline.
10. | The summary row at the bottom counts activities by phase and status. Review weekly with the commissioning team.
Colour Key
Complete — Activity signed off. Commissioning record filed.
In Progress — Activity underway. Actual start date recorded.
Delayed — Activity behind planned schedule. Action plan required.
Not Started — Activity not yet commenced. No overdue flag.
P marker — Activity planned active in this week.
A marker — Activity actually completed / active in this week.
Light teal input cells — User input / editable fields.
Tips
* | Dry commissioning must be completed and signed off before any process fluid (raw sewage, sludge, chemicals) is introduced. A wet run started before dry commissioning is complete creates safety and liability risks.
* | For each wet commissioning activity, confirm the LOTO isolation register is current and all personnel have been briefed on the process fluid hazards before starting. Record the briefing in the Notes column.
* | Update the actual dates daily during commissioning — not weekly. A two-week-old 'In Progress' status tells you nothing about where you actually are. Daily updates catch delays early enough to act on them.

## Commissioning Schedule
Project Name: |  |  | [Enter Project Name] |  |  |  | Contract No: |  | [Contract No]
Activity Details & Dates | [9 empty] | Weekly Progress ¦ P = Planned Active A = Actual Complete
Activity ID | Activity Description | System | Phase | Responsible Engineer | Planned Start | Planned Finish | Actual Start | Actual Finish | Status | Apr 2025 |  |  |  | May 2025 |  |  |  | Jun 2025 |  |  |  |  | Jul 2025 |  |  | Notes
[10 empty] | w/c 07/04 | w/c 14/04 | w/c 21/04 | w/c 28/04 | w/c 05/05 | w/c 12/05 | w/c 19/05 | w/c 26/05 | w/c 02/06 | w/c 09/06 | w/c 16/06 | w/c 23/06 | w/c 30/06 | w/c 07/07 | w/c 14/07 | w/c 21/07
COM-001 | MCC-01 Internal Inspection & Pre-Energisation Check | MCC & Electrical | Dry Commissioning | C. Roberts | 2025-04-07 | 2025-04-11 | 2025-04-07 | 2025-04-11 | Complete | A | A | [14 empty] | EICR completed. All checks signed off 11/04.
COM-002 | MCC-01 Energisation & LV Distribution Check | MCC & Electrical | Dry Commissioning | C. Roberts | 2025-04-14 | 2025-04-18 | 2025-04-14 | 2025-04-18 | Complete |  | A | A | [13 empty] | Energisation permit EP-2025-001. G. Thompson AP.
COM-003 | Field Instrument Loop Testing — Inlet Works | SCADA & Instrumentation | Dry Commissioning | A. Nkosi | 2025-04-14 | 2025-04-25 | 2025-04-14 |  | In Progress |  | P | P | P | [12 empty] | Loop test sheets ICS-LT-001 to ICS-LT-012. 8 of 12 complete.
COM-004 | Pump PST-01 Mechanical Run & Bearing Check | Inlet Works | Dry Commissioning | T. Walsh | 2025-04-28 | 2025-05-02 |  |  | Not Started |  |  |  | P | P | [11 empty] | Requires COM-001 and COM-002 complete before start.
COM-005 | C&E Testing — Inlet Works Interlocks & Trips | SCADA & Instrumentation | Dry Commissioning | A. Nkosi | 2025-05-05 | 2025-05-16 |  |  | Not Started |  |  |  |  | P | P | P | [9 empty] | C&E matrix Template 19. All loops must pass before C&E test.
COM-006 | Inlet Works — Wet Commissioning Run (Water) | Inlet Works | Wet Commissioning | T. Walsh | 2025-05-19 | 2025-05-30 |  |  | Not Started | [6 empty] | P | P | P | [7 empty] | Requires all dry commissioning signed off. ER to witness.
COM-007 | Aeration Blower 01 & 02 — Dry Run & Vibration Check | Aeration | Dry Commissioning | T. Walsh | 2025-05-05 | 2025-05-09 |  |  | Not Started |  |  |  |  | P | P | [10 empty] | FSL-401 loop test must be complete before blower run.
COM-008 | Process Proving — Aeration (DO targets) | Aeration | Wet Commissioning | T. Walsh | 2025-06-09 | 2025-06-20 |  |  | Not Started | [10 empty] | P | P | P |  |  |  | DO setpoint 2.0 mg/L. 72-hour continuous run required.
COM-009 | SCADA Full System SAT | SCADA & Instrumentation | Dry Commissioning | A. Nkosi | 2025-06-02 | 2025-06-06 |  |  | Not Started | [9 empty] | P | P | [5 empty] | SAT procedure ICS-SAT-001 must be approved before test.
COM-010 | Final Settlement — Wet Commissioning & Consent Sampling | Final Settlement | Wet Commissioning | T. Walsh | 2025-06-23 | 2025-07-11 |  |  | Not Started | [12 empty] | P | P | P | P | Effluent consent sampling starts week 13. EA notification required.
TOTAL | 10 | COMPLETE | 2 | IN PROGRESS | 1 | DELAYED | 0 | DRY COMM | 7

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.