## Cover
EBRORA
ebrora.com
FAT / SAT Attendance & Results Log
Log and track Factory Acceptance Tests and Site Acceptance Tests — recording attendance, test outcomes, observations, and the FAT→SAT progression for all MEICA equipment packages.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. Open the 'FAT SAT Log' sheet. Each row represents one acceptance test event — either a Factory Acceptance Test (FAT) or a Site Acceptance Test (SAT).
2. Enter the test reference, select the test type (FAT or SAT), and fill in the equipment tag, description, and manufacturer/supplier.
3. Record the test date and location (factory name for FATs, site area for SATs). List all attendees in the Attendees column.
4. After the test, select the Overall Result from the dropdown: Pass, Conditional Pass, Fail, or Deferred. Add the number of observations and open punch items.
5. The Progression Status auto-calculates for each equipment tag — it shows whether the item has completed FAT only, SAT only, both, or neither.
6. The Summary Dashboard at the top provides live counts: total FATs/SATs, pass rates, and a progression funnel showing how many items have moved from FAT through to SAT.
7. Expand the optional columns for detailed fields: test procedure reference, report reference, next action required, and re-test date.
8. Filter by test type (FAT/SAT), result, or equipment tag to generate focused reports for suppliers, commissioning teams, or client reviews.
Colour Key
Light teal cells = user input / editable fields
Dark navy headers = do not edit
Green = Pass (test fully accepted)
Amber = Conditional Pass (minor observations outstanding)
Red = Fail or Deferred (re-test required)
Tips
• Always attend FATs with a pre-prepared test plan and checklist — the log records outcomes, but the test plan defines what you're actually checking.
• Record observations during the test, not after — details fade quickly. Use the Remarks column for anything the formal report won't capture.
• A Conditional Pass should always have a clear list of conditions and a deadline. Don't leave conditions open-ended or they'll haunt you during commissioning.

## FAT SAT Log
FAT / SAT Attendance & Results Log — Summary Dashboard
Test Results Summary | [5 empty] | FAT → SAT Progression Funnel
Metric | FAT | SAT | Total | Rate |  | Stage | Count | % of Total | Visual
Total Tests | 4 | 2 | 6 |  |  | Unique Equipment Items | 4 |  | ███████████████
Pass | 2 | 1 | 3 | 50% |  | FAT Completed (Pass/Cond.) | 3 | 75% | ███████████
Conditional Pass | 1 | 1 | 2 | 33.33% |  | SAT Completed (Pass/Cond.) | 2 | 50% | ████████
Fail | 1 | 0 | 1 | 16.67% |  | Both FAT & SAT Passed | 1 | 25% | ████
Deferred | 0 | 0 | 0 |  |  | Awaiting SAT | 1 | 25% | ████
Total Open Observations: |  |  | 18 | Total Open Punch Items: |  |  | 7
Test Identification | [5 empty] | Attendance & Location |  |  | Results & Observations |  |  |  |  | ▸ Optional Fields — Click [+] to expand
Item No. | Test Ref | Type | Equipment Tag | Equipment Description | Manufacturer / Supplier | Test Date | Location | Attendees | Overall Result | Observations | Punch Items | Progression | Remarks / Key Findings | Test Procedure Ref | Report Reference | Next Action Required | Re-Test Date
1 | FAT-001 | FAT | MCC-01 | Main Motor Control Centre — Inlet Works | ABB Ltd | 2025-11-18 | ABB Factory, Stonehouse, Glos | M. Clarke (Client), R. Evans (Contractor), P. Hughes (ABB) | Pass | 2 | 0 | FAT+SAT Complete | All tests passed. 2 minor cosmetic observations noted. | TP-MCC-01 Rev A | FAT-RPT-001
2 | FAT-002 | FAT | PLC-CAB-01 | PLC Cabinet — SCADA Outstation 1 | Siemens UK | 2025-12-05 | Siemens Factory, Congleton, Cheshire | M. Clarke (Client), J. Patel (D&B), K. Schmidt (Siemens) | Conditional Pass | 5 | 2 | FAT+SAT Complete | I/O addressing errors found in 2 modules — Siemens to rectify before dispatch. | TP-PLC-01 Rev B | FAT-RPT-002 | Siemens to re-verify I/O and issue updated config
3 | FAT-003 | FAT | VSD-PMP-01 | VSD Panel — Raw Water Pumps 1–3 | Danfoss UK | 2026-01-14 | Danfoss Drives, Leeds | R. Evans (Contractor), T. Brown (Danfoss) | Pass | 0 | 0 | FAT Only — Awaiting SAT | Clean pass. All drives tested at full load. | TP-VSD-01 Rev A | FAT-RPT-003
4 | SAT-001 | SAT | MCC-01 | Main Motor Control Centre — Inlet Works | ABB Ltd | 2026-02-28 | Inlet Works MCC Room, Site | M. Clarke, R. Evans, J. Patel, Site Electrician | Pass | 0 | 0 | FAT+SAT Complete | All site connections verified. Motor rotations confirmed. | TP-MCC-01 Rev A | SAT-RPT-001
5 | FAT-004 | FAT | PNL-HVAC-01 | HVAC Control Panel — AHU Plant Room | Schneider Electric | 2026-02-10 | Schneider Partner, Birmingham | M. Clarke (Client), ACE Controls rep | Fail | 8 | 4 | Not Passed | BMS integration failed. Incorrect protocol — Schneider to rebuild comms module. | TP-HVAC-01 Rev A | FAT-RPT-004 | Re-FAT scheduled after firmware update | 2026-03-28
6 | SAT-002 | SAT | PLC-CAB-01 | PLC Cabinet — SCADA Outstation 1 | Siemens UK | 2026-03-12 | Control Room, Site | M. Clarke, J. Patel, K. Schmidt (remote) | Conditional Pass | 3 | 1 | FAT+SAT Complete | I/O issues from FAT resolved. 3 new observations on HMI screen layout. | TP-PLC-01 Rev B | SAT-RPT-002 | HMI screens to be updated in next software release
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.