## Cover
EBRORA
ebrora.com
Cable Pulling Schedule
Track and manage cable pulling activities across your project — from scheduling through to installation, testing, and sign-off.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the 'Cable Pulling Schedule' sheet. Each row represents one cable to be pulled.
2. | Enter your cable tag/ID in column A. Use your project's cable numbering convention (e.g., CB-001, PW-101).
3. | Fill in the 'From' and 'To' locations — these are the origin and destination of each cable (e.g., MCC-01 to Motor M-101).
4. | Select the cable type and size from the dropdown, or type a custom value if yours isn't listed.
5. | Enter the planned pull date. The schedule will automatically flag overdue cables in red.
6. | Update the 'Pull Status' dropdown as work progresses: Not Started → In Progress → Complete → On Hold.
7. | Once a cable is pulled, enter the actual pull date. The sheet calculates days variance automatically.
Optional Fields
8. | Click the [+] button above the grouped columns on the right to expand optional fields: Drum No., Route/Tray, Megger Result, and Sign-Off.
9. | Use these for more detailed tracking — particularly useful during commissioning and handover phases.
Summary Dashboard
10. | The summary block at the top of the data sheet shows total cables, completion %, and a status breakdown. These update automatically as you fill in data.
Colour Key
| Light Teal cells | Editable — enter your data here
| Dark Navy headers | Do not edit — column headings and structure
| Green | Cable pull complete
| Amber | Cable pull in progress or on hold
| Red | Overdue or not started past planned date
Tips
• | Sort by 'Planned Pull Date' to create a weekly look-ahead for the pulling crew.
• | Use the AutoFilter on the header row to filter by status, area, or cable type — great for progress meetings.
• | Print the schedule landscape on A4 for site use. The print area is pre-set to fit one page wide.

## Cable Pulling Schedule
CABLE PULLING SCHEDULE — PROJECT DASHBOARD
Total Cables: | -490 | Complete: | 2 | In Progress: | 1 | Not Started: | 1 | On Hold: | 1 | % Complete: | 0%
▸ Optional Fields — Click [+] to expand
Cable Tag | From Location | To Location | Cable Type / Size | Length (m) | Planned Pull Date | Actual Pull Date | Pull Status | Days Variance | Notes | Drum No. | Route / Tray Ref | Megger Result (MΩ) | Signed Off By
CB-001 | MCC-01 | Motor M-101 (Pump P1) | SWA 4c 10mm² | 85 | 2026-03-12 | 2026-03-14 | Complete | 2 | Pulled successfully, no issues | DR-2201 | Tray T-01/R-03 | 500+ | J. Williams
CB-002 | DB-03A | FCU-201 (AHU Plant Room) | SWA 3c 4mm² | 42 | 2026-03-17 | 2026-03-18 | Complete | 1 |  | DR-2202 | Tray T-02/R-01 | 250 | J. Williams
CB-003 | LV Panel LP-02 | DOL Starter DS-305 | SWA 4c 6mm² | 120 | 2026-03-19 |  | In Progress | 3 | Awaiting access to riser | DR-2203 | Ladder L-05
CB-004 | JB-12 | Instrument IS-401 (Level) | Inst Cable 2pr | 65 | 2026-03-24 |  | Not Started | -2 |  | DR-2204 | Tray T-03/R-02
CB-005 | MCC-02 | VSD-501 (Blower B1) | XLPE 1c 95mm² | 210 | 2026-03-15 |  | On Hold | 7 | On hold — cable on back-order | DR-2205 | Duct D-01
Formulas:
Days Variance = IF(AND([Planned Pull Date]<>"",[Actual Pull Date]<>""),[Actual Pull Date]-[Planned Pull Date],IF(AND([Planned Pull Date]<>"",[Pull Status]<>"Complete"),TODAY()-[Planned Pull Date],""))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.