## Cover
EBRORA
ebrora.com
Cable Termination & Glanding Register
Track cable glanding and termination at both ends — A-end and B-end — with independent status tracking, gland types, and sign-off.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Two-Panel Layout
1. | This register uses a two-panel design. The LEFT panel (columns A–E) identifies each cable. The RIGHT panel tracks termination status independently at the A-end and B-end.
2. | The A-end is typically the supply side (panel, MCC, DB). The B-end is the field device or equipment side.
Filling In the Register
3. | Enter the Cable Tag in column A — this should match your cable pulling schedule.
4. | Fill in From (A-end) and To (B-end) locations, cable type, and core count.
5. | For each end, select the Gland Type from the dropdown (CW, BW, E1W, etc.) and the Termination Status (Not Started, Glanded, Terminated, Tested).
6. | Enter the date each end was completed. The 'Both Ends Complete' column auto-calculates — it shows Yes only when both A-end and B-end are marked as Tested.
7. | The overall % Complete in the dashboard counts cables where both ends are fully tested.
Optional Fields
8. | Click [+] to expand optional columns: Ferrule/Lug Size, Torque Checked, IR Test Result, and Signed Off By.
Colour Key
| Light Teal cells | Editable — enter your data here
| Dark Navy headers | Do not edit — column headings
| Teal band | Panel sub-header (A-End / B-End sections)
| White cells | Formula cells — auto-calculated
| Green | Tested / Both ends complete
| Amber | Glanded or Terminated (partially done)
| Red | Not Started
Tips
• | Filter by 'Both Ends Complete = No' to generate a termination punch list for the pulling/termination crew.
• | Use this register alongside the Cable Pulling Schedule (Template 41) — a cable should appear here once it has been pulled.
• | For SWA cables, always record the gland type — CW and BW glands are not interchangeable and incorrect glanding is a common NCR issue.

## Termination Register
CABLE TERMINATION & GLANDING REGISTER — STATUS DASHBOARD
Total Cables: | -490 | A-End Complete: | 2 | B-End Complete: | 1 | Both Ends Done: | 1 | A-End %: | 0% | B-End %: | 0% | Overall %: | 0%
▸ Optional Fields — Click [+] to expand
CABLE IDENTITY |  |  |  |  | A-END (SUPPLY SIDE) |  |  |  | B-END (FIELD SIDE)
Cable Tag | From (A-End) | To (B-End) | Cable Type | Cores | A-End Gland | A-End Date | A-End Status | A-End By | B-End Gland | B-End Status | B-End Date | B-End By | Both Complete | Ferrule / Lug | Torque Checked | IR Test (MΩ) | Signed Off By
CB-001 | MCC-01 | Motor M-101 (Pump P1) | SWA 4c 10mm² | 4 | CW | 2026-03-10 | Tested | D. Brooks | CW | Tested | 2026-03-12 | D. Brooks | Yes | M10 Crimp | Yes | 500+ | J. Williams
CB-002 | DB-03A | FCU-201 (AHU Plant Room) | SWA 3c 4mm² | 3 | BW | 2026-03-14 | Tested | D. Brooks | BW | Terminated | 2026-03-17 | K. Singh | No | M6 Bootlace | No
CB-003 | LV Panel LP-02 | DOL Starter DS-305 | SWA 4c 6mm² | 4 | CW | 2026-03-17 | Glanded | K. Singh | E1W | Not Started |  |  | No |  | N/A
CB-004 | JB-12 | Instrument IS-401 (Level) | Inst 2pr | 4 | A2 | 2026-03-19 | Terminated | D. Brooks | A2 | Glanded | 2026-03-20 | K. Singh | No | Pin Terminal | N/A
CB-005 | MCC-02 | VSD-501 (Blower B1) | XLPE 1c 95mm² | 1 | E1W |  | Not Started |  | E1W | Not Started |  |  | No | 185mm² Lug | N/A

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.