## Cover
EBRORA
ebrora.com
MCC Energisation & Isolation Log
Track every MCC panel, distribution board and field isolator — energisation dates, permits, HV/LV status and current isolation state in one controlled register.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template — MCC Energisation & Isolation Log
Step-by-Step Instructions
1. | Go to the 'MCC Energisation Log' sheet. Enter the Project Name, Site Name and Contract Number in the info strip at the top.
2. | Each entry is automatically assigned a sequential reference (ENE-001, ENE-002, etc.) once a Panel/Equipment ID is entered in column C.
3. | Enter the Energisation Date in column B — the date the panel or circuit was first energised under a valid Energisation Permit.
4. | Record the Panel / Equipment ID in column C (e.g. MCC-01, DB-GF-01, LCP-03) and the Panel Description in column D.
5. | Select the Voltage Level in column E: LV 415V, LV 230V, 11kV, 33kV, or Other. HV entries should be treated with additional caution.
6. | Record the Energisation Permit Reference in column F — every energisation must have an associated permit issued by the Appointed Person.
7. | Enter the Appointed Person (AP) who issued the permit in column G.
8. | Use the Status dropdown in column H: Isolated (not yet energised), Energised — Commissioning, Energised — Live Service, or De-Energised. Row colour reflects the current live/safe state.
9. | Record the current Isolation Reference in column I if an isolation is in place (cross-reference the LOTO/Isolation Register, Template 04).
10. | Use column J for notes — e.g. ongoing commissioning works, HV earthing details, or restrictions. Expand Optional Columns K–N for the interlocking scheme, EICR reference, test cert and file path.
Colour Key
Energised — Live Service. Panel is live and in normal operation. Treat as LIVE at all times.
Energised — Commissioning. Panel is energised for commissioning purposes. Permit required for all work.
Isolated. Panel is safely isolated. Current isolation reference shown in column I.
De-Energised. Panel has been de-energised and is not currently in service.
Pending. Panel not yet energised. Pre-energisation checks incomplete.
Light teal cells — User input / editable fields.
Tips
* | Every energisation — no matter how small — requires a written Energisation Permit signed by the Appointed Person. A verbal instruction to energise is not safe and is not compliant with BS 7671 or the Electricity at Work Regulations 1989.
* | For HV systems (11kV and above), the energisation permit must be issued by a qualified HV Authorised Person (AP) with written authority from the Asset Owner. Record the AP's name and their authorisation reference.
* | Review this register at the start of every commissioning shift. Any panel showing 'Energised — Commissioning' has live conductors — ensure all personnel working nearby have been briefed and appropriate barriers are in place.

## MCC Energisation Log
Project / Site: |  | [Enter Project / Site Name] |  |  |  | Contract No: |  | [Contract No] |  | ▸ Optional Fields — Click [+] to expand
ENE Ref | Energisation Date | Panel / Equipment ID | Panel Description | Voltage Level | Energisation Permit Ref | Appointed Person (AP) | Status | Current Isolation Ref | Notes | Interlocking Scheme Ref | EICR Ref | Test Cert Ref | File Path / Link
ENE-001 | 2025-03-05 | MCC-01 | Motor Control Centre 01 — Inlet Works | LV 415V | EP-2025-001 | G. Thompson (AP HV) | Energised — Commissioning |  | HV earthing removed 05/03. EICR completed. Commissioning underway. | INT-MCC01-001 | EICR-MCC01-2025 | TC-MCC01-001
ENE-002 | 2025-03-05 | MCC-02 | Motor Control Centre 02 — Aeration Building | LV 415V | EP-2025-002 | G. Thompson (AP HV) | Energised — Commissioning |  | Energised with MCC-01. Commissioning team on site. | INT-MCC02-001 | EICR-MCC02-2025 | TC-MCC02-001
ENE-003 | 2025-03-12 | DB-MCC-01 | Distribution Board — MCC Room General Services | LV 230V | EP-2025-003 | C. Roberts (AP LV) | Energised — Live Service |  | General services live — lighting, sockets, building services. |  | EICR-DB01-2025
ENE-004 |  | MCC-03 | Motor Control Centre 03 — Final Settlement | LV 415V |  |  | Pending |  | Pre-energisation checks not yet complete. Electrical installation ongoing.
ENE-005 | 2025-01-28 | HV-SW-01 | 11kV Switchboard — Site Incoming Supply | 11kV | EP-HV-2025-001 | G. Thompson (AP HV) | Energised — Live Service |  | DNO energisation. G. Thompson AP authority ref GTE-AUTH-2025-001. | INT-HVSW-001 |  | TC-HVSW-001
TOTAL PANELS | 5 | LIVE SERVICE | 2 | COMMISSIONING | 2 | ISOLATED | 0 | PENDING | 1

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.