## Cover
EBRORA
ebrora.com
Panel / MCC Schedule
Track and manage all electrical panels, motor control centres, and distribution boards across your project — from specification through to commissioning sign-off.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. Open the 'Panel MCC Schedule' sheet. Each row represents one panel, MCC, or distribution board on your project.
2. Enter your panel tag number in the Panel / MCC Tag column. Use your project's standard naming convention (e.g., MCC-01, DB-L2-01, PNL-HVAC-01).
3. Fill in the core columns: description, building/area, room/location, panel type, and supply voltage. These are the minimum fields needed for a useful schedule.
4. Set the Status using the dropdown. Options are: Planned, Ordered, Delivered, Installed, Tested, and Commissioned. Conditional formatting will colour-code the status automatically.
5. Assign responsibility in the Responsible column — typically the electrical subcontractor or commissioning engineer.
6. Use the Notes column for any additional context: delivery dates, issues, punch items, etc.
7. Expand the optional columns by clicking the [+] button above the grouped columns. These contain detailed electrical specifications (rated current, IP rating, incoming supply, ways/outgoing circuits) and commissioning tracking fields.
8. The Summary Dashboard at the top of the data sheet shows live counts by status and panel type — use this for reporting and progress tracking.
Colour Key
Light teal cells = user input / editable fields
Dark navy headers = do not edit
Green = Commissioned / Tested (positive status)
Amber = Installed / Delivered (in progress)
Red = Planned / Ordered (early stage, needs attention)
Tips
• Keep panel tags consistent with your project's electrical drawing register — this makes cross-referencing much easier.
• Update the status column as panels progress through delivery, installation, and commissioning. The dashboard will update automatically.
• Use the optional 'Commissioning Date' and 'Commissioned By' columns to create an auditable record for handover documentation.

## Panel MCC Schedule
Panel / MCC Schedule — Summary Dashboard
Status Summary |  |  |  |  | Panel Type Breakdown
Status | Count | % of Total | Progress |  | Type | Count | Commissioned | % Complete
Planned | 1 | 20% | ████ |  | MCC | 1 | 1 | 100%
Ordered | 0 | 0% |  |  | Distribution Board | 1 | 0 | 0%
Delivered | 1 | 20% | ████ |  | Control Panel | 1 | 0 | 0%
Installed | 1 | 20% | ████ |  | PLC Cabinet | 1 | 0 | 0%
Tested | 1 | 20% | ████ |  | VSD Panel | 1 | 0 | 0%
Commissioned | 1 | 20% | ████
Total Panels: | 5 |  |  |  | Overall Commissioning: |  |  | 20% | ▸ Optional Fields — Click [+] to expand
Item No. | Panel / MCC Tag | Description | Building / Area | Room / Location | Panel Type | Status | Responsible | Notes | Supply Voltage (V) | Rated Current (A) | IP Rating | No. of Ways | Incoming Supply | Manufacturer | Commissioning Date | Commissioned By
1 | MCC-01 | Main Motor Control Centre — WTP Inlet Works | Inlet Works Building | MCC Room GF | MCC | Commissioned | Briggs Electrical Ltd | All drives tested and commissioned 12/02/2026 | 415 | 800 | IP54 | 24 | Transformer T1 — 11kV/415V | ABB | 2026-02-12 | J. Harrison
2 | DB-L2-01 | Distribution Board Level 2 — Admin Block | Admin Building | Riser Cupboard L2 | Distribution Board | Installed | Sparks & Co. | Awaiting final fix connections | 230 | 100 | IP40 | 12 | MCC-01 Way 14 | Hager
3 | PNL-HVAC-01 | HVAC Control Panel — AHU Plant Room | Process Building | AHU Plant Room Roof | Control Panel | Tested | ACE Controls | FAT passed — SAT scheduled next week | 415 | 63 | IP55 | 8 | DB-L3-02 Way 6 | Schneider
4 | VSD-PMP-01 | VSD Panel — Raw Water Pumps 1–3 | Pumphouse A | VSD Room | VSD Panel | Delivered | Briggs Electrical Ltd | Delivered to site 08/03/2026, stored in laydown | 415 | 250 | IP54 | 3 | MCC-01 Way 1-3 | Danfoss
5 | PLC-CAB-01 | PLC Cabinet — SCADA Outstation 1 | Control Room | SCADA Room | PLC Cabinet | Planned | Integrated Automation Ltd | Awaiting final I/O schedule confirmation | 230 | 16 | IP20 | 0 | DB-CR-01 Way 2 | Siemens

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.