## Cover
EBRORA
ebrora.com
Instrument Schedule
Catalogue every instrument on your project — tag, type, range, location, calibration and commissioning status in a single master schedule.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the 'Instrument Schedule' sheet. Each row represents one instrument on your project.
2. | Enter the Instrument Tag in column A (e.g., PT-101, FT-201, LT-301) following your project's tagging convention.
3. | Select the Instrument Type from the dropdown: Pressure, Temperature, Flow, Level, Analytical, or Miscellaneous.
4. | Fill in the description, range/units, location, and service fields using the light teal input cells.
5. | Track each instrument through two stages: 'Calibration Status' (has it been bench-calibrated?) and 'Comm. Status' (has it been loop-checked and commissioned in the field?).
6. | The dashboard at the top auto-calculates totals, calibration %, and commissioning % in real time.
Optional Fields
7. | Click the [+] button above the grouped columns on the right to expand optional fields: Manufacturer, Model No., Signal Output, and P&ID Reference.
8. | These are useful for procurement tracking, loop drawing preparation, and handover documentation packs.
Colour Key
| Light Teal cells | Editable — enter your data here
| Dark Navy headers | Do not edit — column headings and structure
| Green | Calibrated / Commissioned
| Amber | In progress or partially complete
| Red | Not started or failed calibration
Tips
• | Filter by Instrument Type to generate calibration punch lists by discipline (e.g., all pressure transmitters).
• | Use the Calibration Status column to track bench calibrations before installation — this prevents instruments going into the field unchecked.
• | Export a filtered view of 'Comm. Status = Not Started' as a commissioning priority list for weekly progress meetings.

## Instrument Schedule
INSTRUMENT SCHEDULE — PROJECT DASHBOARD
Total Instruments: | -490 | Calibrated: | 2 | Cal. Failed: | 1 | Commissioned: | 1 | Cal. %: | 0% | Comm. %: | 0%
▸ Optional Fields — Click [+] to expand
Instrument Tag | Instrument Type | Description | Range / Units | Location / Area | Service / Process | Loop No. | Installed | Calibration Status | Comm. Status | Notes | Manufacturer | Model No. | Signal Output | P&ID Ref
PT-101 | Pressure | Inlet Pressure Transmitter | 0-10 bar | Pump House PH-01 | Raw Water Intake | LP-101 | Yes | Complete | Complete |  | Endress+Hauser | Cerabar PMC51 | 4-20mA | P&ID-003
TT-201 | Temperature | Process Water Temp Sensor | 0-100°C | Heat Exchanger HX-01 | Process Water | LP-201 | Yes | Complete | In Progress | Loop check scheduled Fri | Siemens | SITRANS TH300 | 4-20mA | P&ID-005
FT-301 | Flow | Treated Water Flow Meter | 0-500 m³/h | Outlet Chamber OC-01 | Treated Water | LP-301 | Yes | In Progress | Not Started | Awaiting zero-flow check | ABB | ProcessMaster FEP630 | HART | P&ID-007
LT-401 | Level | Sludge Holding Tank Level | 0-5 m | Sludge Tank ST-01 | Sludge | LP-401 | No | Not Started | Not Started | Instrument on order | Vega | VEGAPULS 64 | 4-20mA | P&ID-010
AT-501 | Analytical | Residual Chlorine Analyser | 0-5 mg/l | Contact Tank CT-01 | Treated Water | LP-501 | Yes | Failed | Not Started | Sensor replaced — re-cal required | Hach | CL17sc | Modbus | P&ID-012

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.