## Cover
EBRORA
ebrora.com
MEICA Spares Inventory
Manage spare parts for mechanical, electrical, instrumentation, and control equipment — with automatic stock-level monitoring, reorder alerts, and inventory value tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
1. Open the 'Spares Inventory' sheet. The top section shows a Stock Health Dashboard with live summaries by discipline and overall inventory value.
2. Each row represents one spare part or consumable item held for MEICA equipment on your project or site.
3. Enter the Part Number, description, associated equipment tag, and discipline (Mechanical, Electrical, Instrumentation, Control & Automation).
4. Set the Min Stock and Max Stock thresholds. The Stock Status column auto-calculates: OK (at or above min), Low (below min but >0), or Out of Stock (zero).
5. Update the Qty in Stock as items are used or received. The Reorder Alert column flags items that need ordering based on the min threshold.
6. Enter the unit cost in the Unit Cost column. The Stock Value auto-calculates as Qty in Stock × Unit Cost.
7. Expand the optional columns for supplier details, lead times, last order date, and storage location.
8. Use filters to view spares by discipline, stock status, or equipment — useful for generating reorder lists or handover inventories.
Colour Key
Light teal cells = user input / editable fields
Dark navy headers = do not edit
Green = Stock OK (at or above minimum level)
Amber = Stock Low (below minimum but not zero)
Red = Out of Stock or Reorder Required
Tips
• Set minimum stock levels based on criticality and lead time — a pump mechanical seal with a 12-week lead time needs a higher min stock than an off-the-shelf gasket.
• Review the reorder alerts weekly and place orders before stock reaches zero — commissioning delays caused by missing spares are entirely preventable.
• Include this inventory as an appendix to your O&M handover package — the operations team needs to know what spares are available from day one.

## Spares Inventory
MEICA Spares Inventory — Stock Health Dashboard
Stock Health by Discipline | [5 empty] | Inventory Summary
Discipline | Total Items | In Stock | Low Stock | Out of Stock |  | Total Unique Parts: |  | 9
Mechanical | 3 | 2 | 0 | 1 |  | Total Stock Value: |  | 5053.5
Electrical | 2 | 1 | 1 | 0 |  | Items at OK Level: |  | 6
Instrumentation | 2 | 2 | 0 | 0 |  | Items Low: |  | 1
Control & Automation | 2 | 1 | 0 | 1 |  | Items Out of Stock: |  | 2
[6 empty] | Reorders Required: |  | 5
Part Identification |  |  |  |  | Stock Levels & Reorder Logic | [6 empty] | Notes | ▸ Optional Fields — Click [+] to expand
Item No. | Part Number | Part Description | Equipment Tag | Discipline | Min Stock | Max Stock | Qty in Stock | Unit Cost (£) | Stock Value (£) | Stock Status | Reorder Alert | Notes | Supplier | Lead Time (wks) | Last Order Date | Storage Location
1 | SP-M-001 | Mechanical Seal — Pump Type A (Grundfos CR 45) | PMP-RW-01 | Mechanical | 2 | 4 | 3 | 285 | 855 | OK |  |  | Grundfos UK | 12 | 2025-11-15 | Store Room A — Shelf M1
2 | SP-M-002 | Impeller — Raw Water Pump (Xylem NS80) | PMP-RW-02 | Mechanical | 1 | 2 | 0 | 1450 | 0 | Out of Stock | REORDER | Impeller on order — ETA mid-April 2026 | Xylem Water Solutions | 16 | 2025-09-20 | Store Room A — Shelf M3
3 | SP-M-003 | V-Belt Set — AHU Supply Fan | AHU-01 | Mechanical | 2 | 6 | 5 | 42.5 | 212.5 | OK |  |  | Bearings Direct | 2 | 2026-02-01 | Store Room B — Shelf M1
4 | SP-E-001 | Contactor LC1D25 — DOL Starter | MCC-01 | Electrical | 3 | 6 | 2 | 68 | 136 | Low | REORDER |  | Schneider Electric UK | 3 | 2026-01-10 | Elec Store — Bin E4
5 | SP-E-002 | Fuse Link 63A HRC BS88 | DB-L2-01 | Electrical | 6 | 12 | 8 | 12.5 | 100 | OK |  |  | RS Components | 1 | 2026-03-01 | Elec Store — Bin E1
6 | SP-I-001 | Pressure Transmitter — 0–6 bar 4–20mA | PT-310 | Instrumentation | 1 | 2 | 1 | 520 | 520 | OK | REORDER |  | Endress+Hauser UK | 8 | 2025-12-05 | Inst Store — Shelf I2
7 | SP-I-002 | RTD Sensor PT100 — 150mm Insertion | TT-402 | Instrumentation | 2 | 4 | 4 | 95 | 380 | OK |  |  | TC Direct | 2 | 2026-02-15 | Inst Store — Shelf I1
8 | SP-C-001 | PLC CPU Module — Siemens S7-1500 1515 | PLC-CAB-01 | Control & Automation | 1 | 1 | 1 | 2850 | 2850 | OK | REORDER |  | Siemens UK | 10 | 2025-10-01 | Control Store — Cabinet C1
9 | SP-C-002 | Digital I/O Module — Siemens SM 1223 | PLC-CAB-01 | Control & Automation | 2 | 4 | 0 | 385 | 0 | Out of Stock | REORDER | Urgent — 2 modules needed for commissioning next week | Siemens UK | 10 | 2025-10-01 | Control Store — Cabinet C1
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.