## Cover
EBRORA
ebrora.com
Weld Inspection Register
Track every weld joint through fit-up, visual inspection, and NDT stages with automatic acceptance status and pipeline progression.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Weld Register' sheet — this tracks every weld joint from fit-up to final acceptance.
2. The pipeline summary (rows 2–5) shows live counts of welds at each inspection stage plus acceptance/rejection rates.
3. Enter each weld joint with its reference, location, material details, WPS number, and welder ID.
4. Record the fit-up inspection result first (Accept/Reject). Only accepted fit-ups should proceed to welding.
5. After welding, record the visual inspection (VT) result. Then record the NDT method and result when available.
6. The Overall Status column auto-calculates: ACCEPTED (all stages pass), REJECTED (any stage fails), or IN PROGRESS.
7. Use the [+] button to expand optional columns for preheat temp, PWHT status, and repair details.
8. Filter by status or welder to monitor individual performance or find outstanding inspections.
Colour Key
| Light teal cells | Editable — enter your data here
| Dark navy headers | Do not edit — column headers and labels
| Green fill | ACCEPTED — inspection stage passed
| Red fill | REJECTED — inspection stage failed
| Amber fill | IN PROGRESS — awaiting inspection result
Tips
• Always record the WPS (Welding Procedure Specification) number — this links the weld to its approved procedure and is essential for QA audits.
• Ensure welder IDs match their valid welding certificates — check qualifications cover the material, thickness, and position for each joint.
• If a weld is rejected and repaired, log the repair in the optional columns and re-inspect. Keep the original rejection visible for traceability.

## Weld Register
WELD INSPECTION REGISTER — PIPELINE SUMMARY
Total Welds |  | Fit-Up Done |  | VT Done |  | NDT Done |  | Accepted |  | Rejected
5 |  | 5 |  | 4 |  | 3 |  | 3 |  | 1
[8 empty] | 75% | acceptance rate
▸ Optional Fields — Click [+] to expand
Weld Ref | Date Welded | Location / Element | Joint Type | Material / Grade | WPS No. | Welder ID | Fit-Up Result | VT Result | NDT Method | NDT Result | Overall Status | Notes | Preheat Temp (°C) | PWHT Required | PWHT Status | Repair Details
W-001 | 2026-02-10 | Steelwork — Col C1 Base Plate | Fillet | S355 J2 | WPS-042 | JB-101 | Accept | Accept | MT (Magnetic Particle) | Accept | ACCEPTED | Full pen fillet as per dwg SK-101 | 150 | No | N/A
W-002 | 2026-02-11 | Pipe Spool PS-14 Flange | Butt | P265GH | WPS-018 | KR-205 | Accept | Accept | RT (Radiographic) | Accept | ACCEPTED | 100% RT per spec | 200 | Yes | Complete
W-003 | 2026-02-13 | Steelwork — Beam B7 Splice | Butt | S275 JR | WPS-042 | JB-101 | Accept | Reject |  |  | REJECTED | Undercut >1mm — repair required |  | No | N/A | Repair logged — see NCR-045
W-004 | 2026-02-14 | Pipe Spool PS-22 Branch | Branch | 316L SS | WPS-055 | MH-310 | Accept | Accept | PT (Dye Penetrant) | Accept | ACCEPTED |  | 120 | No | N/A
W-005 | 2026-02-15 | Tank T2 Shell Course 1 | Butt | S355 J2 | WPS-042 | KR-205 | Accept |  |  |  | IN PROGRESS | Awaiting VT inspection | 150 | Yes | Pending

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.