## Cover
EBRORA
ebrora.com
Plant & Equipment Register
Manage all plant and equipment on site — track assets, certification status, hire costs, and inspection expiry dates in one register.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Go to the “Plant & Equipment Register” tab. Each row records one item of plant or equipment on site.
2. | Enter the Plant ID / Asset No. (as marked on the machine), a description, and select the Plant Type from the dropdown.
3. | Select whether the item is Hired or Owned, and enter the Supplier / Hire Company name.
4. | Record the Date on Site and the current Inspection Certificate Date and Cert Expiry Date. The Cert Status column auto-calculates: Valid (>14 days remaining), Expiring (within 14 days), or Expired (past expiry).
5. | Enter the current Location on Site for the item.
6. | Expand optional columns for: Serial No., Operator Assigned, Weekly Hire Rate, Insurance Cert Held, Off-Hire Date, and Notes.
7. | The summary section includes a cross-tab matrix showing plant count by type and certification status, plus key totals and weekly hire cost.
Summary Matrix
• | The matrix at the top of the register shows a grid: rows = plant types, columns = certification status (Valid / Expiring / Expired). This gives you an instant visual of fleet health.
• | Below the matrix: total items on site, hired vs owned split, expired certs count, and total weekly hire cost.
Colour Key
• | Light teal cells = User input / editable fields.
• | Cert Status: Green = Valid, Amber = Expiring (within 14 days), Red = Expired.
• | Full-row red highlight = Cert has expired — machine should not be operated.
Tips
• | Under PUWER 1998, all work equipment must be maintained and where required have current inspection certificates. Expired certs mean the machine must be taken out of service.
• | Review this register weekly. Filter by Cert Status = “Expiring” to arrange re-inspections before they lapse. Arrange inspections at least 14 days before expiry.
• | For hired plant, check the weekly rate against the hire company’s schedule. The register auto-totals your weekly hire cost to help with cost management.

## Plant & Equipment Register
PLANT & EQUIPMENT REGISTER
CERTIFICATION STATUS MATRIX
Plant Type | Valid | Expiring | Expired | Total |  | Total Items on Site: | 7
Excavator | 1 | 0 | 0 | 1 |  | Hired: | 6
Dumper | 1 | 0 | 0 | 1 |  | Owned: | 1
Telehandler | 1 | 0 | 0 | 1 |  | Certs Expired: | 1
Roller | 0 | 0 | 0 | 0 |  | Certs Expiring (14d): | 1
MEWP | 0 | 0 | 1 | 1 |  | Weekly Hire Cost (£): | 9530
Crane | 0 | 1 | 0 | 1
Other | 2 | 0 | 0 | 2
TOTAL | 5 | 1 | 1 | 7
▸ Optional Fields — Click [+] to expand
Plant ID / Asset No. | Plant Description | Plant Type | Hired / Owned | Supplier / Hire Co. | Date on Site | Inspection Cert Date | Cert Expiry Date | Cert Status | Location on Site | Serial No. | Operator Assigned | Weekly Rate (£) | Insurance Cert (Y/N) | Off-Hire Date | Notes
EXC-03 | Komatsu PC210 Tracked Excavator | Excavator | Hired | Hewden Plant Hire | 2026-01-06 | 2026-02-10 | 2026-08-10 | Valid | Block C, Piling Mat | SN-KPC210-44821 | D. Evans | 1850 | Yes |  | 6-month hire. LOLER thorough examination current.
DUMP-07 | Thwaites 6T Forward Tip Dumper | Dumper | Hired | Hewden Plant Hire | 2026-01-06 | 2026-01-15 | 2026-07-15 | Valid | Block C, Earthworks | SN-TW6T-51002 | T. Williams | 650 | Yes
TH-02 | JCB 540-170 Telehandler | Telehandler | Hired | A-Plant | 2026-02-03 | 2026-02-05 | 2026-08-05 | Valid | General — site-wide | SN-JCB540-77310 | P. Morgan | 1200 | Yes |  | 17m reach. Used for steel and material offloading.
TC-01 | Liebherr 280 EC-H Tower Crane | Crane | Hired | Select Plant Hire | 2025-11-15 | 2026-02-20 | 2026-04-01 | Expiring | Central Compound, Fixed Base | SN-LB280-99102 | Crane operator (Select) | 4500 | Yes |  | LOLER thorough exam due 01/04. Re-inspection booked with Select for 28/03.
MEWP-01 | Genie Z-45/25J RT Articulating Boom | MEWP | Hired | Nationwide Platforms | 2026-03-01 | 2026-03-01 | 2026-03-20 | Expired | Block B, External cladding | SN-GEN45-63401 | S. Hall | 950 | Yes |  | LOLER cert expired 20/03. Machine stood down. Hire company arranging re-inspection.
GEN-02 | Atlas Copco QAS 150 Generator (150 kVA) | Generator | Hired | Speedy Hire | 2026-01-20 | 2026-01-20 | 2027-01-20 | Valid | Temp Compound B, South | SN-AC150-20441 |  | 380 | Yes |  | Powering welfare and site offices. Annual PAT and load test current.
COMP-01 | Atlas Copco XATS 138 Compressor | Compressor | Owned | Main Contractor (owned) | 2026-02-10 | 2025-12-05 | 2026-06-05 | Valid | Block A, Ground Floor | SN-ACXATS-10882 |  | 0 | Yes |  | Company-owned. PSSR examination current. Used for pneumatic testing.
Formulas:
Cert Status = IF([Cert Expiry Date]="","",IF([Cert Expiry Date]<TODAY(),"Expired",IF([Cert Expiry Date]<=TODAY()+14,"Expiring","Valid")))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.