## Cover
EBRORA
ebrora.com
LOLER Thorough
Examination Calendar
Schedule and track LOLER thorough examinations for cranes, MEWPs,
hoists, and lifting accessories with due date alerts.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Examination Calendar' sheet. Each row is one item of lifting equipment or accessory.
2. | Record the Equipment ID, Description, Type (Crane, MEWP, Hoist, Passenger Hoist, Goods Lift, Other), and SWL/WLL.
3. | Enter the Last Examination Date, Examiner (competent person), and Certificate Number.
4. | The Exam Frequency column determines the interval: 6 months for equipment lifting persons, 12 months for other lifting equipment.
5. | Monthly columns (Apr 2026 – Mar 2027) show the status. Mark each month as: Due, Booked, Done, N/A.
6. | The 'Next Due' column auto-calculates from the last examination date plus the frequency.
7. | Items overdue (Next Due in the past) highlight red. Items due within 30 days highlight amber.
Colour Key
Light teal cells = User input
Green = Done (examination complete)
Amber = Due or Booked this month, or due within 30 days
Red = Overdue
Tips
Tip 1: | LOLER thorough examinations are a legal requirement. Operating lifting equipment without a valid examination is a criminal offence.
Tip 2: | Book examinations 4–6 weeks in advance. Examiners are in high demand — last-minute bookings cause programme delays.
Tip 3: | Pin this calendar in the site office. The crane supervisor and lifting coordinator should check it weekly.

## Examination Calendar
Equipment ID | Description | Type | SWL / WLL | Last Exam Date | Examiner | Certificate No | Frequency (months) | Next Due | Apr 26 | May 26 | Jun 26 | Jul 26 | Aug 26 | Sep 26 | Oct 26 | Nov 26 | Dec 26 | Jan 27 | Feb 27 | Mar 27 | Overall Status
CR-001 | Liebherr LTM 1100 — 100t Mobile Crane | Crane (Mobile) | 100t | 2025-10-15 | Zurich Engineering | TE-2025-4412 | 6 | 2026-04-15 | Done | N/A | N/A | Due | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | DUE SOON
MEWP-001 | JLG 600AJ — Articulating Boom | MEWP | 227kg / 20.3m | 2025-12-01 | CFTS Examiner | TE-2025-5501 | 6 | 2026-06-01 | N/A | N/A | Done | N/A | N/A | Booked | N/A | N/A | N/A | N/A | N/A | N/A | Current
MEWP-002 | Genie GS-2632 — Scissor Lift | MEWP | 227kg / 9.9m | 2026-01-20 | CFTS Examiner | TE-2026-0088 | 6 | 2026-07-20 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Due | N/A | N/A | N/A | N/A | Current
PH-001 | Alimak SC 65/32 — Passenger Hoist | Hoist (Passenger) | 2000kg / 32m | 2025-11-10 | Alimak Service | TE-2025-4998 | 6 | 2026-05-10 | N/A | N/A | N/A | N/A | Due | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Current
TH-001 | JCB 540-170 — Telehandler | Telehandler | 4t / 17m | 2025-08-05 | HSB Engineering | TE-2025-3315 | 12 | 2026-08-05 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Due | N/A | N/A | N/A | N/A | Current
FLT-001 | Toyota Tonero 3t — Counterbalance | Forklift | 3t | 2026-02-28 | Zurich Engineering | TE-2026-0201 | 12 | 2027-02-28 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Due | Current
SUMMARY | Total Equipment: | 6 | Overdue: | 0 | Due Soon: | 1
Formulas:
Next Due = IF(OR([Last Exam Date]="",[Frequency (months)]=""),"",DATE(YEAR([Last Exam Date]),MONTH([Last Exam Date])+[Frequency (months)],DAY([Last Exam Date])))
Overall Status = IF([Next Due]="","",IF([Next Due]<TODAY(),"OVERDUE",IF([Next Due]<=TODAY()+30,"DUE SOON","Current")))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.