## Cover
EBRORA
ebrora.com
PUWER Inspection
Matrix
Inspect small plant and power tools against PUWER requirements
with pass/fail criteria, condition ratings, and inspection scheduling.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'PUWER Matrix' sheet. Each row is one item of work equipment (power tools, bench saws, grinders, etc.).
2. | Record the Equipment ID, Description, Category (from dropdown), and Location on site.
3. | For each inspection criterion (columns E–H), mark Pass, Fail, or N/A. These form the PUWER compliance check.
4. | Assign a Condition Rating: Good, Fair, or Poor. Items rated Poor must be removed from service immediately.
5. | Record the Last Inspection date, Inspector name, and Next Due date (typically weekly or monthly for small plant).
6. | The Overall Status auto-calculates: if any criterion is Fail or Condition is Poor, the status shows 'FAIL — Remove from Service'.
7. | Use the Completion % row at the bottom to track how many items have been inspected this period.
Colour Key
Light teal cells = User input
Green = Pass / Good condition
Amber = Fair condition (monitor)
Red = Fail / Poor condition / Overdue inspection
Tips
Tip 1: | PUWER inspections must be carried out by a competent person. For power tools, this is typically a trained supervisor — not the operator.
Tip 2: | Failed items must be immediately quarantined with a 'DO NOT USE' tag. Never leave a failed tool accessible.
Tip 3: | Weekly visual inspections + quarterly formal inspections is a sensible regime for most construction small plant.

## PUWER Matrix
Equipment ID | Description | Category | Location | Visual Check | Guards & Safety Devices | Emergency Stop | Electrical Test (PAT) | Condition Rating | Last Inspection | Inspector | Next Due | Overall Status | Notes
PT-001 | Makita GA9050 — 230mm Angle Grinder | Angle Grinder | Inlet Works | Pass | Pass | N/A | Pass | Good | 2026-03-19 | R. Evans | 2026-04-16 | PASS | Disc guard in place, cable intact
PT-002 | Hilti TE 60-ATC — SDS Breaker | Breaker | Storm Tanks | Pass | Pass | N/A | Pass | Good | 2026-03-19 | R. Evans | 2026-04-16 | PASS
PT-003 | Stihl TS 420 — Petrol Cut-Off Saw | Circular Saw | General Site | Pass | Fail | N/A | N/A | Fair | 2026-03-19 | R. Evans | 2026-04-16 | FAIL — Remove | Blade guard return spring weak — replace before next use
PT-004 | DeWalt DCD996 — 18V Combi Drill | Drill (Cordless) | MCC Building | Pass | N/A | N/A | N/A | Good | 2026-03-19 | A. Khan | 2026-04-16 | PASS | Battery charge OK
PT-005 | Honda EU70is — 7kVA Generator | Generator | Compound | Pass | Pass | Pass | Pass | Good | 2026-03-12 | R. Evans | 2026-04-09 | PASS | Earth bonding checked
PT-006 | Lincoln Invertec V270-T — TIG Welder | Welder | Pipe Fabrication Area | Pass | Pass | Pass | Pass | Good | 2026-03-21 | M. Thompson | 2026-04-18 | PASS | Flash-back arrestors fitted
PT-007 | Wacker Neuson BS 60-4As — Rammer | Compactor | Trench Works | Pass | Pass | N/A | N/A | Fair | 2026-03-16 | R. Evans | 2026-04-13 | PASS — Monitor | Handle vibration slightly high — monitor
PT-008 | 110V Transformer — 5kVA | Other | General Site | Fail | N/A | N/A | Fail | Poor | 2026-03-22 | R. Evans | 2026-03-22 | FAIL — Remove | REMOVED FROM SERVICE — earth fault detected on PAT test
SUMMARY | Total Items: | 8 | Pass: | 5 | Monitor: | 1 | Fail: | 2

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.