## Cover
EBRORA
ebrora.com
Early Warning Register
Log and risk-score early warnings under NEC Clause 15
with automatic risk rating and risk reduction meeting tracking.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'EW Register' sheet. The top section has two panels: a Risk Summary (left) showing counts by risk level and a Status Summary (right) showing early warnings by current status.
2. | Each row is one early warning. Enter the EW Ref, Date Raised, who raised it, a clear description of the risk or matter that could increase cost/delay/impair performance, and the current Status.
3. | Score each early warning using the Likelihood (1–5) and Impact (1–5) dropdowns. The Risk Score calculates automatically as Likelihood × Impact, and the Risk Rating assigns High / Medium / Low based on the score.
4. | The scoring thresholds are: High = 15–25, Medium = 6–14, Low = 1–5. These match common 5×5 risk matrix conventions.
5. | Update the Status as the early warning progresses: Open → Discussed at RRM → Mitigated / Closed / Escalated to CE. Enter the Date of next or last Risk Reduction Meeting.
Risk Scoring Guide
Likelihood: 1 = Very unlikely, 2 = Unlikely, 3 = Possible, 4 = Likely, 5 = Very likely
Impact: 1 = Negligible, 2 = Minor, 3 = Moderate, 4 = Major, 5 = Critical
Risk Score = Likelihood × Impact (auto-calculated)
Risk Rating: 1–5 = Low (green), 6–14 = Medium (amber), 15–25 = High (red)
Optional Fields
6. | Click [+] to expand optional fields: Risk Owner, Mitigation Action, Date RRM Discussed, Residual Risk Score (post-mitigation), Linked CE Ref, and Estimated Cost Impact (£).
7. | The Residual Risk Score lets you track how effective your mitigation has been by re-scoring after the Risk Reduction Meeting.
Colour Key
Light teal cells (#E8F6F7) — User input.
Dark navy headers — Do not edit.
Red risk rating — High risk (score 15–25).
Amber risk rating — Medium risk (score 6–14).
Green risk rating — Low risk (score 1–5).
Blue status — Open (new, not yet discussed).
Amber status — Discussed at RRM (under active management).
Green status — Mitigated or Closed.
Red status — Escalated to CE (compensation event raised).
Tips
Tip 1: | Under NEC4 Clause 15.1, both the PM and Contractor must notify early warnings. Log them immediately — proactive early warning management is a contractual obligation, not optional.
Tip 2: | Hold Risk Reduction Meetings fortnightly as a minimum. Review all Open and Discussed items. Record outcomes and update the Mitigation Action column.
Tip 3: | When an early warning materialises into a compensation event, update the status to 'Escalated to CE' and enter the linked CE Ref. This creates a clear audit trail between the EW and CE registers.

## EW Register
EARLY WARNING REGISTER — NEC RISK SCORING
RISK LEVEL SUMMARY | [5 empty] | STATUS SUMMARY
High (15–25) |  |  | 2 |  |  | Open |  | 1
Medium (6–14) |  |  | 3 |  |  | Discussed at RRM |  | 2
Low (1–5) |  |  | 0 |  |  | Mitigated |  | 1
Total Active |  |  | 4 |  |  | Closed |  | 0
[6 empty] | Escalated to CE |  | 1
Scoring: Likelihood (1=Very Unlikely → 5=Very Likely) × Impact (1=Negligible → 5=Critical) ¦ High = 15–25 ¦ Medium = 6–14 ¦ Low = 1–5
▸ Optional Fields — Click [+] to expand
EW Ref | Date Raised | Raised By | Description | Likelihood (1–5) | Impact (1–5) | Risk Score | Risk Rating | Status | Notes | Risk Owner | Mitigation Action | Date RRM Discussed | Residual Risk Score | Linked CE Ref | Est. Cost Impact (£)
EW-001 | 2025-06-15 | Contractor | Ground investigation indicates potential soft spots in Zone A. Risk of additional piling if confirmed during excavation. | 4 | 5 | 20 | High | Escalated to CE | Materialised — see CE-001 | Site Agent | Instructed additional trial pits. Results confirmed soft ground. | 2025-07-01 | 8 | CE-001 | 48000
EW-002 | 2025-07-22 | PM | Utility diversion by UKPN running 4 weeks behind programme. Risk of delayed access to Zone D for substructure works. | 4 | 4 | 16 | High | Discussed at RRM | UKPN latest update: 2-week delay remains. Monitoring weekly. | Project Manager | Weekly liaison with UKPN. Resequencing Zone D to mitigate. | 2025-08-05 | 9 |  | 0
EW-003 | 2025-08-10 | Contractor | Cladding manufacturer reports global aluminium shortage. Risk of 6–8 week lead time extension on curtain wall system. | 3 | 4 | 12 | Medium | Mitigated | Alternative supplier approved. Lead time confirmed at 12 weeks. | Procurement Manager | Sourced Kawneer alternative. Approved by architect. | 2025-08-19 | 4 |  | 0
EW-004 | 2025-10-05 | Designer | Revised Building Regulations Part L requirements may apply to north elevation glazing. Potential cost impact if U-values need upgrading. | 3 | 3 | 9 | Medium | Discussed at RRM | Design team reviewing options. Decision due by end of month. | Design Manager | Commission thermal modelling study. Review at next RRM. | 2025-10-19 |  |  | 15000
EW-005 | 2025-11-20 | Contractor | Specialist fire stopping subcontractor has limited capacity in Q1 2026. Risk of delay to internal fit-out if not secured early. | 3 | 3 | 9 | Medium | Open | Procurement to issue enquiry this week. | Procurement Manager |  |  |  |  | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.