## Cover
EBRORA
ebrora.com
Weather Delay Log
Record weather events that affect site progress — with contractual delay tracking to support extension of time claims and compensation events.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Delay Log' sheet. The monthly summary grid at the top shows total delay events and hours lost per month — this updates automatically as you add entries.
2. | Each row in the main log represents one weather delay event. Fill in the light teal cells.
3. | Enter the Date, select the Weather Type from the dropdown, and record the Start Time and End Time of the disruption.
4. | The Duration column calculates automatically in hours and minutes. The Delay Hours column rounds this to a decimal for reporting.
5. | Describe the Affected Area or Activity (e.g. 'Crane operations suspended', 'Concrete pour postponed') and select the Impact level: Full Stop, Partial, or Minor.
6. | Expand the optional columns (click [+]) to record wind speed, temperature, rainfall measurements, contractual references, notification status, and photo evidence.
7. | For NEC contracts, cross-reference each entry with a Compensation Event number in the optional 'Contractual Ref' column. For JCT, reference the relevant EOT clause.
Colour Key
Light teal cells — Editable input cells.
Dark navy headers — Do not edit.
Red — Impact is 'Full Stop' (total site shutdown).
Amber — Impact is 'Partial' (some activities affected).
Green — Impact is 'Minor' (limited disruption).
Tips
Tip 1: | Record weather events the same day they happen. Retrospective entries are weaker evidence in a contractual dispute — contemporaneous records carry far more weight.
Tip 2: | Cross-reference this log with your Daily Site Diary. The diary gives narrative context; this log gives the hard data (times, durations, measurements).
Tip 3: | Under NEC4 clause 60.1(12), weather is a compensation event if it's measured at the 1-in-10 year threshold. Keep the optional weather measurement columns filled in to support your case.

## Delay Log
WEATHER DELAY LOG
MONTHLY SUMMARY
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | TOTAL
Events | 2 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5
Hours Lost | 13.5 | 5 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26.5
Full Stops | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2
Summary auto-calculates from the log below. Months with zero events show 0.
▸ Optional Fields — Click [+] to expand
No. | Date | Weather Type | Start Time | End Time | Duration | Affected Area / Activity | Impact | Delay (hrs) | Wind (mph) | Temp (°C) | Rain (mm) | Contractual Ref | Notified | Photo Ref
1 | 2026-01-08 | Rain | 6:00 | 14:00 | 0.33333 | Full site — crane ops suspended, excavation flooded | Full Stop | 8 | 35 | 4 | 22.5 | CE-2026-003 | Yes | IMG_0501.jpg
2 | 2026-01-22 | High Wind | 10:30 | 16:00 | 0.22917 | Tower crane zone — all lifting stopped above 38mph | Partial | 5.5 | 42 | 7 | 0 | CE-2026-005 | Yes | IMG_0518.jpg
3 | 2026-02-05 | Snow/Ice | 6:00 | 11:00 | 0.20833 | Access roads impassable — deliveries cancelled, morning shift delayed | Full Stop | 5 | 0 | -3 | 0 | CE-2026-008 | Yes | IMG_0530.jpg
4 | 2026-03-12 | Storm | 13:00 | 17:30 | 0.1875 | Scaffolding inspection required after 55mph gusts — external works stopped | Partial | 4.5 | 55 | 9 | 8 |  | No | IMG_0545.jpg
5 | 2026-03-19 | Fog | 6:00 | 9:30 | 0.14583 | Crane visibility below safe limits — morning lift programme delayed | Minor | 3.5 | 0 | 5 | 0 |  | N/A
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.