## Cover
EBRORA
ebrora.com
Critical Path Register
Map key programme milestones against a monthly timeline — track planned vs actual progress and flag critical path delays at a glance.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2025 — All rights reserved

## Instructions
How to Use This Template — Critical Path Register
Step-by-Step Instructions
1. | Go to the 'Critical Path Register' sheet. Enter your project name and programme start month in the info strip at the top.
2. | For each activity or milestone, enter a unique Activity ID in column A and a description in column B.
3. | Assign responsibility in column C. Enter the planned float in column D (0 = critical, >0 = non-critical).
4. | Mark the activity as Critical (Y/N) in column E using the dropdown. Critical items will be highlighted red.
5. | Enter baseline start and finish dates in columns F and G. These should match your accepted programme baseline.
6. | Update columns H and I with the actual or forecast start and finish dates as the project progresses.
7. | Use the Status dropdown (column J) to record the current state: Not Started, In Progress, Complete, or Delayed.
8. | In the monthly columns (K onwards), type P for each month the activity is planned to be active, and A once it has been completed in that period.
9. | The summary row at the bottom counts how many planned and actual entries exist per month, giving a quick programme health check.
10. | Click [+] above columns T–W to expand Optional Fields for WBS codes, predecessor/successor links, and free-text comments.
Colour Key
Critical activity (Float = 0) — entire row highlighted red. Any delay directly impacts completion.
Delayed status — activity is running behind programme.
Complete — activity finished within programme.
P marker — activity planned in this monthly period.
A marker — activity actually completed/active in this period.
Light teal cells — User input / editable fields.
Tips
* | Update this register at your weekly site meeting. It only takes 10 minutes and gives the PM a clear view of programme health without needing to open Primavera or MS Project.
* | Focus on activities with Float = 0 first. Any delay on a critical item needs an immediate mitigation plan — raise an Early Warning under NEC4 if it affects the Completion Date.
* | If an activity becomes critical mid-project (float burns away), update column E to Y and add a note. Programme changes should be logged formally.

## Critical Path Register
Project Name: |  |  |  | [Enter Project Name] |  |  |  | Programme Baseline: | [25 empty] | ▸ Optional Fields — Click [+] to expand
Activity Details | [9 empty] | Monthly Progress ¦ P = Planned Active ¦ A = Actual Complete | [23 empty] | Optional
Activity ID | Activity / Milestone Description | Responsible | Float (Days) | Critical? | Baseline Start | Baseline Finish | Actual / Forecast Start | Actual / Forecast Finish | Status | Apr-25 | May-25 | Jun-25 | Jul-25 | Aug-25 | Sep-25 | Oct-25 | Nov-25 | Dec-25 | Jan-26 | Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | WBS Code | Predecessor | Successor | Comments
CP-001 | Enabling Works & Site Establishment | J. Hargreaves | 0 | Y | 2025-04-01 | 2025-05-31 | 2025-04-01 | 2025-05-31 | Complete | A | A
CP-002 | Groundworks — Primary Tank Formation | M. Clarke | 0 | Y | 2025-05-01 | 2025-08-31 | 2025-05-07 |  | In Progress |  | A | A | P | P
CP-003 | Concrete Works — Inlet Chamber | S. Patel | 5 | N | 2025-06-01 | 2025-07-31 |  |  | Not Started |  |  | P | P
CP-004 | MEICA Installation — MCC & Cabling | C. Roberts | 0 | Y | 2025-09-01 | 2025-12-31 |  |  | Not Started | [5 empty] | P | P | P | P
CP-005 | Commissioning — Dry Run & FAT Sign-Off | T. Walsh | 0 | Y | 2026-01-01 | 2026-02-28 |  |  | Not Started | [10 empty] | P | P
CP-006 | Survey & As-Built Drawing Submission | A. Nkosi | 10 | N | 2026-01-01 | 2026-03-31 |  |  | Not Started | [10 empty] | P | P | P
CP-007 | Handover — Snag Clearance & Certificate | J. Hargreaves | 0 | Y | 2026-03-01 | 2026-03-31 |  |  | Not Started | [12 empty] | P
PROGRAMME SUMMARY — PLANNED (P) / ACTUAL (A) COUNTS PER PERIOD
Planned (P) count: | [9 empty] | 0 | 0 | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Actual (A) count: | [9 empty] | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.