## Cover
EBRORA
ebrora.com
Simple Project Timeline
Visual Gantt-style project timeline with task bars, milestone markers, percentage completion, and automatic duration tracking.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Step-by-Step Instructions
1. Go to the 'Timeline' sheet. Tasks are listed on the left; the Gantt grid shows 26 weeks on the right.
2. Enter each task/activity with its name, start date, end date, owner, and current % complete.
3. Duration (days) auto-calculates from the date range. Status auto-determines from % complete and dates.
4. The Gantt grid auto-fills with teal bars where the task spans each week column.
5. Completed tasks show green bars; in-progress show teal; overdue show red bars.
6. Add milestone rows (0-day duration) by setting the same start and end date — they show as diamond markers.
7. The summary panel shows overall progress, tasks on track, and overdue count.
8. Print on A3 landscape for wall display, or A4 landscape for desk reference.
Colour Key
| Light teal | Editable cells
| Dark navy | Headers
| Teal bar | Task in progress / planned
| Green bar | Task complete
| Red | Overdue task
Tips
• Keep task descriptions short — this is a visual overview, not a detailed programme.
• Use this alongside your full programme (Primavera/MS Project) as a management summary.
• Update % complete weekly and bring to progress meetings — one page tells the whole story.

## Timeline
SIMPLE PROJECT TIMELINE
Overall Progress: |  | 27.5% | Tasks: | 12
# | Task / Activity | Start | End | Duration (days) | Owner | % Complete | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29 | 2026-07-06 | 2026-07-13 | 2026-07-20 | 2026-07-27
1 | Site Setup & Mobilisation | 2026-02-02 | 2026-02-13 | 11 | M. Evans | 100%
2 | Demolition & Site Strip | 2026-02-10 | 2026-02-28 | 18 | D. Murphy | 100%
3 | Earthworks — Cut & Fill | 2026-02-17 | 2026-03-20 | 31 | D. Murphy | 75%
4 | Piling Works | 2026-03-02 | 2026-03-27 | 25 | Piling Sub | 40%
5 | Foundations & Ground Beams | 2026-03-16 | 2026-04-17 | 32 | M. Evans | 10%
6 | Steelwork Erection | 2026-04-06 | 2026-05-08 | 32 | Steel Sub | 0%
7 | Ground Floor Slab | 2026-04-20 | 2026-05-15 | 25 | M. Evans | 0%
8 | Drainage & External Works | 2026-03-23 | 2026-06-12 | 81 | D. Murphy | 5%
9 | M&E First Fix | 2026-05-04 | 2026-06-05 | 32 | M&E Sub | 0%
10 | Cladding & Roofing | 2026-05-11 | 2026-06-19 | 39 | Cladding Sub | 0%
11 | Commissioning | 2026-06-15 | 2026-07-10 | 25 | M&E Sub | 0%
12 | Handover & Completion | 2026-07-13 | 2026-07-24 | 11 | M. Evans | 0%
13 |  |  |  | 0
14 |  |  |  | 0
15 |  |  |  | 0
16 |  |  |  | 0
17 |  |  |  | 0
18 |  |  |  | 0
19 |  |  |  | 0
20 |  |  |  | 0

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.