## Cover
EBRORA
ebrora.com
Look-Ahead Constraint Log
Identify and track materials, access, permit, design and information constraints blocking upcoming work — before they become programme delays.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2025 — All rights reserved

## Instructions
How to Use This Template — Look-Ahead Constraint Log
Step-by-Step Instructions
1. | Navigate to the 'Constraint Log' sheet. Enter the project name and current look-ahead period at the top.
2. | For each constraint, the Ref column (A) auto-generates a sequential ID (CL-001, CL-002, etc.) once a description is entered.
3. | Enter the Date Raised in column B and a clear description of the constraint in column C.
4. | Select the Constraint Type from the dropdown in column D: Materials, Access, Permit, Design, Information, Labour, or Other.
5. | Enter the Area or Zone affected in column E (e.g., 'Inlet Works', 'Zone 3 Earthworks', 'MCC Room').
6. | Set the Required By Date in column F — this is the date the constraint MUST be resolved to avoid programme impact.
7. | Column G calculates days until the constraint is due automatically. Negative values mean the constraint is overdue.
8. | Assign an Owner in column H — the person responsible for resolving the constraint.
9. | Update the Status dropdown in column I as constraints are progressed. The row will change colour to reflect the current state.
10. | Expand Optional Columns (K–N) to record the affected programme activity, estimated programme impact, resolution date, and resolution notes.
Colour Key
Overdue — Status is Open and the Required By Date has passed. Needs immediate action.
Due Soon — Status is Open and the Required By Date is within the next 14 days.
Closed — Constraint has been resolved. No further action required.
Escalated — Constraint cannot be resolved at site level and has been escalated to PM or client.
Light teal cells — User input / editable fields.
Tips
* | Review this log at every weekly look-ahead meeting. Any constraint with a Required By Date in the next 4 weeks should have a named owner and a clear action plan.
* | Be specific in column C. 'Waiting for materials' is not useful. 'Ductile iron pipe DN300 x 6m — 240 No. required at site by 14/04/25 for installation in Zone 3' is actionable.
* | Under NEC4, information constraints with programme impact should be raised as Early Warnings. Cross-reference the Early Warning number in the Notes column.

## Constraint Log
Project Name: |  |  | [Enter Project Name] |  |  |  | Look-Ahead Period: |  | [e.g. Wk 14–18 / Apr–May 2025] | ▸ Optional Fields — Click [+] to expand
Ref | Date Raised | Constraint Description | Type | Area / Zone | Required By | Days Until Due | Owner | Status | Notes | Activity Affected | Programme Impact (Days) | Date Resolved | Resolution Notes
CL-001 | 2025-03-10 | DN300 ductile iron pipe — 240Nr required for Zone 3 installation. Lead time 6 weeks from order. | Materials | Zone 3 — Inlet Main | 2025-04-14 | -344 | B. Kowalski | Open | Order placed 10/03. Confirm delivery date with supplier by 25/03. | Zone 3 Pipe Laying | 5
CL-002 | 2025-03-12 | Traffic Management permit (TM-0045) required for works on public highway — NMC submission outstanding. | Permit | Site Access Road | 2025-03-28 | -361 | J. Hargreaves | Open | Submitted to Highways 12/03. Chase weekly. | Haul Road Works | 3
CL-003 | 2025-03-05 | Temporary Works Design — propping scheme for existing culvert crossing. Designer instruction awaited. | Design | Culvert Crossing — Ch 0+340 | 2025-04-01 | -357 | S. Patel | Escalated | Raised as EW-007. Client PM aware. | Culvert Pipe Work | 7
CL-004 | 2025-02-18 | IFC drawing WRC-EL-0005 Rev B required before MCC installation can commence. | Information | MCC Room | 2025-03-21 | -368 | C. Roberts | Open | Drawing under client review — chased 11/03. Target issue 20/03. | MCC Installation | 2
CL-005 | 2025-01-20 | Confined space entry rescue team briefing — all operatives to complete before tank entry works. | Access | Inlet Tank Works | 2025-02-28 |  | T. Walsh | Closed | Completed 26/02. Records filed in H&S file. | Inlet Tank Works | 0 | 2025-02-26 | Rescue team briefing completed and signed off.
OPEN | 3 | CLOSED | 1 | ESCALATED | 1 | OVERDUE | 3 | DUE ≤14 DAYS | 0 | TOTAL | 5
Formulas:
Days Until Due = IF(AND([Required By]<>"",[Status]<>"Closed"),[Required By]-TODAY(),"")
Owner = COUNTIFS(I3:[Status, row above],"Open",F3:[Required By, row above],"<"&TODAY())
Notes = COUNTIFS(I3:[Status, row above],"Open",F3:[Required By, row above],">="&TODAY(),F3:[Required By, row above],"<="&(TODAY()+14))

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.