## Cover
EBRORA
ebrora.com
Two-Week Look-Ahead Programme
A rolling two-week short-term programme showing planned activities against 10 working days — the essential coordination tool for weekly site meetings.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Look-Ahead' sheet. Start by entering the Programme Start Date in cell B3 — this is the Monday of Week 1. All 10 day-column headers will update automatically.
2. | Fill in the Project Name, Prepared By, and Revision fields in the header block.
3. | Each row below the grid header represents one planned activity. Enter the Activity description, Trade/Package, who is Responsible, and set the Status.
4. | In the day-grid columns (F–O), use the dropdown to mark each day: P = Planned, A = Actual (completed), X = Delayed / not done.
5. | Cells turn teal for Planned, green for Actual, and red for Delayed — giving you a visual Gantt chart at a glance.
6. | Update the sheet daily: change P to A when work is completed, or P to X if it was delayed. Add new activities as they emerge.
7. | Expand the optional columns (click [+]) for Notes, Resources Required, and Predecessors.
Colour Key
Light teal cells — Editable input cells (left-hand columns).
Dark navy headers — Do not edit.
Teal (P) — Work is Planned for this day.
Green (A) — Work was completed (Actual).
Red (X) — Work was Delayed or not done.
Tips
Tip 1: | Update this at the start of every Monday. Print it for the weekly coordination meeting — it replaces lengthy discussion with a clear visual plan everyone can follow.
Tip 2: | At the end of each week, review any X (delayed) items and carry them forward. This gives you a running record of slippage that feeds into your delay analysis.
Tip 3: | Keep activities at a summary level — one row per trade per area, not individual tasks. The look-ahead is a coordination tool, not a full programme. Aim for 15–25 activities.

## Look-Ahead
TWO-WEEK LOOK-AHEAD PROGRAMME
Programme Start Date: | 2026-03-23 |  | Project Name: | Riverside Gateway Phase 2
Prepared By: | S. Patel |  | Revision: | Rev 08 — w/c 23 March 2026
Status: | [5 empty] | Planned: | 31 | Actual: | 11 | Delayed: | 2
▸ Optional — Click [+]
No. | Trade / Package | Activity Description | Responsible | Status | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | Notes | Resources Req'd | Predecessors
[5 empty] | Mon | Tue | Wed | Thu | Fri | Mon | Tue | Wed | Thu | Fri
[5 empty] | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03
1 | Groundworks | Excavation for pad foundations PF-07 to PF-12 | Briggs GW | On Track | [10 empty] | 20t excavator + 2 dumpers | 6 operatives + banksman | Piling complete | bar: 2026-03-23 to 2026-04-01
2 | Concrete | Concrete pour — ground beams GB-10 to GB-14 | McAlpine | On Track | [10 empty] | Boom pump req'd Wednesday | Pour gang + pump operator | Formwork & rebar sign-off | bar: 2026-03-26 to 2026-03-31
3 | Steelwork | Steel erection — Level 2 frame Zone A | SteelFix | At Risk | [10 empty] | Tower crane required all week | Erection gang (6) + crane | L1 frame complete + bolts torqued | bar: 2026-03-30 to 2026-04-03
4 | M&E | First fix containment — Level 1 risers | Northern M&E | On Track | [10 empty] | Unistrut & cable tray | 2 electricians + 1 plumber | Builders work holes formed | bar: 2026-03-23 to 2026-04-03
5 | Scaffolding | Scaffold erection — Block B south elevation | ScaffCo | Behind | [10 empty] | Delayed by wind Mon/Tue | Scaffold gang (4) | Access agreement signed | bar: 2026-03-23 to 2026-03-27
6 | Cladding | Rainscreen panel installation — Block A east | FacadeTech | Not Started | [10 empty] | Material delivery due Thu W2 | 3 cladders + MEWP | Scaffold complete + inspected | bar: 2026-04-01 to 2026-04-03
7 | Externals | Kerbing & drainage — car park Phase 1 | Briggs GW | On Track | [11 empty] | 3 operatives + mini digger | Formation complete & approved | bar: 2026-03-23 to 2026-04-02
KEY: | P = Planned | A = Actual | X = Delayed

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.