## Cover
EBRORA
ebrora.com
Key Dates & Milestone Register
Track every key date and milestone across your project — with variance monitoring, status RAG, and a visual 12-month calendar strip.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Milestone Register' sheet. The calendar strip at the top shows 12 months with milestone counts per month — giving a visual distribution of your key dates.
2. | Each row represents one milestone or key date. Enter the Ref, Description, select the Category, and set the Planned Date.
3. | As the project progresses, update the Forecast Date (your current best estimate) and eventually the Actual Date (when it was achieved or missed).
4. | The Variance column auto-calculates: Forecast minus Planned in days. Positive = late, negative = early, zero = on programme.
5. | Set the Status: On Track, At Risk, Missed, or Achieved. The conditional formatting provides instant RAG visibility.
6. | Expand optional columns for Owner, Dependencies, Linked Documents, and Notes.
Colour Key
Green — Status 'Achieved' or 'On Track'. Variance ≤ 0.
Amber — Status 'At Risk'. Variance 1–14 days.
Red — Status 'Missed'. Variance >14 days.
Calendar strip — Darker shading indicates more milestones that month.
Tips
Tip 1: | Review this register at every monthly progress meeting. It's your early warning system — a milestone forecast slipping by even a few days should trigger action, not just a note.
Tip 2: | Include contractual key dates (from the contract conditions), programme milestones (from your master programme), and client/regulatory dates. Categorise them so you can filter by type.
Tip 3: | When a milestone is missed, record the Actual Date and change Status to 'Missed'. Don't delete or adjust the Planned Date — the variance record is your audit trail for delay analysis.

## Milestone Register
KEY DATES & MILESTONE REGISTER
Project: | Riverside Gateway Phase 2 |  | Contract Start: | 2026-01-05 | Contract End: | 2027-03-31 | On Track: | 6
Prepared By: | S. Patel |  | Rev: | Rev 06 — March 2026 | Missed: | 0 | At Risk: | 4
MILESTONE CALENDAR | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
| 1 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0
▸ Optional Fields — Click [+] to expand
Ref | Milestone Description | Category | Planned Date | Forecast Date | Actual Date | Variance (days) | Status | Priority | Owner | Dependencies | Linked Document | Notes
KD-001 | Contract award / possession of site | Contractual | 2026-01-05 | 2026-01-05 | 2026-01-05 | 0 | Achieved | Critical | S. Patel |  | Contract doc ref | Complete on time
KD-002 | Piling works complete | Programme | 2026-03-15 | 2026-03-12 | 2026-03-12 | -3 | Achieved | High | Briggs GW | KD-001 |  | Completed 3 days early
KD-003 | Substructure complete (all foundations) | Programme | 2026-05-30 | 2026-05-30 |  | 0 | On Track | Critical | S. Patel | KD-002 | Programme Rev 08
KD-004 | Building control Stage 2 sign-off | Regulatory | 2026-04-15 | 2026-04-15 |  | 0 | On Track | High | J. Hartley | KD-003 partial | BC application ref | Inspector visit booked 10/04
KD-005 | Steel frame Level 3 complete | Programme | 2026-07-31 | 2026-08-14 |  | 14 | At Risk | Critical | SteelFix | KD-003 |  | Steel delivery 2 weeks late — mitigation plan in progress
KD-006 | Watertight building envelope | Programme | 2026-09-30 | 2026-10-07 |  | 7 | At Risk | Critical | FacadeTech | KD-005 |  | Dependent on steel frame — may slip if KD-005 not recovered
KD-007 | Section 278 highways works complete | Contractual | 2026-06-30 | 2026-06-30 |  | 0 | On Track | High | Briggs GW |  | S278 agreement
KD-008 | M&E first fix complete | Programme | 2026-10-31 | 2026-11-07 |  | 7 | At Risk | High | Northern M&E | KD-006 |  | Tracking 7 days late due to envelope dependency
KD-009 | Practical completion — Block A | Contractual | 2027-02-28 | 2027-03-07 |  | 7 | At Risk | Critical | S. Patel | All |  | 7 days forecast slip — recovery plan under review
KD-010 | Defects liability period ends | Contractual | 2028-02-28 | 2028-02-28 |  | 0 | On Track | Medium | S. Patel | KD-009 |  | 12 months from PC

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.