## Cover
EBRORA
ebrora.com
Sectional Completion &
Milestone Trigger Matrix
Track project sections through completion milestones with trigger criteria,
planned vs actual dates, and overall readiness assessment.
This is a free template from Ebrora.
For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Milestone Matrix' sheet. Rows = project sections/areas. Columns = completion milestones.
2. | Each section has TWO rows: 'Planned' (target date) and 'Actual' (achieved date or status).
3. | Milestones progress left to right: Design → Construction → Testing → Commissioning → Process Proving → Handover → Sectional Completion.
4. | For Planned rows, enter the target date for each milestone. For Actual rows, enter the achieved date or select a status.
5. | The Section Readiness % auto-calculates based on how many milestones have actual dates (i.e., are complete).
6. | The Milestone Completion % row at the bottom shows progress across all sections for each milestone.
7. | Use this matrix at programme reviews to visualise which sections are ahead/behind across all milestones.
Colour Key
Light teal = Input cells (dates)
Green = Milestone achieved (actual date entered)
Amber = In progress (planned date in future)
Red = Overdue (planned date past, no actual date)
Tips
Tip 1: | This matrix is the single best tool for sectional completion meetings. It shows the whole project on one page.
Tip 2: | Sectional completion triggers commercial milestones (liquidated damages, payment milestones). Get the planned dates right.
Tip 3: | Update actual dates the day they're achieved, not retrospectively. The audit trail matters for contractual milestone claims.

## Milestone Matrix
Section Ref | Section Name | Plan/ Actual | Design Complete | Construction Complete | Testing Complete | Commissioning Complete | Process Proving | Handover Ready | Sectional Completion | Section Readiness %
SC-01 | Inlet Works | Planned | 2025-06-01 | 2025-12-15 | 2026-02-01 | 2026-03-15 | 2026-06-15 | 2026-07-01 | 2026-07-15
|  | Actual | 2025-05-28 | 2025-12-20 | 2026-02-10 | 2026-03-20 |  |  |  | 57.14%
SC-02 | Storm Water | Planned | 2025-08-01 | 2026-02-28 | 2026-04-15 | 2026-05-30 | 2026-08-30 | 2026-09-15 | 2026-09-30
|  | Actual | 2025-08-15 | 2026-03-10 | [5 empty] | 28.57%
SC-03 | Secondary Treatment | Planned | 2025-07-01 | 2026-01-31 | 2026-03-31 | 2026-05-15 | 2026-08-15 | 2026-09-01 | 2026-09-15
|  | Actual | 2025-07-05 | 2026-02-05 | 2026-04-01 |  |  |  |  | 42.86%
SC-04 | Tertiary Treatment | Planned | 2025-09-01 | 2026-03-31 | 2026-05-15 | 2026-06-30 | 2026-09-30 | 2026-10-15 | 2026-10-30
|  | Actual | 2025-09-10 | [6 empty] | 14.29%
SC-05 | Sludge Treatment | Planned | 2025-10-01 | 2026-04-30 | 2026-06-15 | 2026-07-31 | 2026-10-31 | 2026-11-15 | 2026-11-30
|  | Actual | 2025-10-15 | [6 empty] | 14.29%
SC-06 | Electrical & SCADA | Planned | 2025-08-15 | 2026-03-15 | 2026-05-01 | 2026-06-15 | 2026-09-15 | 2026-10-01 | 2026-10-15
|  | Actual | 2025-08-20 | 2026-03-20 | 2026-05-05 |  |  |  |  | 42.86%
SC-07 | Site-Wide Civils | Planned | 2025-06-15 | 2026-05-31 | 2026-06-30 | 2026-07-15 |  | 2026-08-01 | 2026-08-15
|  | Actual | 2025-06-20 | [6 empty] | 16.67%
MILESTONE COMPLETION % |  |  | 100% | 57.14% | 42.86% | 14.29% | 0% | 0% | 0% | 30.95%
SUMMARY | Total Sections: | 7 | 100% Complete: | 0 | Overall Readiness: | 30.95%

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.