## Cover
EBRORA
ebrora.com
Shutdown / Outage Works Schedule
An hour-by-hour works schedule for planned shutdowns and outages — with shift-based timeline, critical path tracking, and task sequencing.
This is a free template from Ebrora. For our full range of professional-grade construction management tools, visit ebrora.com
© Ebrora 2026 — All rights reserved

## Instructions
How to Use This Template
Getting Started
1. | Open the 'Outage Schedule' sheet. Fill in the outage details at the top: system being shut down, planned start/end, duration, and the critical constraint.
2. | The timeline grid shows 24 hours split into Day Shift (06:00–18:00, yellow tint) and Night Shift (18:00–06:00, blue tint).
3. | List each task on the left: Sequence number, Task Description, Trade/Team, Duration (hrs), and whether it's on the Critical Path.
4. | In the hourly grid, mark each hour the task is active using the dropdown: P = Planned, A = Actual, X = Delayed, H = Hold Point.
5. | Hold Points (H) are mandatory inspection or sign-off gates — the next task cannot start until the hold point is released.
6. | Update the Status column as work progresses: Not Started, In Progress, Complete, or Delayed.
Colour Key
Yellow-tinted columns — Day Shift hours (06:00–18:00).
Blue-tinted columns — Night Shift hours (18:00–06:00).
Teal (P) — Planned work for this hour.
Green (A) — Work completed (Actual).
Red (X) — Task delayed.
Dark Navy (H) — Hold Point — requires sign-off before proceeding.
Tips
Tip 1: | Plan backwards from the reconnection time. The outage window is fixed — every hour counts. Build in contingency but know where it sits.
Tip 2: | Print this at A3 landscape and pin it to the wall at the works control point. Everyone involved should be able to see the live status at a glance.
Tip 3: | Assign one person to update this schedule in real time during the outage. Delays cascade quickly — if you lose visibility, you lose control.

## Outage Schedule
SHUTDOWN / OUTAGE WORKS SCHEDULE
System: | Incoming HV Supply — Main Transformer T1 |  | Outage Ref: | OUT-2026-007 | Date: | 2026-04-04
Planned Start: | 6:00 | Planned End: | 22:00 | Duration: | 16 hours
Controller: | T. Brennan (SAP) | Critical Path: | Isolation → Cable pull → Termination → Testing → Re-energise |  |  | Tasks: |  |  | 14 |  | Complete: |  | 5
Seq | Task Description | Trade / Team | Dur (hrs) | Critical? | Status | DAY SHIFT (06:00 — 18:00) | [11 empty] | NIGHT SHIFT (18:00 — 06:00)
[6 empty] | 06 | 07 | 08 | 09 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 00 | 01 | 02 | 03 | 04 | 05
[6 empty] | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00 | :00
1 | Site safety briefing & toolbox talk | All trades | 1 | No | Complete | bar: DAY SHIFT (06:00 — 18:00) 06
2 | HV isolation & LOTO — confirm dead | HV Auth. Person | 1 | Yes | Complete | bar: DAY SHIFT (06:00 — 18:00) 07
3 | Issue isolation certificate & permits | SAP / T. Brennan | 0.5 | Yes | Complete | bar: DAY SHIFT (06:00 — 18:00) 08
4 | HOLD POINT — Isolation confirmed |  | 0 | Yes | Complete | bar: DAY SHIFT (06:00 — 18:00) 08
5 | Strip existing cable terminations | Electrical | 2 | Yes | Complete | bar: DAY SHIFT (06:00 — 18:00) 09 to DAY SHIFT (06:00 — 18:00) 10
6 | Pull new 3-core 185mm XLPE cable (120m) | Cable team | 3 | Yes | In Progress | bar: DAY SHIFT (06:00 — 18:00) 11 to DAY SHIFT (06:00 — 18:00) 13
7 | HOLD POINT — Cable pull complete, visual inspection |  | 0 | Yes | Not Started | bar: DAY SHIFT (06:00 — 18:00) 14
8 | Terminate & gland at transformer end | Electrical | 2 | Yes | Not Started | bar: DAY SHIFT (06:00 — 18:00) 15 to DAY SHIFT (06:00 — 18:00) 16
9 | Terminate & gland at switchboard end | Electrical | 2 | Yes | Not Started | bar: DAY SHIFT (06:00 — 18:00) 17 to NIGHT SHIFT (18:00 — 06:00) 18
10 | HOLD POINT — Terminations inspected |  | 0 | Yes | Not Started | bar: NIGHT SHIFT (18:00 — 06:00) 19
11 | Insulation resistance & continuity testing | Test engineer | 2 | Yes | Not Started | bar: NIGHT SHIFT (18:00 — 06:00) 20 to NIGHT SHIFT (18:00 — 06:00) 21
12 | Phase rotation & HV pressure test | Test engineer | 1 | Yes | Not Started | bar: NIGHT SHIFT (18:00 — 06:00) 22
13 | Remove LOTO, re-energise, load test | HV Auth. Person | 1 | Yes | Not Started | bar: NIGHT SHIFT (18:00 — 06:00) 23
14 | Reinstate barriers, clear site, handback | All trades | 1 | No | Not Started | bar: NIGHT SHIFT (18:00 — 06:00) 00
KEY: | P = Planned | A = Actual | X = Delayed | H = Hold Point

## Terms of Use (hidden)
EBRORA — TERMS OF USE
This template is provided free of charge by Ebrora (ebrora.com) for personal and professional use.
1. LICENCE: You may use this template for your own projects. You may not resell, redistribute, or claim authorship of this template.
2. NO WARRANTY: This template is provided "as is" without warranty of any kind. Ebrora accepts no liability for errors, omissions, or losses arising from use of this template.
3. INTELLECTUAL PROPERTY: All design, layout, branding, and content remain the intellectual property of Ebrora.
4. MODIFICATIONS: You may modify this template for your own use. Modified versions may not be distributed or sold.
5. ATTRIBUTION: If you share outputs generated using this template, attribution to Ebrora (ebrora.com) is appreciated but not required.
6. SUPPORT: For queries, feedback, or to report errors, contact support@ebrora.com.
For our full range of professional construction management tools, visit ebrora.com.